JUABESO DISTRICT ASSEMBLY

ANNUAL ACTION PLAN 2023

Prepared by DPCU

October, 2022

SUMMARY OF PROJECTS

| DEVELOPMENT DIMENSION | NUMBER OF ACTIVITIES |
| --- | --- |
| ECONOMIC DEVELOPMENT | 3 |
| SOCIAL DEVELOPMENT | 18 |
| ENVIRONMENT,INFRASTRUCTURE AND HUMAN SETTLEMENT | 12 |
| GOOD GOVERNANCE AND PUBLIC ACCOUNTABILITY | 1 |
| TOTAL | 34 |
| GRAND TOTAL ROJECTS AND ROGRAMMES | 121 |

Composite Annual Action Plan 2023

| Programme (PBB) | Sub-Programme (PBB) |  | Broad Activities |  | Location |  | Timeframe (2023) |  |  |  |  | Cost |  |  | Programme Status |  |  | Implementing Institution/Department |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 | Q4 | GoG | IGF/ABFA | Others | New | Ongoing |  | Lead |  | Collaborating |  |  |
| DEVELOPMENT DIMENSION: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Strong and Resilient Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management administration | Finance and Revenue Mobilization |  | Revise and update data on revenue sources |  | Juaboso |  |  |  |  |  |  | 10,000.00 |  |  | New | - |  | Finance Dept |  | MLGDRD |  |  |
| Management administration | Finance and Revenue Mobilization |  | Organize fresher training for revenue collectors |  | Juaboso |  |  |  |  |  |  | 13,000.00 |  | - | New | - |  | DBA, DFO |  | Central Admin |  |  |
| Focus area: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize social media marketing training for women and men |  | District wide |  |  |  |  |  |  |  | 6,000.00 |  |  | On-going |  | BAC |  | JDA, GEA, MOTI |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organise stakeholders forum on business counselling |  | Juaboso |  |  |  |  |  |  | 4,500.00 |  |  |  | On-going |  | BAC |  | JDA, GEA, MOTI |  |  |
| Economic Development | Trade, tourism and industrial development |  | Construction of 2No 12Unit Market sheds |  | Boinzan |  |  |  |  |  |  | 300,000.00 |  |  | New |  |  | Central Admin |  | JDA |  |  |
| Economic Development | Trade, tourism and industrial development |  | Construction of 2No 12Unit Market sheds |  | Sayerano |  |  |  |  |  |  | 20,000.00 |  |  |  | On-going |  | Central Admin |  | JDA |  |  |
| Economic Development | Trade, tourism and industrial development |  | Construction of 1No 6Unit Market sheds |  | Proso Kofikrom |  |  |  |  |  |  | 15,000.00 |  |  |  | On-going |  | Central Admin |  | JDA |  |  |
| Economic Development | Trade, tourism and industrial development |  | Provide support for oil palm processing expellers |  | Proso, Antwikrom, Bonsu Nkwanta, Africa, kwasi Adaekrom |  |  |  |  |  |  | 18,000.00 |  |  | New |  |  | Central Admin |  | JDA |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize 1 Training session on Credit Management |  | Juaboso |  |  |  |  |  |  | 5,200.00 |  |  |  | On-going |  | BAC |  | Trobenbos Ghana |  |  |
| Economic Development | Trade, tourism and industrial development |  | Formalize Business registration and certification |  | District wide |  |  |  |  |  |  | 4,500.00 |  |  |  | On-going |  | BAC |  | GEA/ Clients |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize 2 training workshop on technology improvement in cosmetics and bead making |  | Selected communities |  |  |  |  |  |  | 15,000.00 |  |  |  | On-going |  | BAC |  | GEA/DA |  |  |
| Focus area: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agricultural Development | Training of staff and farmers on improved agricultural technology, FBO formation, HIV/AIDS and malaria prevention, etc. |  |  | 20 Communities |  |  |  |  |  |  | 2,800.00 | 3,000.00 | 15,000.00 |  | On-going |  | Agric. dept |  | RADU, GHS, Researchers, MAG |  |  |
| Economic Development | Agricultural Development | Organization of community and district planning session |  |  | Juaboso |  |  |  |  |  |  |  |  | 5,050.00 |  | On-going |  | Agric. dept |  | RADU, Research, NGOs, DA, Farmers |  |  |
| Economic Development | Agricultural Development | Establish 5 yield plots for the 5 major crops |  |  | 10 Communities |  |  |  |  |  |  | 4,000.00 |  | 1,000.00 |  | On-going |  | Agric. dept |  | SRID, RADU Farmers |  |  |
| Economic Development | Agricultural Development | Maintenance of official vehicle and motorbikes |  |  | Juaboso |  |  |  |  |  |  | 7,000.00 |  |  |  | Onging |  | Agric. dept |  | D.A |  |  |
| Economic Development | Agricultural Development | Organization of District Farmers Day |  |  | District wide |  |  |  |  |  |  |  |  | 80,000.00 |  | On-going |  | Agric. dept |  | D.A |  |  |
| Economic Development | Agricultural Development | Carry out Coconut Plantation Project |  |  | Selected communities |  |  |  |  |  |  | 100,000.00 |  |  |  | On-going |  | D.A |  | GHA. PRDT SAFETY NET PHS II |  |  |
| Economic Development | Agricultural Development | Maintenance of office complex and DDA residence |  |  | Juaboso |  |  |  |  |  |  |  | 5,000.00 |  | New |  |  | Agric. dept |  | D.A |  |  |
| Economic Development | Agricultural Development | Acquisition of equipment for SRID activities |  |  | Juaboso |  |  |  |  |  |  | 5,000.00 |  |  | New |  |  | Agric. dept |  | D.A |  |  |
| Economic Development | Agricultural Development | Carry out Oil Palm plantation Project |  |  | Selected communities |  |  |  |  |  |  | 150,000.00 |  |  |  | On-going |  | D.A |  | GHA. PRDT SAFETY NET PHS II |  |  |
| Economic Development | Agricultural Development | Supply of farmer inputs under (PFJ) |  |  | District wide |  |  |  |  |  |  | 70,000,00 |  |  | New |  |  | Agric. dept |  | D.A |  |  |
| Economic Development | Agricultural Development | Undertake capacity building training on climate change mitigation strategies for women in crop production |  |  | District wide |  |  |  |  |  |  | 10,000 |  | 5,000.00 | New |  |  | GDO |  | Agric. dept |  |  |
| Development Dimension: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Education and Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organise Science, Technology, Mathematics, and Innovative Education (STMIE) clinics |  |  |  | Juaboso |  |  |  |  |  | 3,000.00 | 3,000.00 |  |  | On-going |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Support the District Education Oversight Committee to monitor teaching and learning in schools |  |  |  | Juaboso |  |  |  |  |  | 4,500.00 |  |  |  | On-going |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organisation of Independence day celebration |  |  |  | Juaboso |  |  |  |  |  | 43,000.00 |  |  |  | On-going |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organise reading festivals to create awareness and encourage children to read |  |  |  | Juaboso |  |  |  |  |  |  | 5,000.00 |  |  | On-going |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organise mock examination for JHS three students |  |  |  | District wide |  |  |  |  |  | 20,000.00 |  |  |  | On-going |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1 No. 3 Unit Classroom Block , 3 KVIP & urinal |  |  |  | Brekorm |  |  |  |  |  | 330,000.00 |  |  |  | On-going |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1 No. 3 Unit Classroom Block , 3 KVIP & urinal |  |  |  | Danyame |  |  |  |  |  | 34,571.00 |  |  |  | On-going |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1 No. 6 Unit Classroom Block , 3 KVIP & urinal |  |  |  | Benchima |  |  |  |  |  | 62,000.00 |  |  |  | On-going |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1 No. 6 Unit Classroom Block |  |  |  | Komeamaa |  |  |  |  |  | 14,000.00 |  |  |  | On-going |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1 No. 6 Unit Classroom Block , 3 KVIP & urinal |  |  |  | Mantukwa |  |  |  |  |  | 8,000.00 |  |  |  | On-going |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1 No. 6 Unit Classroom Block |  |  |  | Yawagyimkrom |  |  |  |  |  | 35,000.00 |  |  |  | On-going |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1 No. 6 Unit Classroom Block |  |  |  | Dominibo |  |  |  |  |  | 40,000.00 |  |  |  | On-going |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1 No. 6 Unit Classroom Block |  |  |  | Eteso |  |  |  |  |  | 60,000.00 |  |  |  | On-going |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Renovation of 1 No. 6 Unit Classroom Block |  |  |  | Sayerano |  |  |  |  |  | 304,695.50 |  |  |  | On-going |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1 No. 3 Unit Classroom block & Ancillary facility |  |  |  | Nkra |  |  |  |  |  | 303,227 |  |  | New |  |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Supply of 45 dual desks and 150 mono desks for basic schools |  |  |  | Nkra |  |  |  |  |  | 59,000 |  |  | New |  |  | GES |  | JDA |  |  |
| Focus area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Development | Support the organisation of inter district sports festival |  |  |  | Juaboso |  |  |  |  |  | 15,000.00 |  |  | New |  |  | GES |  | JDA |  |  |
| Social Services Delivery | Education and Youth Development | Reactivation and completion of Juaboso Town Park |  |  |  | Juaboso |  |  |  |  |  | 50,000.00 |  |  |  | On-going |  | GES |  | JDA |  |  |
| Focus area: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Construction of 1N0. CHPS Compound |  |  | Sayerano |  |  |  |  |  |  | 30,000.00 |  |  |  | On-going |  | District Health |  | DA |  |  |
| Social Services Delivery | Health Delivery | Construction of 1No. 4Unit Nurses Quarters |  |  | Bonsu Nkwanta |  |  |  |  |  |  | 26,000.00 |  |  |  | On-going |  | District Health |  | DA |  |  |
| Social Services Delivery | Health Delivery | Construction of 1No. CHPS Compound |  |  | Juaboso Nkwanta |  |  |  |  |  |  | 430,000.00 |  |  |  | On-going |  | District Health |  | DA |  |  |
| Social Services Delivery | Health Delivery | Construction of 1N0. CHPS Compound |  |  | Keyfas |  |  |  |  |  |  | 350,000.00 |  |  | New |  |  | District Health |  | DA |  |  |
| Social Services Delivery | Health Delivery | Organise T.B Case detection exercise at the end of 2022 |  |  | District wide |  |  |  |  |  |  | 15,000.00 |  |  | New |  |  | District Health |  | DA |  |  |
| Social Services Delivery | Health Delivery | Intensify public education on causes, prevention and control of Malaria |  |  | District wide |  |  |  |  |  |  | 5,500.00 |  |  | New |  |  | District Health Dir |  | DA |  |  |
| Social Services Delivery | Health Delivery | Undertake demonstration activity of best cooking practices at weighing centers for breast feeding mothers. |  |  | Selected Centers |  |  |  |  |  |  | 15,000 |  |  | New |  |  | GDO |  | DHD |  |  |
| Social Services Delivery | Health Delivery | Construction of 1No. 4Unit Nurses Quarters |  |  | Bonsu Nkwanta |  |  |  |  |  |  | 26,000.00 |  |  |  | On-going |  | District Health |  | DA |  |  |
| Social Services Delivery | Health Delivery | Construction of 1No. CHPS compound |  |  | Sayerano |  |  |  |  |  |  | 30,000.00 |  |  |  | On-going |  | District Health |  | DA |  |  |
| Focus area: HIV/AIDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | HIV/AIDS | Organize 95-95-95 campaigns in selected communities |  |  | District-wide |  |  |  |  |  |  | 6,000 |  |  | New |  |  | District Health Dir |  | DA |  |  |
| Social Services Delivery | HIV/AIDS | Ensure celebration of World HIV/AIDS day and Know your status Campaigns |  |  | District-wide |  |  |  |  |  |  | 7,500 |  |  | New |  |  | District Health Dir |  | DA |  |  |
| Social Services Delivery | HIV/AIDS | Organize radio sensitization on the effect of stigmatization against PLWHA |  |  | District-wide |  |  |  |  |  |  | 5,500 |  |  |  | Ongoing |  | District Health Dir |  | DA |  |  |
| Social Services Delivery | Health Delivery | Provide support for organization of health education on communicable and non-communicable diseases on local FM station |  |  | District-wide |  |  |  |  |  |  | 3,000.00 |  |  | New |  |  | District Health Dir |  | DA |  |  |
| Focus area: Environmental and Sanitation Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Organized medical screening exercise |  |  | District wide |  |  |  |  |  |  | 6,000.00 |  |  |  | On going |  | DEHU |  | DA |  |  |
| Social Services Delivery | Health Delivery | Facilitate the organization of monthly national sanitation day |  |  | District wide |  |  |  |  |  |  | 60,000 |  |  |  | On going |  | DEHU |  | DA |  |  |
| Social Services Delivery | Health Delivery | Quarterly pushing/leveling of final dumping site |  |  | District wide |  |  |  |  |  |  | 80,000.00 |  |  |  | On going |  | DEHU |  | DA |  |  |
| Social Services Delivery | Health Delivery | Undertake premises inspection |  |  | District wide |  |  |  |  |  |  | 3,000.00 |  |  |  | On going |  | DEHU |  | DA |  |  |
| Focus area: Population Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Population management | Sensitize people on reproductive health to increase family planning acceptor rate |  |  | District-wide |  |  |  |  |  |  |  | 6,000.00 |  | New |  |  | GHS |  | Birth & Death department |  |  |
| Social Services Delivery | Population management | Organize radio and community information center discussions on birth and death registration |  |  | District-wide |  |  |  |  |  |  |  | 6,000.00 |  |  | On-going |  | Birth & Death department |  | GHS, communities, traditional and religious leaders |  |  |
| Social Services Delivery | Population management | Registration of births and deaths in the district |  |  | District-wide |  |  |  |  |  |  |  | 4,500.00 |  | New |  |  | Birth & Death department |  | GHS, |  |  |
| Focus area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Child development and protection | Create 4 awareness campaigns for parents to desist from child neglect, discrimination, exposure to physical and moral threats |  |  | District-wide |  |  |  |  |  |  |  | 1,400.00 |  |  | Ongoing |  | SWCD Central Admin |  | CRI, Mondelez ILO |  |  |
| Social Services Delivery | Child development and protection | Promote public-private partnerships in the provision of alternative care services |  |  | 20 Communities |  |  |  |  |  |  | 2,200.00 |  |  |  | Ongoing |  | SWCD Central Admin |  | CRI, Mondelez ILO |  |  |
| Social Services Delivery | Child development and protection | Formation of four (4) new women groups and monitoring twelve (12) of the existing groups and to link them to Additional Livelihoods Training |  |  | District-wide |  |  |  |  |  |  | 2,550.00 |  |  |  | Ongoing |  | SWCD Central Admin |  | Planning Unit / Gender Desk Officer |  |  |
| Disability and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | Organise 4 Community durbars to assist to prepare their community action plan quarterly |  |  | Four (4) communities |  |  |  |  |  |  | 2,500.00 |  |  |  | Ongoing |  | SWCD Central Admin |  | NGOs |  |  |
| Social Services Delivery | Social Welfare and Community Development | Create 4awareness campaign on voluntary participation in community initiated projects |  |  | 20 Communities |  |  |  |  |  |  | 2,642.00 |  |  |  | Ongoing |  | SWCD Central Admin |  | NGOs |  |  |
| Social Services Delivery | Gender Empowerment | Organise radio talk show programmes to advocate for girl child education |  |  | 5 communities |  |  |  |  |  |  | 1,500.00 |  |  |  | Ongoing |  | SWCD Central Admin |  | NGOs |  |  |
| Social Services Delivery | Disability and Development | Facilitate the registration and renewal of 400 vulnerable groups such as PWDs, LEAP beneficiaries etc. onto NHIS |  |  | District wide |  |  |  |  |  |  | 1,500.00 |  |  |  | Ongoing |  | SWCD Central Admin |  | NGOs |  |  |
| Social service Delivery | Disability and Development | To support and to train 60% of registered PWDs in the District to engage in economic and business ventures |  |  | District wide |  |  |  |  |  |  | 2,000.00 |  |  |  | Ongoing |  | SWCD Central Admin |  | NGOs |  |  |
| Poverty and Inequality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Gender Empowerment | To Establish four (4) Village Savings and Loans Associations (VSLA) |  |  | District wide |  |  |  |  |  |  | 1,000.00 |  |  |  | Ongoing |  | SWCD Central Admin |  | NGOs |  |  |
| Social Services Delivery | Gender Empowerment | To facilitate 2 community dialogue and school outreaches on redefining gender roles to harness women participation in politics, science and technology |  |  | District wide |  |  |  |  |  |  | 2,000.00 |  |  |  | New |  | GDO |  | NGOs SWCD Central Admin GES |  |  |
| Social Services Delivery | Gender Empowerment | Carry out sensitization of climate change vulnerabilities in 5 communities and school |  |  | District wide |  |  |  |  |  |  | 1,500.00 |  |  |  | New |  | SWCD Central Admin |  | NGOs Agric. dept |  |  |
| Social Services Delivery | Social Welfare and Community Development | To organize training workshops for the NGOs working within the District to understand the need to be registered with the department |  |  | Juaboso |  |  |  |  |  |  | 3,000.00 |  |  |  | Ongoing |  | SWCD Central Admin |  | NGOs |  |  |
| Development Dimension: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Protected Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out tree planting exercise in schools and other institutions |  |  | District wide |  |  |  |  |  |  | 13,000.00 |  |  | New |  | Forestry Commission |  | DA |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out afforestation of depleted forest reserve |  |  | District wide |  |  |  |  |  |  | 65,000.00 |  |  | New |  | Forestry Commission |  | DA |  |  |  |
| Focus Area: Water Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Water resources management | Construct 10No. new boreholes |  |  | District wide |  |  |  |  |  |  | 350,000.00 |  |  | New |  | DWE |  | CWSA, DP |  |  |  |
| Environment, Infrastructure and Human Settlements | Water resources management | Maintain broken down boreholes |  |  | District wide |  |  |  |  |  |  | 170,000.00 |  |  | New |  | DWE |  | CWSA, DP |  |  |  |
| Environment, Infrastructure and Human Settlements | Water resources management | Extension of water to 8 seater W/C |  |  | Juaboso |  |  |  |  |  |  | 35,550.00 |  |  |  | Ongoing | DWE |  | CWSA, DP |  |  |  |
| Environment, Infrastructure and Human Settlements | Water resources management | Completion of 6No. Borehole |  |  | Onyinakrom, Asoredanho, Pusi, Camp 5,Ensonyameye,Yiemfo |  |  |  |  |  |  | 60,000.00 |  |  |  | Ongoing | DWE |  | CWSA, DP |  |  |  |
| Environmental and Sanitation Management | Water resources management | Train WATSAN committees and for and new ones and train them |  |  | 20 Communities |  |  |  |  |  |  |  | 20,00.00 |  | New |  | DWST |  | CWSA, DP |  |  |  |
| Key Focus Area: Climate variability and change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Organised awareness creation workshop on climate change for Assembly Members, staff and other stakeholders |  |  | District wide |  |  |  |  |  |  | 14,000.00 |  |  | New |  | JDA |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Supply 8,000 Oil Palm seedlings to 300 farmers and 20,000 oil palm seedlings to 80 farmers. |  |  | District wide |  |  |  |  |  |  | 18,000.00 | 20,000.00 |  | New |  | MoFA |  | JDA |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Train male and female farmers on climate-smart agribusiness |  |  | District wide |  |  |  |  |  |  | 10,000.00 |  |  | New |  | MoFA |  | JDA |  |  |  |
| Focus area: Transport Infrastructure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance and reshaping of 125km feeder roads |  |  | District Wide |  |  |  |  |  |  | 305,000.00 |  |  |  |  | DWE |  | Central Admi |  |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance of Assembly vehicle |  |  | Juaboso |  |  |  |  |  |  | 36,000.00 |  |  |  |  | DWE |  | Central Admi |  |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Maintenance of Assembly grader |  |  | Juaboso |  |  |  |  |  |  | 88,000.00 |  |  |  |  | DWE |  | Central Admi |  |  |  |
| Focus area: Infrastructure and Infrastructure Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure delivery | Rehablitation and completion of DCD’s Bungalow |  |  | Juaboso |  |  |  |  |  |  | 23,018.00 |  |  |  | On-going | DWE |  | Central Admi |  |  |  |
| Management and administration | General administration | Maintenance of office laptops, printers and photo copiers |  |  | Juaboso |  |  |  |  |  |  | 25,000 | 10,000 | - | - | On-going | ICT officer |  | Central Admin |  |  |  |
| Management and administration | General administration | Maintenance of official buildings and accommodation |  |  | Juaboso |  |  |  |  |  |  | 45,000 | 20,000 | - | New | - | JDA |  | MLGDRD |  |  |  |
| Focus area: Energy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Procure/ Maintain 600 Street light bulbs |  |  | District-wide |  |  |  |  |  |  | 140,000 | 10,000 |  | New |  | JDA, ECG |  | Energy Ministry |  |  |  |
| Infrastructure Delivery and Management | Infrastructure delivery | Preparation of 2 spatial Plans (Planning Schemes/ Layout) |  |  | Bonsu Nkwanta & Proso-Kofikrom |  |  |  |  |  |  | 45,000.00 |  |  | New |  | Physical Planning Dept |  | JDA |  |  |  |
| Infrastructure Delivery and Management | Infrastructure delivery | Organize Spatial Planning Committee (SPC) Meetings Spatial Planning Technical Su-Committee (SPTSC) Meetings |  |  | Juaboso |  |  |  |  |  |  | 53,000.00 |  |  |  | ongoing | Physical Planning Dept |  | JDA |  |  |  |
| Infrastructure Delivery and Management | Infrastructure delivery | Prepare Thematic Maps |  |  | District Wide |  |  |  |  |  |  | 4,800.00 |  |  |  | On-going | Physical Planning Dept |  | JDA |  |  |  |
| Infrastructure Delivery and Management | Infrastructure delivery | Embark on Public sensitization on efficient land use and management |  |  | District wide |  |  |  |  |  |  | 7,800.00 |  |  |  | On-going | Physical Planning Dept |  | JDA |  |  |  |
| Infrastructure Delivery and Management | Infrastructure delivery | Ensure proper inventorisation of public lands |  |  | District wide |  |  |  |  |  |  | 7,800.00 |  |  |  | On-going | Physical Planning Dept |  | JDA |  |  |  |
| Infrastructure Delivery and Management | Infrastructure delivery | Procure aerial images for four communities |  |  | Asempanaye/ Proso-Kofikrom/ Antobia/ Sayerano |  |  |  |  |  |  | 20,000.00 |  |  | New |  | Physical Planning Dept |  | JDA |  |  |  |
| Infrastructure Delivery and Management | Infrastructure delivery | Compile Street Names from four communities Prepare Address Maps for three communities Procure 20 signage Upload address maps on the DlRev Software for three communities |  |  | Antobia/ Proso-Kofikrom/ Sayerano Antobia/ Asempanaye/ Proso-Kofikrom/ Bonsu Nkwanta Proso-Kofikrom/ Asempanaye |  |  |  |  |  |  | 32,000.00 |  |  | New |  | Physical Planning Dept |  | JDA |  |  |  |
| Infrastructure Delivery and Management | Infrastructure delivery | Procure 1 No. Motorbike for fieldwork |  |  | Juaboso |  |  |  |  |  |  | 10,000.00 |  |  | New |  | Physical Planning Dept |  | JDA |  |  |  |
| Focus area: Human Settlements and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Organize radio sensitization on building permit |  |  | Juaboso |  |  |  |  |  |  | 5,000.00 |  |  |  | On-going | Works/Planning |  | LUSPA |  |  |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Expansion of street naming and property addressing system |  |  | Bonsu Nkwanta Boinzan |  |  |  |  |  |  | 40,000.00 |  |  |  | On-going | Works/Planning |  | Central Admi |  |  |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Enforce planning and building regulations |  |  | District-wide |  |  |  |  |  |  | 6,000.00 |  |  |  | On-going | Works/Planning |  | Central Admi |  |  |  |
| Focus area: Disaster Prevention and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Hold disaster management committee meeting |  |  | District-wide |  |  |  |  |  |  | 4,500 |  |  | New |  | NADMO |  | Central Admin |  |  |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Reformation of DVG’s |  |  | District-wide |  |  |  |  |  |  | 5,000 |  | 5,000 | New |  | NADMO |  | Central Admin |  |  |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Organize anti-bush fire campaign on radio and communities |  |  | District-wide |  |  |  |  |  |  | 8,000 |  |  | New |  | NADMO, GNFS |  | Central Admi |  |  |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Form and train disaster clubs |  |  | Schools in the district |  |  |  |  |  |  |  | 9,500.00 |  | New |  | NADMO, GNFS |  | Central Admi |  |  |  |
| Development Dimension: Governance, Corruption and Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Local Government and Decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Organize sub-committee, general assembly meeting, and management meetings |  |  | Juaboso |  |  |  |  |  |  | 60,000.00 |  |  | New |  | Central Admi |  |  |  | MLGDRD NALAG |  |
| Management and administration | General administration | Prepare and gazette Assembly by-laws and fee fixing resolution |  |  | Juaboso |  |  |  |  |  |  | 35,000.00 |  |  | New |  | Central Admi |  |  |  | MLGDRD NALAG |  |
| Management and administration | General administration | Procure and supply office logistics and equipment |  |  | Juaboso |  |  |  |  |  |  | 30,000.00 |  |  | New |  | Procurement officer |  |  |  | Central Admi, stores |  |
| Management and administration | General administration | Prepare and submit monthly and quarterly progress reports |  |  | Juaboso |  |  |  |  |  |  | 10,000.00 |  |  |  | Ongoing | DPCU |  |  |  |  |  |
| Management and administration | General administration | Organised quarterly Audit Committee meetings |  |  | Juaboso |  |  |  |  |  |  | 24,000.00 |  |  |  | Ongoing | Audit committee |  |  |  |  |  |
| Management and administration | General administration | Provide financial support for anti-corruption activities |  |  | Juaboso |  |  |  |  |  |  | 10,000.00 |  |  | New |  | NACAP Desk Officer |  |  |  | Central Admi, CHRAG, NCCE |  |
| Focus area: Security and public safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Construction of police post at Juaboso Benchima Highway |  |  | Juaboso |  |  |  |  |  |  | 39,000.00 |  |  | New |  | Central Admi |  |  |  |  | GPS |
| Management and administration | General administration | Provide financial support for conflict and DISEC activities |  |  | District wide |  |  |  |  |  |  | 11,000.00 |  |  |  | Ongoing | JDA |  |  |  |  | Security Agencies |
| Management and administration | General administration | Sensitize the public on violent extremism, security consciousness through radio and community visits |  |  | Juaboso |  |  |  |  |  |  | 15,000.00 |  |  | New |  | NCCE, GPS |  |  |  |  | Central Admi |
| Emergency Planning And Response (Include COVID-19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Emergency Planning and response | Health delivery | Carry out active surveillance of diseases of public health importance |  |  | District-wide |  |  |  |  |  |  | 10,000 | 2,000 |  | New |  | DHD |  |  |  |  | NADMO, JDA |
| Focus area: IMPLEMENTATION, CO-ORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination |  |  | Prepare 2024 Annual Action Plan | Juaboso |  |  |  |  |  |  | 10,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination |  |  | Prepare 2024 composite budget and procurement plan | Juaboso |  |  |  |  |  |  | 35,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination |  |  | Organize 2 Town Hall meetings | Juaboso |  |  |  |  |  |  | 40,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination |  |  | Ensure Monitoring of all development projects/programmes | Juaboso |  |  |  |  |  |  | 40,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination |  |  | Prepare and dissemination M&E reports | Juaboso |  |  |  |  |  |  | 13,000.00 |  |  | New |  | DPCU |  |  |  |  |  |