JUABOSO DISTRICT ASSEMBLY

2024 ANNUAL ACTION PLAN

SUMMARY OF ACTIVIITES FOR 2024

| DEVELOPMENT DIMENSION | NUMBER OF ACTIVITIES |
| --- | --- |
| ECONOMIC DEVELOPMENT | 20 |
| SOCIAL DEVELOPMENT | 40 |
| ENVIRONMENT,INFRASTRUCTURE AND HUMAN SETTLEMENT | 27 |
| DISASTER PREARAREDNESS | 2 |
| GOOD GOVERNANCE AND PUBLIC ACCOUNTABILITY | 12 |
| MONITORING AND EVALUATION | 5 |
| TOTAL | 106 |

ANNUAL ACTION PLAN FOR 2024

| Table 8.10.5: Programme (PBB) | Sub-Programme (PBB) |  | Broad Activities |  | Location | Timeframe (2024 |  |  |  |  |  |  | Cost |  |  | Programme Status |  |  | Implementing Institution/Department |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |  | GoG | IGF/ABFA | Others | New | Ongoing |  | Lead | Collaborating |  |  |  |
| DEVELOPMENT DIMENSION: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Strong and Resilient Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management administration | Finance and Revenue Mobilization |  | Revise and update data on revenue sources |  | Juaboso |  |  |  |  |  |  |  | 12,000.00 |  |  | New | - |  | Finance Dept | MLGDRD |  |  |  |
| Management administration | Finance and Revenue Mobilization |  | Organize fresher training for revenue collectors |  | Juaboso |  |  |  |  |  |  |  | 15,000.00 |  | - | New | - |  | DBA, DFO | Central admin |  |  |  |
| Focus area: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize social media marketing training for women and men |  | District wide |  |  |  |  |  |  |  |  | 7,000.00 |  |  | On-going |  | BAC | JDA, GEA, MOTI |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize 2 stakeholders forum on business counselling |  | Juaboso |  |  |  |  |  |  |  | 4,500.00 |  |  |  | On-going |  | BAC | JDA, GEA, MOTI |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Construction of 2No 12 unit Market sheds |  | Boinzan |  |  |  |  |  |  |  | 350,000.00 |  |  | New |  |  | BAC | JDA |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize 1Training session on Credit Management |  | Juaboso |  |  |  |  |  |  |  | 4,200.00 |  |  |  | On-going |  | BAC | Trobenbos Ghana |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Formalize Business registration and certification |  | Districtwide |  |  |  |  |  |  |  | 5,000.00 |  |  |  | On-going |  | BAC | GEA/ Clients |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize 2 training workshop on technology improvement in cosmetics and bead making |  | Selected Communities |  |  |  |  |  |  |  | 11,000.00 |  |  |  | On-going |  | BAC | GEA/DA |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize coaching and internship training for 5 BAC Clients |  | Juaboso |  |  |  |  |  |  |  | 2,500.00 |  |  | New |  |  | BAC | JDA, GEA, MOTI |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organise training on beekeeping and honey processing |  | Juaboso |  |  |  |  |  |  |  | 3,000.00 |  |  | New |  |  | BAC | JDA |  |  |  |
| Focus area: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agricultural Development | Training of staff and farmers on climate and conservation agriculture technologies |  |  | Districtwide |  |  |  |  |  |  |  |  |  | 17,000.00 |  | On-going |  | Agric. dept | RADU, GHS, Researchers, MAG |  |  |  |
| Economic Development | Agricultural Development | Organization of community and district RELC planning session |  |  | Juaboso |  |  |  |  |  |  |  |  |  | 6250.00 |  | On-going |  | Agric. dept | RADU, Research, NGOs, DA, Farmers |  |  |  |
| Economic Development | Agricultural Development | Establish 5 Demonstration plots for 5 major crops |  |  | 5 Communities |  |  |  |  |  |  |  | 2,000.00 |  | 4,000.00 |  | On-going |  | Agric. dept | SRID, RADU Farmers |  |  |  |
| Economic Development | Agricultural Development | Maintenance of official vehicle and motorbikes |  |  | Juaboso |  |  |  |  |  |  |  | 6,000.00 |  | 7,000.00 |  | On-going |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Maintenance of office complex and DDA residence |  |  | Juaboso |  |  |  |  |  |  |  |  | 6,000.00 |  | New |  |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Acquisition of equipment for SRID activities |  |  | Juaboso |  |  |  |  |  |  |  | 4,000.00 |  |  | New |  |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Organization of District Farmers Day |  |  | District wide |  |  |  |  |  |  |  |  |  | 80,000.00 |  | On-going |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Acquisition and distribution of 24 Coconut seedlings for PERD programme |  |  | District wide |  |  |  |  |  |  |  | 65,000.00 |  |  |  | On-going |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Maintenance 55 Acre Oil Palm Plantation |  |  | District wide |  |  |  |  |  |  |  | 105,000,00 |  |  | New |  |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Carry out impact analysis studies of agroforestry interventions on gender |  |  | Selected Communities |  |  |  |  |  |  |  | 10, 000 |  | 5,000 | New |  |  | GDO | Agric dept |  |  |  |
| Development Dimension: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Education and Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organize Science, Technology, Mathematics, and Innovative Education (STMIE) clinics |  | Juaboso |  |  |  |  |  |  |  |  | 4,000.00 | 3,000.00 |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Support the District Education Oversight Committee to monitor teaching and learning in schools |  | Juaboso |  |  |  |  |  |  |  |  | 4,500.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organization of Independence day celebration |  | Juaboso |  |  |  |  |  |  |  |  | 40,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organize reading festivals to create awareness and encourage children to read |  | Juaboso |  |  |  |  |  |  |  |  |  | 5,000.00 |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organize mock examination for JHS three students |  | District wide |  |  |  |  |  |  |  |  | 18,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1No. KG Block |  | Juaboso |  |  |  |  |  |  |  |  | 150,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1 No. KG Block |  | Bonsu Nkwanta |  |  |  |  |  |  |  |  | 400,227 |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1No 6 unit classroom Block with Ancillary facility |  | Yawagyiemkrom |  |  |  |  |  |  |  |  | 83,703.00 |  |  | On going |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1No 3unit classroom block |  | Mantukwa |  |  |  |  |  |  |  |  | 8,000.00 |  |  | On going |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Renovation of 1No. 6unit classroom Block with office and store |  | Sayerano |  |  |  |  |  |  |  |  | 115,757.07 |  |  | On going |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1No 6unit block with ancillary facilities |  | Bechimaa |  |  |  |  |  |  |  |  | 35,186.26 |  |  | On going |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Procure and Supply 500 mono desks for JHS |  | District-wide |  |  |  |  |  |  |  |  | 300,000.00 |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Provide financial support to promote ICT education |  | Juaboso |  |  |  |  |  |  |  |  | 15,000.00 |  |  | New |  |  | JDA | GIFEC |  |  |  |
| Focus area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Development | Support the organization of inter district sports festival |  | Juaboso |  |  |  |  |  |  |  |  | 15,000.00 |  |  | New |  |  | GES | JDA |  |  |  |
| Focus area: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Construction of 1N0. CHPS Compounds |  |  | Kafass |  |  |  |  |  |  |  | 550,000.00 |  |  | New |  |  | District Health | JDA |  |  |  |
| Social Services Delivery | Health Delivery | Intensify public education on causes, prevention and control of Malaria |  |  | District wide |  |  |  |  |  |  |  | 3,500.00 |  |  | New |  |  | District Health Dir | JDA |  |  |  |
| Social Services Delivery | Health Delivery | Carry out school talk on healthy nutrition |  |  | Selected schools |  |  |  |  |  |  |  | 6,000 |  |  | New |  |  | GDO | SWCD, Health Service |  |  |  |
| Social Services Delivery | Health Delivery | Renovation of 1No 4unit Nurses Quarters |  |  | Bonsu Nkwanta |  |  |  |  |  |  |  | 50,000.00 |  |  | On going |  |  | DHD | JDA |  |  |  |
| Focus area: HIV/AIDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | HIV/AIDS | Organize know your status campaigns in selected communities |  |  | District-wide |  |  |  |  |  |  | 6,000 |  |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | HIV/AIDS | Ensure celebration of World HIV/AIDS day and Know your status Campaigns |  |  | District-wide |  |  |  |  |  |  | 7,500 |  |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | HIV/AIDS | Organize radio sensitization on the effect of stigmatization against PLWHA |  |  | District-wide |  |  |  |  |  |  | 5,500 |  |  |  |  | Ongoing |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | Health Delivery | Provide support for organization of health education on communicable and non-communicable diseases on local FM station |  |  | District-wide |  |  |  |  |  |  | 3,000.00 |  |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Focus area: Environmental and Sanitation Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Organized medical screening exercise for Food and Drinks Vendors |  |  | District wide |  |  |  |  |  |  |  | 6,000.00 |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Facilitate the organization of monthly national sanitation day |  |  | District wide |  |  |  |  |  |  |  | 60,000 |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Quarterly pushing/leveling of final dumping site |  |  | District wide |  |  |  |  |  |  |  | 80,000.00 |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Undertake premises inspection |  |  | District wide |  |  |  |  |  |  |  | 3,000.00 |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Focus area: Population Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Population management | Sensitize people on reproductive health to increase family planning acceptor rate |  |  | District-wide |  |  |  |  |  |  |  |  | 5,000.00 |  | New |  |  | GHS | Birth & Death department |  |  |  |
| Social Services Delivery | Population management | Organize radio and community information center discussions on birth and death registration |  |  | District-wide |  |  |  |  |  |  |  |  | 6,000.00 |  |  | On-going |  | Birth & Death department | GHS, communities, traditional and religious leaders |  |  |  |
| Social Services Delivery | Population management | Registration of births and deaths in the district |  |  | District-wide |  |  |  |  |  |  |  |  | 4,500.00 |  | New |  |  | Birth & Death department | GHS, |  |  |  |
| Focus area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Child development and protection | Create 4 awareness campaigns for parents to desist from child neglect, discrimination, exposure to physical and moral threats |  |  | District-wide |  |  |  |  |  |  |  |  | 1,400.00 |  |  | Ongoing |  | SWCD Central Admin | CRI, Mondelz ILO |  |  |  |
| Social Services Delivery | Child development and protection | Promote public-private partnerships in the provision of alternative care services |  |  | 20 Communities |  |  |  |  |  |  |  | 2,200.00 |  |  |  | Ongoing |  | SWCD Central Admin | CRI, Mondelez ILO |  |  |  |
| Social Services Delivery | Child development and protection | Formation of four (4) new women groups and monitoring twelve (12) of the existing groups and to link them to Additional Livelihoods Training |  |  | District-wide |  |  |  |  |  |  |  | 1,550.00 |  |  |  | Ongoing |  | SWCD Central Admn | Planning Unit / Gender Desk Officer |  |  |  |
| Disability and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | Organize 4 Community durbars to assist and help community in the preparation of their Community Action Plan quarterly |  |  | Four (4) communities |  |  |  |  |  |  |  | 1,500.00 |  |  |  | Ongoing |  | SWCD Central Admin | World Viaion |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | Create awareness campaign on voluntary participation in community initiated projects |  |  | 20 Communities |  |  |  |  |  |  |  | 1,642.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Gender Empowerment | Organize radio talk show programmes to advocate for girl child education |  |  | 5 communities |  |  |  |  |  |  |  | 1,500.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Disability and Development | Facilitate the registration and renewal of 400 vulnerable groups such as PWDs, LEAP beneficiaries etc. onto NHIS |  |  | District wide |  |  |  |  |  |  |  | 1,500.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social service Delivery | Disability and Development | To support and to train 60% of registered PWDs in the District to engage in economic and business ventures |  |  | District wide |  |  |  |  |  |  |  | 1,000.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Poverty and Inequality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Gender Empowerment | To Establish four (4) Village Savings and Loans Associations (VSLA) |  |  | District wide |  |  |  |  |  |  |  | 1,000.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Gender Empowerment | Enhance youth capabilities in building sustainable livelihoods |  |  | District wide |  |  |  |  |  |  |  | 6,000.00 |  |  |  | New |  | GDO | SWCD NGO’s BAC |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | To organize training workshops for the NGOs working within the District to understand the need to be registered with the department |  |  | Juaboso |  |  |  |  |  |  |  | 2,000.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Development Dimension: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Protected Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Promote planting of other trees in cocoa farms |  |  | District wide |  |  |  |  |  |  |  | 30,000.00 |  |  | New |  | Forestry Commission |  |  |  |  | DA |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out tree planting exercise in schools and other institutions |  |  | District wide |  |  |  |  |  |  |  | 13,000.00 |  |  | New |  | Forestry Commission |  |  |  |  | DA |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out afforestation of depleted forest reserve |  |  | District wide |  |  |  |  |  |  |  | 50,000.00 |  |  | New |  | Forestry Commission |  |  |  |  | DA |
| Focus Area: Water Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Water resources management | Construct 5No. new boreholes |  |  | District wide |  |  |  |  |  |  |  | 260,000.00 |  |  | New |  | DWE |  |  |  |  | CWSA, DP |
| Environment, Infrastructure and Human Settlements | Water resources management | Maintain broken down boreholes |  |  | District wide |  |  |  |  |  |  |  | 150,000.00 |  |  | New |  | DWE |  |  |  |  | CWSA, DP |
| Key Focus Area: Climate variability and change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Organized awareness creation workshop on climate change for Assembly Members, staff and other stakeholders |  |  | District wide |  |  |  |  |  |  |  | 13,000.00 |  |  | New |  | JDA |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Supply 24,000 Oil Palm seedlings to farmers. |  |  | District wide |  |  |  |  |  |  |  | 18,000.00 | 20,000.00 |  | New |  | MoFA |  |  |  |  | JDA |
| Environmental and Sanitation Management | Natural Resource Conservation | Train male and female farmers on climate-smart agribusiness |  |  | District wide |  |  |  |  |  |  |  | 10,000.00 |  |  | New |  | MoFA |  |  |  |  | JDA |
| Environmental and Sanitation Management | Natural Resource Conservation | Procure and Supply 5,000 other tree spices seedlings to Community around the Forest and plant them in the Forest |  |  | District Wide |  |  |  |  |  |  |  |  |  |  | New |  | JDA |  |  |  |  | Forestry |
| Environmental and Sanitation Management | Natural Resource Conservation | Organised sensitization on effect of climate change in community and schools |  |  | District Wide |  |  |  |  |  |  |  |  |  |  | New |  | JDA |  |  |  |  | Forestry |
| Focus area: Transport Infrastructure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance and reshaping of 65 km feeder roads |  |  | District Wide |  |  |  |  |  |  |  | 345,000.00 |  |  | - | On-going | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Construction of 2No. culverts |  |  | Etese Mafia |  |  |  |  |  |  |  | 290,000.00 |  |  | - | On-going | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Construction of 1No. Double culverts |  |  | Yawagyiemkrom |  |  |  |  |  |  |  | 87,358.00 |  |  | - | On-going | DWE |  |  |  |  | Works |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance of Assembly vehicle |  |  | Juaboso |  |  |  |  |  |  |  | 36,000.00 |  |  | - | On-going | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Maintenance of Assembly grader |  |  | Juaboso |  |  |  |  |  |  |  | 80,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Organised Road safety campaign at various lorry station |  |  | District Wide |  |  |  |  |  |  |  | 6, 000.00 |  | - | New | - | JDA |  |  |  |  |  |
| Focus area: Infrastructure and Infrastructure Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Maintenance of office laptops, printers and photo copiers |  |  | Juaboso |  |  |  |  |  |  |  | 25,000 | 10,000 | - | - | On-going | ICT officer |  |  |  |  | Central admi store keeper |
| Management and administration | General administration | Maintenance of official buildings and accommodation |  |  | Juaboso |  |  |  |  |  |  |  | 45,000 | 20,000 | - | New | - | JDA |  |  |  |  | MLGDRD |
| Focus area: Energy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Procure/ Maintain 500 Street light bulbs |  |  | District-wide |  |  |  |  |  |  |  | 120,000 | 10,000 |  | New |  | JDA, ECG |  |  |  |  | Energy Ministry |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Extend electricity to the communities without lights |  |  | Selected communities |  |  |  |  |  |  |  | 30,500 |  | 450,000 | New |  | JDA, ECG |  |  |  |  | Energy Ministry |
| Focus area: Human Settlements and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Organize radio sensitization on building permit |  |  | Juaboso |  |  |  |  |  |  |  | 5,000.00 |  |  |  | On-going | Works/Planning |  |  |  |  | LUSPA |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Expansion of street naming and property addressing system |  |  | Bonsu Nkwanta Bonzain |  |  |  |  |  |  |  | 40,000.00 |  |  |  | On-going | Works/Planning |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Enforce planning and building regulations |  |  | District-wide |  |  |  |  |  |  |  | 6,000.00 |  |  |  | On-going | Works/Planning |  |  |  |  | Central Admi |
| Focus area: Disaster Prevention and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Hold disaster management committee meeting |  |  | District-wide |  |  |  |  |  |  |  | 3,500 |  |  | New |  | NADMO |  |  |  |  | Central Admi |
| Environmental and Sanitation Management | Disaster Prevention and Management | Reformation of DVG’s |  |  | District-wide |  |  |  |  |  |  |  | 5,000 |  | 5,000 | New |  | NADMO |  |  |  |  | Central Admi |
| Environmental and Sanitation Management | Disaster Prevention and Management | Organize anti-bush fire campaign on radio and communities |  |  | District-wide |  |  |  |  |  |  |  | 8,000 |  |  | New |  | NADMO, GNFS |  |  |  |  | Central Admi |
| Environmental and Sanitation Management | Disaster Prevention and Management | Form and train disaster clubs |  |  | Schools in the district |  |  |  |  |  |  |  |  | 10,500.00 |  | New |  | NADMO, GNFS |  |  |  |  | Central Admi |
| Development Dimension: Governance, Corruption and Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Local Government and Decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Organize sub-committee, general assembly meeting, and management meetings |  |  | Juaboso |  |  |  |  |  |  |  | 60,000.00 |  |  | New |  | Central Admi |  |  | MLGDRD NALAG |  |  |
| Management and administration | General administration | Prepare and gazette Assembly by-laws and fee fixing resolution |  |  | Juaboso |  |  |  |  |  |  |  | 35,000.00 |  |  | New |  | Central Admi |  |  | MLGDRD NALAG |  |  |
| Management and administration | General administration | Procure and supply office logistics and equipment |  |  | Juaboso |  |  |  |  |  |  |  | 30,000.00 |  |  | New |  | Procurement officer |  |  | Central Admi, stores |  |  |
| Management and administration | Security and safety | Construction of 1No. security Post |  |  | Benchima Nkwanta highway |  |  |  |  |  |  |  | 20,000.00 |  |  |  | Ongoing | Works Dept |  |  | District Police Command |  |  |
| Management and administration | General administration | Prepare and submit monthly and quarterly progress reports |  |  | Juaboso |  |  |  |  |  |  |  | 10,000.00 |  |  |  | Ongoing | DPCU |  |  |  |  |  |
| Management and administration | General administration | Organised quarterly Audit Committee meetings |  |  | Juaboso |  |  |  |  |  |  |  | 12,000.00 |  |  |  | Ongoing | Audit committee |  |  |  |  |  |
| Management and administration | General administration | Provide financial support for anti-corruption activities |  |  | Juaboso |  |  |  |  |  |  |  | 10,000.00 |  |  | New |  | NACAP Desk Officer |  |  | Central Admin, CHRAG, NCCE |  |  |
| Management and administration | General administration | Organise Annual Constitution/citizens week |  |  | 3 Educational Circuits |  |  |  |  |  |  |  | 3,000.00 |  |  | New |  | NCCE |  |  | Central Admin, |  |  |
| Management and administration | General administration | Organise sensitization on 2024 electoral process |  |  | Juaboso |  |  |  |  |  |  |  | 10,000.00 |  |  | New |  | NCCE |  |  | Central Admin, |  |  |
| Management and administration | General administration | Organise sensitization on laws against tax invasion and non compliance |  |  | Juaboso |  |  |  |  |  |  |  | 12,000.00 |  |  | New |  | NCCE |  |  | Central Admin, |  |  |
| Management and administration | General administration | Organise Financial management and revenue training mobilization for Area councils |  |  | Juaboso |  |  |  |  |  |  |  | 11,000.00 |  |  | New |  | Finance Dept |  |  |  |  |  |
| Focus area: Security and public safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Provide financial support for conflict and DISEC activities |  |  | District wide |  |  |  |  |  |  |  | 11,000.00 |  |  |  | Ongoing | JDA |  |  |  | Security Agencies |  |
| Emergency Planning And Response (Include COVID-19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Emergency Planning and response | Health delivery | Carry out active surveillance of diseases of public health importance |  |  | District-wide |  |  |  |  |  |  |  | 10,000 | 2,000 |  | New |  | DHD |  |  |  | NADMO, JDA |  |
| Emergency Planning and response | Health delivery | Conduct outbreak investigation |  |  | District-wide |  |  |  |  |  |  |  | 7,000 | 3,000 |  | New |  | DHD |  |  |  | NADMO |  |
| Focus area: IMPLEMENTATION, CO-ORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Prepare 2025 Annual Action Plan |  |  | Juaboso |  |  |  |  |  |  |  | 10,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Prepare 2025 composite budget and procurement plan |  |  | Juaboso |  |  |  |  |  |  |  | 35,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Organize 4 Town Hall meetings |  |  | Juaboso |  |  |  |  |  |  |  | 40,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Ensure Monitoring of all development projects/programmes |  |  | Juaboso |  |  |  |  |  |  |  | 40,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Prepare and dissemination M&E reports |  |  | Juaboso |  |  |  |  |  |  |  | 13,000.00 |  |  | New |  | DPCU |  |  |  |  |  |