JUABOSO DISTRICT ASSEMBLY

ANNUAL ACTION PLAN FOR 2025

| DEVELOPMENT DIMENSION | NUMBER OF ACTIVITIES |
| --- | --- |
| ECONOMIC DEVELOPMENT | 17 |
| SOCIAL DEVELOPMENT | 49 |
| ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENT | 22 |
| EMERGENCY PLANNING AND RESPONSE (INCLUDE COVID-19) | 7 |
| GOOD GOVERNANCE AND PUBLIC ACCOUNTABILITY | 12 |
| IMLEMENTATION, COORDINATION, MONITORING AND EVALUATION | 6 |
| TOTAL | 113 |

Composite Annual Action Plan 2025

| Programme (PBB) | SubProgramme (PBB) | Broad Activities | Location | Timeframe (2023) |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Departm ent |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Q 1 | Q 2 | Q3 | Q4 | GoG | IGF/AB FA | Others | New | Ongoing | Lead | Collabora ting |
| DEVELOPMENT DIMENSION: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Strong and Resilient Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management administration | Finance and Revenue Mobilization | Revise and update data on revenue sources | Juaboso |  |  |  |  | 12,500.00 |  |  | New | - | Finanac e Dept | MLGDRD |
| Management administration | Finance and Revenue Mobilization | Organize fresher training for revenue collectors | Juaboso |  |  |  |  | 20,000.00 |  | - | New | - | DBA, DFO | Central admi |
| Focus area: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, tourism and industrial development | Organize social media marketing training for women and men | District wide |  |  |  |  | 8,500.00 |  |  |  | On-going | BAC | JDA, GEA, MOTI |
| Economic Development | Trade, tourism and industrial development | Organize business forum and business counselling | Juaboso |  |  |  |  | 5,000.00 |  |  |  | On-going | BAC | JDA, GEA, MOTI |
| Economic Development | Trade, tourism and industrial development | Construction of 2No 12 Market sheds | Sayerano |  |  |  |  | 150,000.00 |  |  | New |  | BAC | JDA |

| Economic Development | Trade, tourism and industrial development |  | Organize 1Training session on Credit Management | Juaboso |  |  |  |  | 4,500.00 |  |  |  | On-going | BAC | Trobenbos Ghana |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Economic Development | Trade, tourism and industrial development |  | Formalization of Business registration and certification | Districtwid e |  |  |  |  | 5,000.00 |  |  |  | On-going | BAC | GEA/ Clients |
| Economic Development | Trade, tourism and industrial development |  | Organize 2 training workshop on technology improvement in bee keeping | Selected Communiti es |  |  |  |  | 12,000.00 |  |  |  | On-going | BAC | GEA/DA |
| Focus area: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agricultural Development | Training of staff and farmers on IMO technology |  | 20 Communiti es |  |  |  |  |  |  | 19,000. 00 |  | On-going | Agric. dept | RADU, Farmers, Staff |
| Economic Development | Agricultural Development | Organization of community and district planning session |  | Juaboso |  |  |  |  |  |  | 4,350.0 0 |  | On-going | Agric. dept | RADU, Research, NGOs, DA, Farmers |
| Economic Development | Agricultural Development | Train Farmers on Vegetable production |  | 10 Communiti es |  |  |  |  | 2,000.00 |  | 3,000.0 0 |  | On-going | Agric. dept | RADU Farmers, AEAs |
| Economic Development | Agricultural Development | Maintenance of official vehicle and motorbikes |  | Juaboso |  |  |  |  | 7,000.00 |  |  |  | On-going | Agric. dept | D.A |

| Economic Development | Agricultural Development | Maintenance of office complex and DDA residence |  | Juaboso |  |  |  |  |  | 2,000.00 |  | New |  | Agric. dept | D.A |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Economic Development | Agricultural Development | Training farmers on post-harvest management |  | Juaboso |  |  |  |  | 4,000.00 |  |  | New |  | Agric. dept | D.A |
| Economic Development | Agricultural Development | Organization of District Farmers Day |  | District wide |  |  |  |  |  |  | 200,00 0.00 |  | On-going | Agric. dept | D.A |
| Economic Development | Agricultural Development | Acquisition of 1,200 Palm oil for PERD program |  | District wide |  |  |  |  | 15,000.00 |  |  |  | On-going | Agric. dept | D.A |
| Economic Development | Agricultural Development | Organise workshop and staff train climate smart agricultural |  | District wide |  |  |  |  | 10,000,00 |  |  | New |  | Agric. dept | D.A |
| Development Dimension: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Education and Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organize Science, Technology, Mathematics, and Innovative Education (STMIE) clinics | Juaboso |  |  |  |  |  | 5,000.00 | 4,000.00 |  |  | On-going | GES | JDA |
| Social Services Delivery | Education and Youth Dev’t. | Support the District Education Oversight Committee to monitor teaching and learning in schools | Juaboso |  |  |  |  |  | 4,500.00 |  |  |  | On-going | GES | JDA |

| Social Services Delivery | Education and Youth Dev’t. | Organization of Independence day celebration | Juaboso |  |  |  |  | 45,000.00 |  |  |  | On-going | GES | JDA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Social Services Delivery | Education and Youth Dev’t. | Organize reading festivals to create awareness and encourage children to read | Juaboso |  |  |  |  |  | 6,000.00 |  |  | On-going | GES | JDA |
| Social Services Delivery | Education and Youth Dev’t. | Organise my first day at school ceremony schools | Selected schools |  |  |  |  | 15,000.00 |  |  |  | On-going | GES | JDA |
| Social Services Delivery | Education and Youth Dev’t. | Organize mock examination for JHS three students | District wide |  |  |  |  | 20,000.00 |  |  |  | On-going | GES | JDA |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1 No. K.G block & Ancillary facility | Bonsu Nkwanta |  |  |  |  | 500,227 |  |  | New |  | GES | JDA |
| Social Services Delivery | Education and Youth Dev’t. | Supply of 600 dual desks for Pry. School and 500 mono desks for JHS | District-wide |  |  |  |  | 400,000.00 |  |  | New |  | GES | JDA |
| Social Services Delivery | Education and Youth Dev’t. | Provide financial support to promote ICT education | Juaboso |  |  |  |  | 18,000.00 |  |  | New |  | JDA | GIFEC |

| Social Services Delivery | Education and Youth Dev’t. | Undertake stakeholder and consultative meeting on scaling up effective mechanisms to promote and build sustainable TVET among women | District wide |  |  |  |  | 6,000.00 |  |  | New |  | GDO | JDA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1 No. K.G block & Ancillary facility | Juaboso |  |  |  |  | 500,227 |  |  | New |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Renovation . of 1 No. 6 K.G block | Sayerano |  |  |  |  | 350,227 |  |  |  | On going | GES | JDA |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1No 6 unit classroom Block with Ancillary facility | Yawagyiem krom |  |  |  |  | 83,703.00 |  |  |  | On going | GES | JDA |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1No 3unit classroom block | Mantukwa |  |  |  |  | 3,447.10 |  |  |  | On going | GES | JDA |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1No 3unit classroom block | Komeamaa |  |  |  |  | 2,000.00 |  |  |  | On going | GES | JDA |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1no. 6unit C. Block and | Benchima |  |  |  |  | 30,186.26 |  |  |  | On going | GES | JDA |

|  |  | Ancillary facilities |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Social Services Delivery | Education and Youth Dev’t. | Const. of 1 no. 6 unit Classroom Block with Ancillary facilities | Mafia |  |  |  |  | 12,524.87 |  |  |  | On going | GES | JDA |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1no. Double 1200mm | Kotosah |  |  |  |  | 6,021.76 |  |  |  | On going | GES | JDA |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1 no. 6 unit Classroom Block with Ancillary facilities | Dominibo |  |  |  |  | 30,000.00 |  |  |  | On going | GES | JDA |
| Focus area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Development | Support the organization of inter district sports festival | Juaboso |  |  |  |  | 20,000.00 |  |  | New |  | GES | JDA |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1No 6unit block with ancillary facilities | Bechimaa |  |  |  |  | 35,186.26 |  |  | On going |  | GES | JDA |
| Social Services Delivery | Education and Youth Development | Construction of football pitch | Juaboso Kotosah Antobia |  |  |  |  | 450,000.00 |  |  | New |  | GES | JDA |
| Focus area: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Social Services Delivery | Health Delivery | Construction of 2N0. CHPS Compounds | Kefas Nkra |  |  |  |  | 600,000.00 |  |  | New |  | District Health | DA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Social Services Delivery | Health Delivery | Intensify public education on causes, prevention and control of Malaria | District wide |  |  |  |  | 4,500.00 |  |  | New |  | District Health Dir | DA |
| Focus area: HIV/AIDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | HIV/AIDS | Organize know your status campaigns in selected communities | Districtwide |  |  |  |  | 7,000 |  |  | New |  | District Health Dir | DA |
| Social Services Delivery | HIV/AIDS | Ensure celebration of World HIV/AIDS day and Know your status Campaigns | Districtwide |  |  |  |  | 7,500 |  |  | New |  | District Health Dir | DA |
| Social Services Delivery | HIV/AIDS | Organize radio sensitization on the effect of stigmatization against PLWHA | Districtwide |  |  |  |  | 6,500 |  |  |  | Ongoing | District Health Dir | DA |
| Social Services Delivery | Health Delivery | Provide support for organization of health education on communicable and non-communicable diseases on local FM station | Districtwide |  |  |  |  | 3,500.00 |  |  | New |  | District Health Dir | DA |
| Focus area: Environmental and Sanitation Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Organized medical screening exercise and Promote Public Health Hygiene | District wide |  |  |  |  | 8,000.00 |  |  |  | Ongoing | DEHU | DA |

|  |  | Education in Basic School |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Social Services Delivery | Health Delivery | Facilitate the organization of monthly national sanitation day and Daily Public Cleaning | Asempane ye,Juaboso ,Proso,Bon su Nkwanta |  |  |  |  | 8,000.00 |  |  |  | Ongoing | DEHU | DA |
| Social Services Delivery | Health Delivery | Facilitate the organization of monthly national sanitation day and Daily Public Cleaning | District wide |  |  |  |  | 60,500.00 |  |  |  | Ongoing | DEHU | DA |
| Social Services Delivery | Health Delivery | Quarterly pushing/leveling of final dumping site | District wide |  |  |  |  | 80,000.00 |  |  |  | Ongoing | DEHU | DA |
| Social Services Delivery | Health Delivery | Undertake premises inspection | District wide |  |  |  |  | 3,500.00 |  |  |  | Ongoing | DEHU | DA |
| Social Services Delivery | Health Delivery | Construction of 3 No. public toilet at market centers and Promote Household Latrine construction. | Selected communiti es |  |  |  |  | 360,000.00 |  |  | New |  | DEHU | DA |
| Social Services Delivery | Health Delivery | Construct 1NO. Modern Slaughterhouse | Juaboso |  |  |  |  | 100,000 |  |  | New |  | DEHU | DA |
| Social Services Delivery | Health Delivery | Educate the Public on Noise and Air Pollution and Purchase 1No | Selected Communiti es |  |  |  |  | 10,000 |  |  | New |  | DEHU | DA |

|  |  | Ambient Device for Noise Control |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Social Services Delivery | Health Delivery | Control of Stray Animals | District Wide |  |  |  |  | 5,000 |  |  | New |  | DEHU | DA |
| Focus area: Population Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Population management | Sensitize people on reproductive health to increase family planning acceptor rate | Districtwide |  |  |  |  |  | 5,000.00 |  | New |  | GHS | Birth & Death department |
| Social Services Delivery | Population management | Organize radio and community information center discussions on birth and death registration | Districtwide |  |  |  |  |  | 6,500.00 |  |  | On-going | Birth & Death depart ment | GHS, communiti es, traditional and religious leaders |
| Social Services Delivery | Population management | Registration of births and deaths in the district | Districtwide |  |  |  |  |  | 4,500.00 |  | New |  | Birth & Death depart ment | GHS, |
| Focus area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Child development and protection | Create 4 awareness campaigns for parents to desist from child neglect, discrimination, exposure to physical and moral threats | Districtwide |  |  |  |  |  | 1,600.00 |  |  | Ongoing | SWCD Central Admin | CRI, Mondelez ILO |

| Social Services Delivery | Child development and protection | Promote public- private partnerships in the provision of alternative care services | 20 Communiti es |  |  |  |  | 2,600.00 |  |  |  | Ongoing | SWCD Central Admin | CRI, Mondelez ILO |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Social Services Delivery | Child development and protection | Formation of four (4) new women groups and monitoring twelve (12) of the existing groups and to link them to Additional Livelihoods Training | Districtwide |  |  |  |  | 1,550.00 |  |  |  | Ongoing | SWCD Central Admin | Planning Unit / Gender Desk Officer |
| Disability and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | Create 4 awareness campaign on voluntary participation in community initiated projects | 20 Communiti es |  |  |  |  | 1,642.00 |  |  |  | Ongoing | SWCD Central Admin | NGOs |
| Social Services Delivery | Gender Empowerme nt | Organize radio talk show programs to advocate for girl child education | 5 communiti es |  |  |  |  | 2, 000.00 |  |  |  | Ongoing | SWCD Central Admin | NGOs |
| Social Services Delivery | Disability and Development | Facilitate the registration and renewal of 400 vulnerable groups such as PWDs, LEAP beneficiaries etc. onto NHIS | District wide |  |  |  |  | 2, 000.00 |  |  |  | Ongoing | SWCD Central Admin | NGOs |

| Social service Delivery | Disability and Development | To support and to train 60% of registered PWDs in the District to engage in economic and business ventures | District wide |  |  |  |  | 1,500.00 |  |  |  | Ongoing | SWCD Central Admin | NGOs |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Poverty and Inequality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Gender Empowerme nt | To Establish four (4) Village Savings and Loans Associations (VSLA) | District wide |  |  |  |  | 1,500.00 |  |  |  | Ongoing | SWCD Central Admin | NGOs |
| Social Services Delivery | Gender Empowerme nt | To facilitate community dialogue and school outreaches on redefining gender roles to harness women participation in politics, science and technology | District wide |  |  |  |  | 1,500.00 |  |  | New |  | GDO | SWCD NGO’s GES |
| Social Services Delivery | Social Welfare and Community Development | To organize training workshops for the NGOs working within the district to understand the need to be registered with the department | Juaboso |  |  |  |  | 2,000.00 |  |  |  | Ongoing | SWCD Central Admin | NGOs |
| Development Dimension: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Protected Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Key Focus Area: Climate variability and change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental and Sanitation Management | Natural Resource Conservation | Organized awareness creation workshop on climate change for Assembly Members, staff and other stakeholders | District wide |  |  |  |  | 13,500.00 |  |  | New |  | JDA |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Train male and female farmers on climate-smart agribusiness | District wide |  |  |  |  | 10,000.00 |  |  | New |  | MoFA | JDA |
| Environmental and Sanitation Management | Natural Resource Conservation | Gazette and strictly enforcement of all HIA by-laws in Juaboso District by December 2024. | Juaboso |  |  |  |  | 50,000.00 |  |  | New |  | JDA |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out sensitization campaign on climate change awareness in line with the Ghana Cocoa Forest REED+ Programme (GCFRP) in 15 Communities | HTA Communiti es |  |  |  |  | 91,971.00 |  |  | New |  | JDA | MoFA |

| Environmental and Sanitation Management | Natural Resource Conservation | Formation and establishment of Climate Change Ambassadorial Clubs (CCAC) in 20 schools | Selected schools |  |  |  |  | 100,000.00 |  |  | New |  | JDA | GES |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out stakeholder training and sensitization on climate smart agricultural practices in 13 communities within the HIAs | HTA Communiti es |  |  |  |  | 82,500.00 |  |  | New |  | JDA | Agric |
| Environmental and Sanitation Management | Natural Resource Conservation | Undertake quarterly forest monitoring (Quarterly) | Krokosue forest |  |  |  |  | 28,000.00 |  |  | New |  | JDA | Agric |
| Environmental and Sanitation Management | Natural Resource Conservation | Participate in consortium meetings with other stakeholders in the HIAs (Quarterly) | Juaboso |  |  |  |  | 20,000.00 |  |  | New |  | JDA | Agric |
| Environmental and Sanitation Management | Natural Resource Conservation | Organize fresher training on the Ghana Cocoa Forest REED+ Programme (GCFRP) for staff and honorable assembly members | Juaboso |  |  |  |  | 22,500.00 |  |  | New |  | JDA | Forestry |
| Environmental and Sanitation Management | Natural Resource Conservation | Support to women in agroforestry within climate prone zones | HTA communiti es |  |  |  |  | 50,000.00 |  |  | New |  | JDA | Agric |
| Focus Area: Water Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Environment, Infrastructure and Human Settlements | Water resources management | Construct 20No. new boreholes | District wide |  |  |  |  | 260,000.00 |  |  | New |  | DWE | CWSA, DP |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environment, Infrastructure and Human Settlements | Water resources management | Maintain broken down boreholes | District wide |  |  |  |  | 170,000.00 |  |  | New |  | DWE | CWSA, DP |
| Focus area: Transport Infrastructure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance and reshaping of 145 km feeder roads | District Wide |  |  |  |  | 345,000.00 |  |  |  | ongoin g | DWE | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Construction of 2No. culverts | Selected communiti es |  |  |  |  | 290,000.00 |  |  | New |  | DWE | Central Admi |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1No. Double Culvert | Yawagyie mkrom |  |  |  |  | 70,000.00 |  |  |  | On going | GES | JDA |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance of Assembly vehicle | Juaboso |  |  |  |  | 36,000.00 |  |  |  | ongoin g | DWE | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Maintenance of Assembly grader | Juaboso |  |  |  |  | 80,000.00 |  |  |  | ongoin g | DWE | Central Admi |
| Focus area: Infrastructure and Infrastructure Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administratio n | Maintenance of office laptops, printers and photo copiers | Juaboso |  |  |  |  | 25,000 | 10,000 | - | - | On- going | ICT officer | Central admi store keeper |

| Management and administration | General administratio n | Maintenance of official buildings and accommodation | Juaboso |  |  |  |  | 50,000 | 20,000 | - | New | - | JDA | MLGDRD |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Focus area: Energy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Procure/ Maintain 500 Street light bulbs | Districtwide |  |  |  |  | 120,000 | 10,000 |  | New |  | JDA, ECG | Energy Ministry |
| Focus area: Human Settlements and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Organize radio sensitization on building permit | Juaboso |  |  |  |  | 5, 500.00 |  |  |  | On- going | Works/Pl anning | LUSPA |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Expansion of street naming and property addressing system | Proso Kofikrom |  |  |  |  | 40,000.00 |  |  |  | On- going | Works/Pl anning | Central Admi |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Enforce planning and building regulations | Districtwide |  |  |  |  | 6,000.00 |  |  |  | On- going | Works/Pl anning | Central Admi |
| Focus area: Emergency Planning And Response (Include COVID-19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Hold disaster management committee meeting | Districtwide |  |  |  |  | 3,500 |  |  | New |  | NADMO | Central Admi |
| Environmental and Sanitation Management | Disaster Prevention and Management | Reformation of DVG’s | Districtwide |  |  |  |  | 5,000 |  | 5,000 | New |  | NADMO | Central Admi |

| Environmental and Sanitation Management | Disaster Prevention and Management | Organize anti-bush fire campaign on radio and communities | Districtwide |  |  |  |  | 8,000 |  |  | New |  | NADMO, GNFS | Central Admi |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Environmental and Sanitation Management | Disaster Prevention and Management | Form and train disaster clubs | Schools in the district |  |  |  |  |  | 10,500.0 0 |  | New |  | NADMO, GNFS | Central Admi |
| Emergency Planning and response | Health delivery | Carry out active surveillance of diseases of public health importance | Districtwide |  |  |  |  | 11, 000 | 2,000 |  | New |  | DHD | NADMO, JDA |
| DEVELOPMENT DIMENSION: GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Local Government and Decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administratio n | Organize sub- committee, general assembly meeting, and management meetings | Juaboso |  |  |  |  | 60,000.00 |  |  | New |  | Central Admi | MLGDR D NALAG |
| Management and administration | General administratio n | Prepare and gazette Assembly by-laws and fee fixing resolution for 2026 | Juaboso |  |  |  |  | 35,000.00 |  |  | New |  | Central Admi | MLGDR D NALAG |
| Management and administration | General administratio n | Procure and supply office logistics and equipment | Juaboso |  |  |  |  | 30,000.00 |  |  | New |  | Procurem ent officer | Central Admi, stores |
| Management and administration | General administratio n | Procure 5N0. Laptop computers | Juaboso |  |  |  |  | 20,000.00 |  |  | New |  | Procurem ent officer | Central Admi, stores |

| Management and administration | General administratio n | Prepare and submit monthly and quarterly progress reports | Juaboso |  |  |  |  | 10,000.00 |  |  |  | Ongoin g | DPCU |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Management and administration | General administratio n | Organized quarterly Audit Committee meetings | Juaboso |  |  |  |  | 12,000.00 |  |  |  | Ongoin g | Audit committee |  |  |
| Management and administration | General administratio n | Provide financial support for anti- corruption activities | Juaboso |  |  |  |  | 10,000.00 |  |  | New |  | NACAP Desk Officer | Central Admi, CHRAG, NCCE |  |
| Management and administration | General administratio n | Financial management and revenue training mobilization for Area councils | Juaboso |  |  |  |  | 11,000.00 |  |  | New |  | Finance Dept |  |  |
| Focus area: Security and public safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administratio n | Provide financial support for conflict and DISEC activities | District wide |  |  |  |  | 11,000.00 |  |  |  | Ongoin g | JDA |  | Security Agencie s |
| Management and administration | General administratio n | Sensitize the public on violent extremism, security consciousness through radio and community visits | Juaboso |  |  |  |  | 15,000.00 |  |  | New |  | NCCE, GPS |  | Central Admi |
| Management and administration | General administratio n | Construction of 2No. Police check points | Selected Communiti es |  |  |  |  | 350,000.00 |  |  | New |  | GPS |  | Central Admi |
| Focus area: IMPLEMENTATION, CO-ORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administratio n | Planning, Budgeting and Coordination | Prepare 2026-2029 MTDP | Juaboso |  |  |  |  | 80,000.00 |  |  | New |  | DPCU |  |  |
| Management and Administratio n | Planning, Budgeting and Coordination | Prepare 2026 composite budget and procurement plan | Juaboso |  |  |  |  | 35,000.00 |  |  | New |  | DPCU |  |  |
| Management and Administratio n | Planning, Budgeting and Coordination | Organize 4 DPCU meetings | Juaboso |  |  |  |  | 24,000.00 |  |  | New |  | DPCU |  |  |
| Management and Administratio n | Planning, Budgeting and Coordination | Organize 4 Town Hall meetings for 35 males and 25 females | Juaboso |  |  |  |  | 45,000.00 |  |  | New |  | DPCU |  |  |
| Management and Administratio n | Planning, Budgeting and Coordination | Ensure Monitoring of all development projects/programmes | Juaboso |  |  |  |  | 40,000.00 |  |  | New |  | DPCU |  |  |
| Management and Administratio n | Planning, Budgeting and Coordination | Prepare and disseminate M&E reports | Juaboso |  |  |  |  | 15,000.00 |  |  | New |  | DPCU |  |  |