JUABESO DISTRICT ASSEMBLY

REVISED ANNUAL ACTION PLAN 2023

Prepared by DPCU

SEPTEMBER 2023

| DEVELOPMENT DIMENSION | NUMBER OF ACTIVITIES |
| --- | --- |
| ECONOMIC DEVELOPMENT | 10 |
| SOCIAL DEVELOPMENT | 39 |
| ENVIRONMENT,INFRASTRUCTURE AND HUMAN SETTLEMENT | 19 |
| PLANNING AND RESPONSE (INCLUDE COVID-19) | 2 |
| GOOD GOVERNANCE AND PUBLIC ACCOUNTABILITY | 7 |
| IMPLEMENTATION, CO-ORDINATION, MONITORING AND EVALUATION | 5 |
| TOTAL | 82 |

Composite Annual Action Plan 2023

| Programme (PBB) | Sub-Programme (PBB) |  | Broad Activities |  |  | Location | Timeframe (2023) |  |  |  |  | Cost |  |  | Programme Status |  |  | Implementing Institution/Department |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 | Q4 | GoG | IGF/ABFA | Others | New | Ongoing |  | Lead | Collaborating |  |  |  |
| DEVELOPMENT DIMENSION: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Strong and Resilient Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organise 4 stakeholders forum on business counselling |  |  | Juaboso |  |  |  |  |  | 4,500.00 |  |  |  | On-going |  | BAC | JDA, GEA, MOTI |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Construction of 2No 6Unit Market sheds |  |  | Boinzan |  |  |  |  |  | 300,000.00 |  |  | New |  |  | Central Admin | JDA |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Formalize Business registration and certification |  |  | District wide |  |  |  |  |  | 4,500.00 |  |  |  | On-going |  | BAC | GEA/ Clients |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize 2 training workshop on technology improvement in cosmetics and bead making |  |  | Selected communities |  |  |  |  |  | 15,000.00 |  |  |  | On-going |  | BAC | GEA/DA |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize 2 financial literacy training |  |  | Komeanmaa Mantukwa |  |  |  |  |  | 5,000.00 |  |  |  | On-going |  | BAC | GEA/DA |  |  |  |
| Focus area: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agricultural Development | Organization of community and district planning session |  |  |  | Juaboso |  |  |  |  |  |  |  | 5,050.00 |  | On-going |  | Agric. dept | RADU, Research, NGOs, DA, Farmers |  |  |  |
| Economic Development | Agricultural Development | Organization of District Farmers Day |  |  |  | District wide |  |  |  |  |  |  |  | 80,000.00 |  | On-going |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Carry out Oil Palm plantation Project |  |  |  | Selected communities |  |  |  |  |  | 150,000.00 |  |  |  | On-going |  | D.A | GHA. PRDT SAFETY NET PHS II |  |  |  |
| Economic Development | Agriculture Development | Carry out field monitoring and supervision |  |  |  | District wide |  |  |  |  |  |  |  | 6,200.00 |  |  |  | Agric. Dept |  |  |  |  |
| Economic Development | Agriculture Development | Conduct 7 trainings and workshops for staff and farmers |  |  |  |  |  |  |  |  |  | 58,000.00 |  |  | New |  |  | D.A | GHA. PRDT SAFETY NET PHS II |  |  |  |
| Development Dimension: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Education and Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organise Science, Technology, Mathematics, and Innovative Education (STMIE) clinics |  |  | Juaboso |  |  |  |  |  |  | 3,000.00 | 3,000.00 |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Support the District Education Oversight Committee to monitor teaching and learning in schools |  |  | Juaboso |  |  |  |  |  |  | 4,500.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organisation of Independence day celebration |  |  | Juaboso |  |  |  |  |  |  | 43,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organise reading festivals to create awareness and encourage children to read |  |  | Juaboso |  |  |  |  |  |  |  | 5,000.00 |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organise mock examination for JHS three students |  |  | District wide |  |  |  |  |  |  | 20,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Deliver Social Services Education and Youth Dev’t. |  |  | District wide |  |  |  |  |  |  | 150,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1 No. 3 Unit Classroom block & Ancillary facility |  |  | Nkra |  |  |  |  |  |  | 393,227 |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1 No. 3 Unit Classroom Block , 3 KVIP & 3 Urinal at |  |  | Danyame |  |  |  |  |  |  | 167,234.80 |  |  |  | On-going On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Reactivation & Completion of 1No. 6 Unit Classroom Block and ancillary |  |  | Benchima |  |  |  |  |  |  | 51,758.96 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1No. 3Unit Classroom Block & Ancillary Facility |  |  | Komeamaa |  |  |  |  |  |  | 14,399.08 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1 No. 6 Unit Classroom block & Ancillary facility |  |  | Yawagyimkrom |  |  |  |  |  |  | 93,227.15 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1 No 6Unit classroom block |  |  | Mantukwa |  |  |  |  |  |  | 41,103.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1 No 6Unit classroom block |  |  | Eteso |  |  |  |  |  |  | 54,963.99 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Focus area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Development | Support the organisation of inter district sports festival |  |  | Juaboso |  |  |  |  |  |  | 15,000.00 |  |  | New |  |  | GES | JDA |  |  |  |
| Focus area: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Construction of 1N0. CHPS Compound |  |  |  | Keyfas |  |  |  |  |  | 350,000.00 |  |  | New |  |  | District Health | DA |  |  |  |
| Social Services Delivery | Health Delivery | Construction of 1 No. 4Unit Nurses quarters |  |  |  | Bonsu Nkwanta |  |  |  |  |  | 15,000.00 |  |  | New | On-going |  | District Health | DA |  |  |  |
| Social Services Delivery | Health Delivery | Organise T.B Case detection exercise at the end of 2023 |  |  |  | District wide |  |  |  |  |  | 16,5000.00 |  |  | New |  |  | District Health | DA |  |  |  |
| Social Services Delivery | Health Delivery | Intensify public education on causes, prevention and control of Malaria |  |  |  | District wide |  |  |  |  |  | 5,500.00 |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Focus area: HIV/AIDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | HIV/AIDS | Organize 95-95-95 campaigns in selected communities |  |  |  | District-wide |  |  |  |  |  | 6,000 |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | HIV/AIDS | Ensure celebration of World HIV/AIDS day and Know your status Campaigns |  |  |  | District-wide |  |  |  |  |  | 7,500 |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | Health Delivery | Provide support for organization of health education on communicable and non-communicable diseases on local FM station |  |  |  | District-wide |  |  |  |  |  | 3,000.00 |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Focus area: Environmental and Sanitation Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Organized medical screening exercise |  |  |  | District wide |  |  |  |  |  | 6,000.00 |  |  |  | On going |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Facilitate the organization of monthly national sanitation day |  |  |  | District wide |  |  |  |  |  | 60,000 |  |  |  | On going |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Quarterly pushing/leveling of final dumping site |  |  |  | District wide |  |  |  |  |  | 80,000.00 |  |  |  | On going |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Undertake premises inspection |  |  |  | District wide |  |  |  |  |  | 3,000.00 |  |  |  | On going |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Orientation of food and drink vendors |  |  |  | District wide |  |  |  |  |  |  | 16,000.00 |  |  |  |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Undertake refresher training for sanitation guards |  |  |  | District wide |  |  |  |  |  |  | 6,000.00 |  | New |  |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Developing new DESSAP |  |  |  | District wide |  |  |  |  |  |  | 6,000.00 |  | New |  |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Celebration of environment/ sanitation days |  |  |  | District wide |  |  |  |  |  |  | 8,000.00 |  |  |  |  | DEHU | DA |  |  |  |
| Focus area: Population Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Population management | Organize radio and community information center discussions on birth and death registration |  |  |  | District-wide |  |  |  |  |  |  | 6,000.00 |  |  | On-going |  | Birth & Death department | GHS, communities, traditional and religious leaders |  |  |  |
| Social Services Delivery | Population management | Registration of births and deaths in the district |  |  |  | District-wide |  |  |  |  |  |  | 4,500.00 |  | New |  |  | Birth & Death department | GHS, |  |  |  |
| Focus area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Child development and protection | Monitor of 20 existing Community Child Protection Committees (CCPCs |  |  |  | District-wide |  |  |  |  |  |  | 1,000.00 |  |  | Ongoing |  | SWCD Central Admin | CRI, Mondelez ILO |  |  |  |
| Social Services Delivery | Child development and protection | Increase education and advocacy on Gender-Based Violence and spousal abused in 20 communities |  |  |  | 20 Communities |  |  |  |  |  | 1,000.00 |  |  |  | Ongoing |  | SWCD Central Admin | CRI, Mondelez ILO |  |  |  |
| Social Services Delivery | Child development and protection | Create awareness for parents to protect their children from neglect, discrimination, exposure to physical and moral threats and oppression |  |  |  | District-wide |  |  |  |  |  | 2,550.00 |  |  |  | Ongoing |  | SWCD Central Admin | Planning Unit / Gender Desk Officer |  |  |  |
| Disability and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | Support and to train 60% of registered PWDs in the District to engage in economic and business ventures |  |  |  | Four (4) communities |  |  |  |  |  | 85,000.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | Facilitate the registration and renewal of 500 vulnerable groups such as PWDs, LEAP onto NHIS |  |  |  | 20 Communities |  |  |  |  |  | 19,000.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Gender Empowerment | Monitor the LEAP beneficiaries make good use of their transfer grants. |  |  |  | 5 communities |  |  |  |  |  | 1,500.00 |  |  |  | Ongoing |  | SWCD Central Admin | GDO NGOs |  |  |  |
| Social Services Delivery | Gender Empowerment | Crate awareness creation on voluntary participation in community development projects in 20 communities. |  |  |  | 20 Communities |  |  |  |  |  | 2,000.00 |  |  |  |  |  | GDO | SWCD, NGO |  |  |  |
| Social Services Delivery | Gender Empowerment | Monitoring of Five (5) Village Savings and Loans Associations (VSLA) quarterly |  |  |  |  |  |  |  |  |  | 1,200.00 |  |  |  |  |  | GDO | SWCD, NGO |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | To organize training workshops for the NGOs working within the District to understand the need to be registered with the department |  |  |  | Juaboso |  |  |  |  |  | 800.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Development Dimension: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Protected Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out tree planting exercise in schools and other institutions |  |  |  | District wide |  |  |  |  |  | 13,000.00 |  |  | New |  | Forestry Commission |  |  |  |  | DA |
| Environmental and Sanitation Management | Natural Resource Conservation | Train male and female farmers on climate-smart agriculture |  |  |  | District wide |  |  |  |  |  | 15,000.00 |  |  | New |  | Forestry Commission |  |  |  |  | DA |
| Focus Area: Water Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Water resources management | Construct 10No. new boreholes |  |  |  | District wide |  |  |  |  |  | 350,000.00 |  |  | New |  | DWE |  |  |  |  | CWSA, DP |
| Key Focus Area: Climate variability and change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Supply 45,000coconut seedlings to 300 farmers a seedlings to 80 farmers. |  |  |  | District wide |  |  |  |  |  | 18,000.00 | 20,000.00 |  | New |  | MoFA |  |  |  |  | JDA |
| Environmental and Sanitation Management | Natural Resource Conservation | Train male and female farmers on climate-smart agribusiness |  |  |  | District wide |  |  |  |  |  | 10,000.00 |  |  | New |  | MoFA |  |  |  |  | JDA |
| Focus area: Transport Infrastructure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance and reshaping of 135 km feeder roads |  |  |  | District Wide |  |  |  |  |  | 345,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Construction of 2No. culverts |  |  |  | Ywagyim, Eteso |  |  |  |  |  | 300,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance of Assembly vehicle |  |  |  | Juaboso |  |  |  |  |  | 36,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Maintenance of Assembly grader |  |  |  | Juaboso |  |  |  |  |  | 88,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Conduct sensitization campaign on road safety regulations |  |  |  | Juaboso Bonsu Proso and Boinzan |  |  |  |  |  | 10,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Focus area: Infrastructure and Infrastructure Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure delivery | Construction of durbar ground |  |  |  | Selected communities |  |  |  |  |  | 160,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Management and administration | General administration | Maintenance of office laptops, printers and photo copiers |  |  |  | Juaboso |  |  |  |  |  | 25,000 | 10,000 | - | - | On-going | ICT officer |  |  |  |  | Central admin store keeper |
| Management and administration | General administration | Maintenance of official buildings and accommodation |  |  |  | Juaboso |  |  |  |  |  | 45,000 | 20,000 | - | New | - | JDA |  |  |  |  | MLGDRD |
| Focus area: Energy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Human Settlements and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Organize radio sensitization on building permit |  |  |  | Juaboso |  |  |  |  |  | 5,000.00 |  |  |  | On-going | Works/Planning |  |  |  |  | LUSPA |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Expansion of street naming and property addressing system |  |  |  | Bonsu Nkwanta Boinzan |  |  |  |  |  | 40,000.00 |  |  |  | On-going | Works/Planning |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Enforce planning and building regulations |  |  |  | District-wide |  |  |  |  |  | 6,000.00 |  |  |  | On-going | Works/Planning |  |  |  |  | Central Admi |
| Focus area: Disaster Prevention and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Hold disaster management committee meeting |  |  |  | District-wide |  |  |  |  |  | 4,500 |  |  | New |  | NADMO |  |  |  |  | Central Admi |
| Environmental and Sanitation Management | Disaster Prevention and Management | Reformation of DVG’s |  |  |  | District-wide |  |  |  |  |  | 5,000 |  | 5,000 | New |  | NADMO |  |  |  |  | Central Admi |
| Environmental and Sanitation Management | Disaster Prevention and Management | Organize bush fire campaign on radio in 4 communities |  |  |  | Kotosah, Brekrom Asempeneye Bremam |  |  |  |  |  | 8,000 |  |  | New |  | NADMO, GNFS |  |  |  |  | Central Admi |
| Development Dimension: Governance, Corruption and Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Local Government and Decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Organize sub-committee, general assembly meeting, and management meetings |  |  |  | Juaboso |  |  |  |  |  | 60,000.00 |  |  | New |  | Central Admi |  |  | MLGDRD NALAG |  |  |
| Management and administration | General administration | Prepare and submit monthly and quarterly progress reports |  |  |  | Juaboso |  |  |  |  |  | 10,000.00 |  |  |  | Ongoing | DPCU |  |  |  |  |  |
| Management and administration | General administration | Organised quarterly Audit Committee meetings |  |  |  | Juaboso |  |  |  |  |  | 24,000.00 |  |  |  | Ongoing | Audit committee |  |  |  |  |  |
| Management and administration | General administration | Provide financial support for anti-corruption activities |  |  |  | Juaboso |  |  |  |  |  | 10,000.00 |  |  | New |  | NACAP Desk Officer |  |  | Central Admi, CHRAG, NCCE |  |  |
| Focus area: Security and public safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Provide financial support for conflict and DISEC activities |  |  |  | District wide |  |  |  |  |  | 11,000.00 |  |  |  | Ongoing | JDA |  |  |  | Security Agencies |  |
| Management and administration | General administration | Sensitize the public on violent extremism, security consciousness through radio and community visits |  |  |  | Juaboso |  |  |  |  |  | 15,000.00 |  |  | New |  | NCCE, GPS |  |  |  | Central Admi |  |
| Emergency Planning And Response (Include COVID-19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Emergency Planning and response | Health delivery | Carry out active surveillance of diseases of public health importance |  |  |  | District-wide |  |  |  |  |  | 10,000 | 2,000 |  | New |  | DHD |  |  |  | NADMO, JDA |  |
| Emergency Planning and response | Health delivery | Conduct outbreak investigation |  |  |  | District-wide |  |  |  |  |  | 7,000 | 3,000 |  | New |  | DHD |  |  |  | NADMO |  |
| Focus area: IMPLEMENTATION, CO-ORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination |  |  | Prepare 2024 Annual Action Plan |  | Juaboso |  |  |  |  |  | 10,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination |  |  | Prepare 2024 composite budget and procurement plan |  | Juaboso |  |  |  |  |  | 35,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination |  |  | Organize 2 Town Hall meetings |  | Juaboso |  |  |  |  |  | 40,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination |  |  | Ensure Monitoring of all development projects/programmes |  | Juaboso |  |  |  |  |  | 40,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination |  |  | Prepare and dissemination M&E reports |  | Juaboso |  |  |  |  |  | 13,000.00 |  |  | New |  | DPCU |  |  |  |  |  |