MEDIUM TERM DEVELOPMENT PLAN

(2022 - 2025)

PREPARED BY: DPCU

JUABOSO DISTRICT ASSEMBLY

P.O BOX 1,

JUABOSO

WESTERN NORTH REGION.

NOVEMBER, 2021

TABLE OF CONTENT

EXECUTIVE SUMMARY	11

CHAPTER ONE	12

1.1 Introduction	12

1.2 MISSION, VISION, CORE VALUES AND FUNCTIONS OF THE ASSEMBLY	12

1.2.1 Vision Statement	12

1.2.2 Mission Statement	12

1.2.3 Core Values	12

1.3 Performance Review (2018-2021)	12

1.4.1 Lessons Learnt	19

1.5 Analysis of Revenue and expenditure performance	20

1.6 Analysis of Existing Situation/Profile of the District	20

1.6.1 Location and Size	20

1.7  Physical and Natural Environment	21

1.7.1 Natural Resource Endowment	21

1.7.2 Climate	22

1.7.3 Vegetation	22

1.7.4 Deforestation	23

1.7.5 Settlement and Built Environment	23

1.7.7 Illegal Mining	25

1.8 Demographic Characteristics	25

1.8.1 Population and Age Structure	25

1.8.2 Migration	26

1.8.3 Gender Equality	26

1.8.4 Societal Role of Gender	26

1.9 Culture	27

1.9.1 The Traditional Set Up	27

1.10 Ethnic Diversity	27

1.10.1 Ethnicity	27

1.10.2 Religion	28

1.10.3 Cultural Practise	28

1.11 SOCIAL SERVICE DELIVERY	28

1.11.1 Education	28

1.11.2 Health Care	30

1.11.3 Availability of health Professional	30

1.11.4 Health facilities	30

1.12 Social Protection	31

1.13 Structure of the Local Economy	31

1.13.1 Household Income and Expenditure	32

1.13.2 Agricultural Activities	32

1.13.3 Job Creation	32

1.13.4 Market	33

1.14 Transportation Networks	33

1.15 Telecommunication Coverage	34

1.15.1 Information and Communication Technology (ICT)	34

1.15.2 Science, Technology and Innovation (STI)	34

1.16 GOVERNANCE	34

1.16.1 Security	34

1.16.2 Traditional Authority	34

1.17 Key development problems/issues/gaps identified from the situation analysis	35

CHAPTER TWO	38

Introduction	38

2.0 Application of Potentials, Opportunities, Constraints and Challenges (POCC)	38

2.1 Impact Analysis on Prioritized Issues from POCC	38

CHAPTER THREE	39

Introduction	39

3.0 Development Projections of the District for 2022-2025	39

3.1 Population Projections	39

3.2 Development Projections	40

3.3 Projection of Health Facilities Requirement	41

3.4 Sanitation projections	42

3.5.1 The Compound Matrix	53

CHAPTER FOUR	55

INTRODUCTION	55

4.0 COMPOSITE PROGRAMME OF ACTION (POA)	55

CHAPTER FIVE	64

Introduction	64

5.1 Plan Implementation Arrangements	64

5.2 Institutional Arrangements	64

5.3 Administrative Arrangements	64

5.4 Community Participation	64

CHAPTER SIX	136

Introduction	136

6.1 Purpose of the Monitoring and Evaluation	136

6.2 Stakeholder Analysis	136

6.4 M & E Work Plan	145

6. 5 M & E Calendar	145

CHAPTER SEVEN	149

Introduction	149

7.1 Strategies	149

7.1.1 Approaches/Channels for Communication	151

ABBREVIATIONS

AAP                                                    - Annual Action Plan

AIDS                                                   - Acquired Immune Deficiency Syndrome

BAC                                                    - Business Advisory Committee

BECE                                                  - Basic Examination Certificate

CAP                                                    - Community Action Plan

CBO’s                                                 - Community Base Organizations

CLPC, s                                                - Community Led Protection committees

CHPS                                                  - Community Health Protection Services

CHRAJ                                               - Commission for Human Right and Administrative Justice

CLP                                                     - Cocoa Life Project

CLTS                                                   - Community Led Total Sanitation

CSM                                                    - Cerebra Spinal Meningitis

CWSA                                                 - Community Water Sanitation Agency

DA                                                       - District Assembly

DACF                                                  - District Assembly Common Fund

DBA                                                    - District Budget Analyst

DCD                                                    - District Coordinating Director

DCE                                                     -District Chief Executive

DDF                                                    - District Development Fund

DEHU                                                 - District Environmental Health Unit

DHD                                                   - District Health Directorate

DISAP                                                - District Sanitation Plan

DISEC                                                - District Security Committee

DMTDP                                              - District Medium Term Development Plan

DPCU                                                 - District Planning and Coordinating Unit

DPO                                                    - District Planning Officer

FSW                                                    - Female Sex Workers

GETFUND                                         - Ghana Education Trust Fund

GIFNET                                              - Governance Issue Forum Network

GoG                                                     - Government of Ghana

GSGDA II                                           - Ghana Shared Growth Development Agenda II

HIV                                                     - Human Immune Virus

ICT                                                     - Information and Communication Technology

IDA                                                    - International Development Assistant

IDEG                                                  - Institute for Democratic Governance

IGF                                                     - Internal Generated Fund

ISD                                                     - Information Service Department

JDA                                                     - Juaboso District Assembly

KVIP                                                  - Kumasi Ventilated Improved Pit

LBC                                            	- Licensed Buying Companies

LDP’S                                                - Local Development Plans

LED                                                   - Local Economic Development

LPG                                                    - Liquefied Petroleum Gas

M/E                                                    - Monitoring and Evaluation

MMDA’s                                           - Metropolitan, Municipal District Assemblies

MTDP                                                - Medium Term Development Plan

MTNDPF                                           - Medium Term National Development Plan Framework

NCCE                                               - National Commission for Civic Education

NGO’S                                              - Non- Governmental Organizations

NHIA                                                 - National Health Insurance Authority

NMTDPF                                          - National Medium Term Development Policy Framework

OPD                                                  - Out Patience Department

PHC                                                  - Population and Housing Census

PLHIV                                              - People Living With HIV

PM/E                                                - Participatory Monitoring and Evaluation

PoA                                                  - Programme of Action

POCC                                               - Potential Opportunities Constrains and Challenges

PRCC                                               - Public Relations and Complaints Committee

PTA                                                 - Parent and Teachers Association

PWD’s                                             - People Living with Disabilities

REDD+                                           - Reduce Emission from Deforestation and Degradation

RPCU                                              - Regional Planning and Coordinating Unit

RTP                                                 - Right To Play

SHEP                                              - Self Help Electrification Project

SMC                                               - School Management Committees

SME                                                - Small and Medium Enterprises

STI                                                  - Science, Technology and Innovation

STWS                                             - Small Town Water System

TB                                                   - Tuber Closes

UNDP                                             - United Nation’s Development Programme

VSLA                                             - Village Savings and Loans Associations

WATSAN                                       - Water and Sanitation Committee

WFCL                                            - Worst Form of Child Labour

WV                                                - World Vision

LIST OF TABLES

Table 1REVIEW OF 2018-2021 MEDIUM TERM DEVELOPMENT PLAN	14

Table 2: The Financial Performance of the District Assembly from 2018 - 2021	20

Table 3: Ethnic Compositions- Juaboso District	28

Table 4: No of School in the District	29

Table 5: Enrolments in Basic Schools	29

Table 6: Basic Schools Enrolment and Staffing Levels – 2021	29

Table 7: Spatial distribution of health facilities by sub districts and types of facilities.	30

Table 8: Summary of Key Issues Development Issues of CPESDP	35

Table 10: Projected Total Population and Sex Composition of the District	40

Table 11: Age Distribution and Projected Population in the District	40

Table 12: Projection of Health Facilities and Doctors Needed	41

Table 13: Population Projection of Water Facilities	42

Table 14: Sanitation Projections	42

Table 15: Basic School Classroom Infrastructure Projections – 2022-2025	42

Table 16: NUMBER OF TEACHERS TRAINED AND UNTRAINED	43

Table 17: ENROLMENT IN BASIC SCHOOLS	44

Table 18: Revenue Projections for All Revenue Sources	44

Table 19: Expenditure Projections	45

Table 20: District Goals, Prioritized Issues, Policy Objectives and Strategies for 2022-2025	46

Table 21: Compound Matrix Record Sheet	53

Table 22: Composite Programme of Action (POA) for Juaboso District (2022 – 2025)	56

Table 23: Programme Financing	63

Table 24: Shows the Composite Annual Action Plans	65

Table 25: Composite Annual Action Plan 2023	84

Table 26: Composite Annual Action Plan 2024	102

Table 27: Composite Annual Action Plan 2025	118

Table 28: Analysis of Stakeholders	137

Table 29: Monitoring Matrix	140

Table 30: M & E Work Plan 2022 – 2025	145

Table 32: M & E Calendar for 2022-2025	146

Table 33: M & E Budget 2022 - 2025	146

Table 34: Communication Strategy Matrix	150

Table 35: Operation and Maintenance Plan (2022-2025)	152

LIST OF FIGURES

Figure 1: JUABOSO DISTRICT IN WESTERN REGIONAL CONTEXT	21

Figure 2: JUABOSO DISTRICT LAND COVER	22

Figure 3: JUABOSO DISTRICT- HIERACHY OF SETTLEMENT	24

Figure 4: Population pyramid of age-sex structure	25

Figure 5: JUABOSO DISTRICT- Road Network in the District	33

Figure 6:Proposed Projects for 2022-2025 Medium Term Plan Period	45

# EXECUTIVE SUMMARY

The District Medium Term Development Plan (DMTDP) serves as a blueprint to guide the Juaboso District Assembly in its development endeavors. Like the previous plans, the plan is prepared with a guideline of a policy framework.

In preparing this MTDP, the Juaboso District Assembly made full use of its competent professional and technical staff. A Plan Preparation Task Force was formed and tasked with preparing the MTDP. The team is made up of the DCE, DCD, DPO, DBO, District Social Welfare officer and Representatives from the District Education, Health and Agriculture as well as other decentralized department and the executive of the four Area Councils. Opinion leaders in the various communities were not left out. The task force members who were all members of the DPCU organized workshops, collected data with the involvement of the District Assembly Members to identify their needs and aspirations. These needs and aspirations of communities were then subjected to a litmus test to find out their relationship with the development dimensions of the plan.

The District goal, objectives and strategies were generated through stakeholder’s meetings. To make the planning process participatory, public hearing were organized to enable the citizenry have their input into the plan and own it. Public hearings were organized in all the four (4) area councils in the District for review and validation

The MTNDPF has Four Broad Goals and their related Thematic or Development Dimensions. The broad goals are Build Prosperous Society, Create Opportunities for all Ghanaians, Safeguard the natural environment and ensure resilient built environment and maintain a stable, united and safe society. The development dimensions are Economic, Social Development, Environment, Infrastructure and Human Settlements, Governance, Corruption and Public Accountability and Ghana’s Role in International Affairs

The Plan has been structured into seven chapters. Chapter one is on performance review, analysis of current situation and development issues. Chapter two is on prioritization of development issues. This is followed by chapter three which focuses on the development goals, objectives and strategies to achieve them. Chapter four is on composite development programmes whiles the fifth chapter is on the annual action plans. The sixth chapter concentrates on Monitoring and Evaluation arrangements and the seventh Chapter focuses on the communication strategies of the plan

# CHAPTER ONE

# PERFORMANCE REVIEW AND PROFILE/CURRENT SITUATION/BASELINE

## 1.1 Introduction

Chapter one discusses the status of performance of the Municipality on the implementation of its Medium Term Development Plan (DMTDP) 2018-2021 base on the Medium-Term National Development Policy Framework (MTNDPF 2018-2021) captioned “An Agenda for Jobs: Creating Prosperity and Equal Opportunity for All” with respect to outcomes/ impact indicators and financial performance and highlights the vision, mission and core values of the Assembly as well as analysis of existing situation (Location and physical characteristics, Demographic characteristics, Social, Economic, Infrastructure, Environment, Governance, Hazards, Disaster and   Security as well as list of development issues in the district.

## 1.2 MISSION, VISION, CORE VALUES AND FUNCTIONS OF THE ASSEMBLY

### 1.2.1 Vision Statement

To be among the first class District in the country.

### 1.2.2 Mission Statement

The Mission Statement of Juaboso District Assembly (JDA) exists to raise the living standards of the people through formulation and implementation of policies in partnership with local development stakeholders to improve access to basic services to create opportunities for wealth creation.

### 1.2.3 Core Values

The core values of the Juaboso district include:

- Accountability

- Client Oriented

- Commitment

- Timeliness

- Transparency

## 1.3 Performance Review (2018-2021)

To inform the preparation of the Medium-Term Development Plan (2022-2025), a performance review was conducted on the previous plan which was prepared under the Coordinated Programme of Economic and Social Development Policies CPESDP (2018-2021) - An Agenda for Jobs: Creating Prosperity and Equal Opportunity for All to ascertain the progress made and challenges encountered for Management decisions and actions. This was done to measure the extent to which the Assembly was able to execute its proposed development initiatives and hence the achievement of its development objectives and goals in relation to the outcome and impact indicators. The outcome of the review provided lessons and best practices as inputs for the preparation and implementation of the (2022 – 2025 Medium-Term Development Plan.

The CPESDP (2022-2025) was hinged on five (5) development dimensions, which are Economic development, Environmental Infrastructure and Human Settlement, Social Development, Governance, Corruption and Public Accountability and Strengthening Ghana’s Role in International Affairs. The Assembly however formulated its programmes, projects/activities for four (4 development dimensions relevant to the development of the district. The performance of the district under the four (4) development dimensions from 2018-2021 is presented below;

The Performance Review of the District in Implementing Programmes and Projects under “An Agenda for Jobs: Creating Prosperity and Equal Opportunity for All.

Table 1REVIEW OF 2018-2021 MEDIUM TERM DEVELOPMENT PLAN

| Development Dimension of Agenda for Jobs) | Indicator | Baseline | 2018-2021 medium term target | DEVELOPMENT OUTCOME |  |
| --- | --- | --- | --- | --- | --- |
|  |  | 2017 |  | YEAR | DATA |
| ECONOMIC DEVELOPMENT | % change in yield of selected crops and livestock - Maize - Rice (milled), - Cassava - Plantain - Yam - Cattle - Goat - Sheep - Pig - Poultry Extension Service to Farmer Ratio |  |  |  |  |
|  |  | 18% | 25% | 2021 | 28% |
|  |  | 21% | 25% | 2021 | 26% |
|  |  | 7% | 10% | 2021 | 7.9% |
|  |  | 8% | 10% | 2021 | 11.26% |
|  |  | 9% | 10% | 2021 | 4.81% |
|  |  | 45% | 50% | 2021 | 51% |
|  |  | 85% | 100% | 2021 | 119.20% |
|  |  | 70% | 100% | 2021 | 78% |
|  |  | 39% | 50% | 2021 | 49% |
|  |  | 160% | 200% | 2021 | 200.84% |
|  |  | 1:8,636 | 50% | 2021 | 1:2,616 |
|  | Percentage of arable land under cultivation | 40% | 65% |  | 57% |
|  | Number of new industries established - Agriculture, - Industry, - Service | 6 | 10 | 2021 | 4 |
|  |  | 3 | 5 | 2021 | 1 |
|  |  | 10 | 15 | 2021 | 6 |
|  | % change in jobs created - Agriculture - Industry - Service |  |  |  |  |
|  |  | 37% | 46% | 2021 | 46% |
|  |  | 23% 21% | 33% 41% | 2021 2021 | 39% 44% |
| SOCIAL DEVELOPMENT |  |  |  |  |  |
|  | Net enrolment ratio i. Kindergarten ii. Primary iii. JHS |  |  |  |  |
|  |  | 90% | 87% | 2021 | 110% |
|  |  | 90% 80% | 87% 82% | 2021 2021 | 110% 100% |
|  | Gender Parity Index - Kindergarten - Primary - JHS - SHS |  |  |  |  |
|  |  | 0.85 | 1.00 | 2021 | 0.87 |
|  |  | 0.75 | 0.95 | 2021 | 0.80 |
|  |  | 0.80 0.67 | 0.99 0.94 | 2021 2021 | 0.82 0.80 |
|  | Completion rate - Kindergarten - Primary - JHS - SHS |  |  |  |  |
|  |  | 90% | 95% | 2021 | 97% |
|  |  | 80% | 90% | 2021 | 95% |
|  |  | 80% 70% | 72% 75% | 2021 2021 | 80% 78% |
|  | Number of operational health facilities - CHP Compound - Clinic - Health Centre - Hospital |  |  |  |  |
|  |  | 23 | 30 | 2021 | 0 |
|  |  | 4 | 4 | 2021 | 0 |
|  |  | 1 1 | 2 1 | 2021 2021 | 0 0 |
| - Social Development | Proportion of population with valid NHIS card - Total (by sex) - Indigents - Informal - Aged - Under 18years - pregnant women |  |  |  |  |
|  |  | Total: 35.8% | Total: 68% |  | Total: 40.7% |
|  |  | Indigents:13% | Indigents: 10% | 2021 | Indigents: 12% |
|  |  | Aged: 3% | Aged: 5 % | 2021 | Aged: 4% |
|  |  | Under 18 years:47% | Under18 yrs:50 | 2021 | Under18years:43% |
|  |  | Pregnant women:3% | Pregnant women:6% | 2021 | Pregnant women: 4% |
|  | Number of births and deaths registered Birth (sex) - Male - Female |  |  |  |  |
|  |  | 1544 | 2,230 | 2021 | 2,540 |
|  |  | 1277 | 2,543 | 2021 | 2,234 |
|  | Percentage of population with sustainable access to safe drinking water sources - District - Urban - Rural |  |  |  |  |
|  |  | 68% | 80% | 2021 | 76% |
|  |  | 40% | 78% | 2021 | 65% |
|  |  | 28% | 57% | 2021 | 46% |
| - Social Development | Proportion of population with access to improved sanitation services - District - Urban - Rural |  |  |  |  |
|  |  | 35% | 45% | 2021 | 50% |
|  |  | 30% 5% | 30% 5% | 2021 2021 | 37% 6% |
|  | Maternal mortality ratio (Institutional) | 38/100000LB | 125/100000LB | 2021 | 122.8/100000LB |
|  | Malaria case fatality (Institutional) | 0.05 | 0.5 | 2021 | 0.0 |
| - Social Development | Percentage change in reported case of abuse |  |  |  |  |
|  | Child trafficking (sex) Male Female - Child abuse (sex) Male Female |  |  |  |  |
|  |  | 2% | 1% | 2021 | 0.5% |
|  |  | 2% | 1.5% | 2021 | 0.8% |
|  |  | 25% | 23% | 2021 | 21% |
|  |  | 30% | 25% | 2021 | 23% |
| - Environment, Infrastructure and Human Settlement | Percentage of road network in good condition Total Urban Feeder |  |  |  |  |
|  |  | 65% | 80% | 2021 | 69% |
|  |  | 71% 30% | 69% 55% | 2021 2021 | 65% 45% |
|  | Percentage of communities covered by electricity |  |  |  |  |
|  | District Rural Urban | 75% | 90% | 2021 | 93% |
|  |  | 50% | 87% | 2021 | 80% |
|  |  | 79% | 98% | 2021 | 90% |
| Governance Corruption and Public Accountability | Percentage change in cases of crime - Men, - Women - Children |  |  |  |  |
|  |  | 4.05 | 6% | 2021 | 4% |
|  |  | 3% 2% | 5% 2% | 2021 2021 | 3.5% 1.5% |
|  | Percentage of annual action plan implemented | 80% | 78% | 2021 | 75% |
|  | Number of communities affected by disaster |  |  |  |  |
|  | - Bushfire | 3 | 4 | 2021 | 3 |
|  | - Floods | 2 | 4 | 2021 | 2 |
|  | Police Citizen Ratio | 1:3509 | 1:1000 | 2021 | 1:2467 |

1.4 Key issues of the Implementation of the 2018-2021 DMTDP

Some key lessons / experiences the district learnt / gathered during the execution of the 2018 - 2021 DMTDP which may have possible development implications for the 2022-2025 DMTDP include the following:

- Delay in completion of some projects due to lack of funds.

- Targets set for certain objectives were too high and unattainable during the planned period.

- Inadequate monitoring, supervision and evaluation of projects and programmes implementation.

- Low commitment of DA, NGOs and Donors towards implementation of some projects vis-à-vis high commitment shown by the same stakeholders towards other projects.

- Low income among the people and the people bad attitude towards payment of taxes affected adequate revenue generation.

- The outbreak of the covid-19 affected implementation of programmes and projects of the Assembly.

- Effective involvement/participation of communities, Private Sector, NGOs Donors, Decentralized Departments and other stakeholders in the implementation process was key.

- Low participation of project beneficiaries in monitoring and evaluation

- Low commitment of some communities towards projects implementation in communities.

- Targets set for certain projects were too high and unattainable during the plan period.

- Effective collaboration/partnership between DA and other Decentralized Department, Donors, NGOs, CBOs and other stakeholders in service provision.

- Regular M & E of projects was crucial in the successful implementation of the plan.

### 1.4.1 Lessons Learnt

Following the challenges that the Assembly faced during the implementation of the 2018-2021 DMTDP, lessons were learnt to improve the implementation of the 2022-2025 DMTDP. These lessons are;

- The implementation of the 2018-2021 DMTDP depended heavily on external funds and as a result, delay in release of funds from these funding sources affected implementation of programmes and projects of the Assembly. There is therefore need to adopt innovative strategies to increase Internally Generated Funds (IGF) to finance significant proportion of planned projects/activities.

- Ensure proper coordination of implementation of programmes and activities in the district

- Put in place emergency plans and strategies to deal with future disasters and pandemic occurrences

- Engage private sector players to partner the district assembly where necessary.

- Conduct regular and participatory monitoring, supervision and evaluation.

Table 2: The Financial Performance of the District Assembly from 2018 - 2021

| SOURCE OF FUNDS | ETIMATED COST OF PLAN | TOTAL RECEIVED | VARIANCE |
| --- | --- | --- | --- |
| GoG | 6,975,774.98 | 5,761,329.71 | 1,214,445.25 |
| IGF | 2,183,387.95 | 1,313,498.17 | 869,889.78 |
| DACF-RGF | 2,435,423.62 | 1,357,165.03 | 1,078,258.59 |
| DPs | - | - | - |
| DACF | 12,646,013.09 | 5,317,353.58 | 7,328,659.51 |
| DP(MAG) | 356,500.97 | 341,142.32 | 15,088.65 |
| MP CF | 1,213,363.63 | 1,115,775.51 | 97,588.12 |
| TOTAL | 25,810,464.24 | 15,206,534.32 | 10,603,929.92 |

Source: District Budget Unit/ Account Department 2021

## 1.5 Analysis of Revenue and expenditure performance

The total amount received in the district indicates that the income received within the last plan period was not adequate to implement all programmes and projects. Over the plan period, the Assembly was able to mobilise/receive Ghc15,206,534.32 representing a short fall of 41%. The trend is that there has been consistent fall in the Assembly’s revenue projections or planned as against the actual received from 2018 to 2021 as indicated in Table 2.0

The implication of this is that expenditure patterns are negatively affected as most development programme/projects cannot be executed and those that will be implemented may unduly delayed. It is important that adequate resources are mobilised in the next plan period (2022-2025) to implement almost all the programmes/projects earmarked in the plan.

## 1.6 Analysis of Existing Situation/Profile of the District

Analysis of existing conditions is essential elements or factors for determining socio-economic development of the District.  This stems from the fact that apart from being potential resources, they also serve as framework within which all development activities take place.  The major factors that need critical analysis, and their implications for development in the district include location and size, demographic characteristics, social, economic, infrastructure, environment, governance, hazard, disaster and security etc. The interaction between the human and physical environment and its development implications with respect to the above major factors are clearly and briefly described below.

### 1.6.1 Location and Size

Juaboso District being one of the Nine districts in the Western North Region is located between latitude 60 65 ‘N and 60 22’ N, and longitude 30 22’W and 20, 66’W.

The District shares borders with Bia West and Asunafo North Municipal in the North, Asunafo South and Sefwi Wiawso Municipal to the East, Bodi district to the south and La Cote D’lvoire to the west.

The district has a surface area of 1,370 square kilometers and serves as entry/exit point between La Cote d’Ivoire.

The district capital Juaboso is located 66 km to Sefwi Wiawso, the Regional capital and a distance of 225 km from Kumasi, the Regional capital of Ashanti Region.

Figure 1: JUABOSO DISTRICT IN WESTERN REGIONAL CONTEXT

## 1.7  Physical and Natural Environment

### 1.7.1 Natural Resource Endowment

The natural resources of the district like Gold, Timber, agricultural lands and even rivers that runs through the district have importance/implications for development in a district. The good climatic condition experience in the district promotes all year round cultivation of food crops. It also promotes the cultivation of cash crops like cocoa which is one of the major exports of the country. Juaboso district is one of the few districts in the country that have a rich forest reserve which influence the quality of biodiversity within the district and provides habitat for many animals. The district can boast of an ever green natural environment ranging from forest reserves with rich species of fauna and flora to vast arable land as well as good climatic conditions that can support the production of food and cash crops.

The forest reserves that are found in almost every part of the District have abounded high economic trees. However, the extensive human landscape modifications (farming, mining and chain saw operations) have dramatically changed the character of the ecosystem within the district especially around communities that depend on the forest for survival.

The erratic rainfall (recording low volumes) experience last year coupled with fluctuation temperatures is a sign of change in the weather pattern. This if continue will affect the production of cocoa in the district and the nation as a whole.

Figure 2: JUABOSO DISTRICT LAND COVER

### 1.7.2 Climate

The district lies in the wet semi-equatorial climatic zone with two rainfall peaks (maxima) in May-June and September-October. The area experiences two main wet and dry seasons with mean annual rainfall figures ranging from 1,250-2,000mm. The wet season is between April and October and the dry season is between November and March. The relatively long wet (rainy) season favors the cultivation of many food and cash crops, especially cocoa. However, this abundant rainfall sometimes disrupts the smooth implementation of development project, including road and building construction. The Krokosue forest, which is earmarked as an international forest reserve also enhances the districts eco system. The mean annual temperature for the district ranges between 25ºC and 26ºC. The highest temperature, which is recorded between March and April, is about 300ºC. The area also records high Relative Humidity figures, ranging from 75-90% during the wet season and 70-80% during the dry season.

### 1.7.3 Vegetation

The District’s vegetation is of moist semi-deciduous forest type.  The forest foliage is made up of upper, middle and low canopies.  As the name “semi-deciduous” implies most of the trees in the upper and middle layers shed their leaves during the dry season while the lower layer remains evergreen. The forest vegetation is normally made up of hundreds of different tree species.  Some of the important species found in the district include Wawa, Mahogany, Esa, Ofram, Edinam, Onyina, Kyenkyen and Odum.  There are three forest reserves in the district, namely Bia Torya, Bia game reserve and Krokosue Forest Reserves.  These are productive reserves where timber harvesting is done.  The forest reserves are also intended to preserve the environment and the eco system of the District.

Effective strategies (like the Ghana-REDD+ strategies) are now in place to prevent degradation of Bia (The core zone which is around 306km is still intact) Forest reserve, the only reserve which is currently not degraded like the other reserves in the district. This has been achieved through boundary line planting (About 92.7km has been planting out of 100km).

### 1.7.4 Deforestation

The Juaboso district is one of the few districts in the country that has large tracks of forest land which is the main economic resource base of the district. These are the Bia game reserve and krokosua forest reserve. However, the high exploitation of timber for logs and lumber by both registered timber firms and illegal chainsaw operators has contributed significantly to deforestation in the district. Illegal mining popularly known as Galamsey and Unchecked farming practices including cocoa farming has also compounded the situation through encroachment on the virgin forest and forest reserves. . Tree planting is one major area considered. UNDP for instance is engaging community members in tree planting. The forest division will also be implementing its REDD+ activities in the District. Through the youth in afforestation programme about 300 youths have been employed to replant degraded and mining areas. The livelihoods enterprises development is also on-going with the Bee-keeping being the most successful enterprise.

### 1.7.5 Settlement and Built Environment

Data from the District Assembly indicates that the District has 24,522 houses.  The housing stock in the semi urban towns of Juaboso, Bonsu Nkwanta and Proso Kofi Krom constitute 29.4% whiles the remaining constitute the housing stock in other areas of the district.

Most houses in the district are of very poor quality because the building materials used are of poor quality.  Many houses have structural defects, dilapidated, cracked or have its foundations exposed through erosion.  The high cost of building materials may account for the poor housing quality, as well as unwillingness of the migrant cocoa farmers who own substantially 67% of the farms in the district to invest in the infrastructural development.

1.7.6 Hazards

Hazards encompass wide range of physical, chemical, biological and social activities that have a potential to threaten the natural ecosystem and the natural environment at large. The most common form of hazards is the environmental hazards that affect people’s, including pollution and natural disasters. Hazards are said to emanate from natural induced events whilst others include events triggered by human actions. More recently human induced activities such as release of toxic waste, waste home chemicals, extreme use of pesticides, pollutants from heavy metals and water pollution is adversely affects in many lives. In the Juaboso district the most prevalent form of hazards are extremely use of pesticides among crop farmers, pollution of major water sources thorough galamsey activities and illegal chain saw operators. All these are imposing threats to human health and the ecological ecosystem within the district.

For this reason, the Juaboso district have increase its operations for forming anti-galamsy groups, increase awareness on climate change mitigation strategies, training of farmers on best agricultural practices. NGO’s like the Tropenbos Ghana, UNDP, World Vision, have contributed in this regard.

1.7.7 Disaster

Disasters are of great concern across different parameters of humanitarian development. Disasters are said to make up two forms, that’s natural disasters and made-up disasters. In all the two forms, disasters have adverse effect on lives, health, nutrition, income, among others. Considering rapid population growth, global climate change activities, urbanization, and land degradation, there is a high frequency and magnitude of disasters to occur in the near future. More recently, issues pertaining to weather conditions (air, water, pressure, and sunlight), drought, flooding, and hazards are constantly increasing vulnerabilities among various occupations. This is because disaster and vulnerability is interlock in nature. This therefore requires a systematic policy dimension.

Disasters such as hydro-met disaster (lightening, rainstorms and floods) and made disasters (bush fires, domestic fires and illegal mining) are some of the disasters that occur in the Juaboso district.  Occassional occurance of Milipedes invasion in the Bonsu Nkwanta Township is also one form of disaster the assembly is battling with. Mitigation measures taken in the district includes, awareness creation and recruiting of volunteers in the various communities.

Figure 3: JUABOSO DISTRICT- HIERACHY OF SETTLEMENT

### 1.7.7 Illegal Mining

Illegal mining popularly known as Galamsey is another environmental disaster practiced by artisanal miners in the Juaboso district. Their activity creates small craters that act as receptacles for water pound that breeds mosquitoes and therefore constitute a health hazard. Worst of it is the distraction of land, vegetation and the pollution of water bodies which threatens aquatic lives and those who depend on the water for domestic use. With the effort of the Government in collaboration with the district assembly a task force will be form to arrest the situation.

## 1.8 Demographic Characteristics

The population characteristics of every geographical area are very essential for planning and developmental purposes. Designing programmes and projects are formulated to suit a specific number or group of people in a geographical area. Therefore, the demographic characteristics like age distribution, growth rate, dependency ratio, population density and migration patterns of people in the District are relevant for proper allocation of the district limited resources and facilities to sectors like health and education.

### 1.8.1 Population and Age Structure

According to the 2010 PHC the population of the Juaboso district in 2010 is 58,435 which is 2.46 percent of the Western North region population of 711,363. However, with a fertility rate of 4.2 the current population of the district stands as 91,879 with males constituting the majority in terms of sex (Male constitute 52.4% while 47.6% are female).

This gives a sex ratio of the population to be 103.7 (roughly, 100 females per 104 males) compared to 100 for the region as a whole. The highest sex ratio is among the 55-59 years’ age group (154.4), followed by 84-89 years’ age group (153.2) and 65-69 years’ age group (151.7). The lowest sex ratio is among the 80-84 years’ age group (58.7), followed by the 95-99 years’ age group (68.4). However, there is no consistency in the sex ratios among the five-year age groups. Generally, the sex ratio decreases steadily from the 0-4-year age group (105.5) to 25-29 years’ age group (88.6). It then increases in a fluctuating fashion to 154.4 among the 55-59 years’ age group. The trend is again downward in a fluctuating fashion as age increases to 68.4 among the 95-99 years’ age group. About 90.7 percent of the population is in rural localities and the remaining 9.3 percent are in urban localities. The district is therefore overwhelmingly rural. The population density of the district is 42.7 compared to 99.3 of the entire region.

Figure 4: Population pyramid of age-sex structure

### 1.8.2 Migration

The district can relatively be described as non-migrated populated district although there are few exceptions in some of the communities. 76.4 percent of people in the Juaboso district are non-migrants while 23.6 percent of the population is migrants. Among the migrants, 80.2 percent were born elsewhere in the Western North Region while 19.8 percent were born elsewhere in another region of Ghana. There are however variations in the number of migrants from other regions of Ghana. The percentage of migrants from other regions of Ghana ranges from a high (25.7%) in Upper East Region to a low (2.5%) in Central Region.

From the above statistic the district intern to benefit from farm labour (since most of the migrants come to the district due to cocoa farming) which will increase productivity. This whoever has a negative challenge in the provision of adequate infrastructure to meet the needs of every one. The health implications are enormous. Disease can easily be transferred from one region to the other.

### 1.8.3 Gender Equality

The 2010 population and housing census shows that, males in the Juaboso District are slightly more than that of the females. The male population forms 50.9 % of the total population of the district whiles that of the female is 49.1 %.

### 1.8.4 Societal Role of Gender

Women play a vital role in the society but most at times they are discriminated when it comes to decision making especially within the household. The responsibility of Women within a rural setting or household is enormous. They seek the welfare of the family, preparation of meals to fetching of water and firewood. In the Juaboso District where water coverage is low (49%), women/girls have to walk a long distance in search of water. This affects the girl child’s education as most of them have to walk a long distance to look for water before attending school.

In terms of social roles, Women play an important role in the development of rural economy. In the district, women are involved in the following economic activities; Trading, Soap making, farming among others.

Gender mainstreaming is a strategy for making women’s as well as men’s concerns an integral dimension of the design, implementation, monitoring and evaluation of the policies and programmes in all political, economic and societal spheres to bring mutual benefit.

These are the vulnerable groups in the district.

- People living with Disability

- Aged

- Children

- Widows

- People living with HIV/AIDS

The following are identified as key gender issues affecting development in the District:

- Employment and income, are largely captured by men whereas environmental and social risks tend to fall upon women

- Formal unemployment rates for women in the District are high.

- Marginalization of the poorest and most vulnerable members of the community mostly impacts women, the elderly and children.

- Negative environmental effects, including dislocation from agricultural lands, pressure on water supply and land for farming affect women most directly, as they traditionally have the role of household agricultural production, drawing water, washing clothes etc.

- There is an increase in dependency by females who are single parents.

- There is direct and indirect health risks for women through the increase in sexual diseases, including HIV/AIDS.

## 1.9 Culture

Culture is the way of life of group of people. This includes the knowledge, values and belief of the people, traditional set-up among others.

### 1.9.1 The Traditional Set Up

Juaboso is under the Sefwi Wiawso Traditional Council.  Sefwi’s are classified under the ethnic group of Akans of Ghana. The traditional authorities of the District are divisional chiefs who pay homage to the Omanhene (paramount chief) of Sefwi Wiawso.

The Sefwi state is divided into seven divisional chiefdoms each of the divisions is headed by a chief from the royal family of the traditional area which Juaboso District has one of the divisional chiefs at Boinzan (Krontihene). There are other non-divisional chiefs who control large tract of lands in the Juaboso district.  These include, chief of Mafia, Kogyina Agyemadiem, Seyerano and Benchema.

## 1.10 Ethnic Diversity

The Sefwis’ are classified under the ethnic group of Akans in Ghana. The Sefwis who are the indigenes people form majority of the district’s population. The settlers who play an important role in the district’s economy were attracted to the district due to its favorable climatic, vegetation and economic conditions.  The language spoken is Sefwi

The district is ethnically diverse as indicated in the table below: -

### 1.10.1 Ethnicity

Table 3: Ethnic Compositions- Juaboso District

| ETHNICITY | MALE | FEMALE | TOTAL |
| --- | --- | --- | --- |
| Sefwi | 26.1 | 26.1 | 52.2 |
| Brong/Ahafo | 14.3 | 11.2 | 25.5 |
| Ashanti | 5.1 | 3.3 | 8.4 |
| Northerners | 3.2 | 4.1 | 7.3 |
| Fanties | 2.2 | 2.1 | 4.3 |
| Others | 1.1 | 1.2 | 2.3 |
| TOTAL | 52 | 48 | 100 |

Source: statistical service 2010

### 1.10.2 Religion

Although the district habours different shades of religions, Christianity accounts for 80.6 percent, Islam 11.1 percent, traditional religion 0.6 percent, those with no religion 5.9 percent and others are 0.8 percent. There is religious tolerance and peaceful co-existence among the various religious groups in the district.

In terms of sex, there are relatively more Christians among the female population (84.2%) than among the male population (79.1%); and a relatively higher proportion among the male population (12.0%) is affiliated to Islam than among the female population (10.2%). The proportions among the male population who have no religion (7.5%) and traditionalist (0.7%) are higher than their female counterparts (4.2% and 0.4%, respectively).

### 1.10.3 Cultural Practise

Festivals

The people of Juaboso Traditional Area celebrate the “Alluolue” festival. It is an agricultural festival held to mark the end of one agricultural season and to welcome the next season. Though the festival is significant in the life of the people, many communities in the district do not celebrate it. However, a few communities who want to keep the cultural flames of the Sefwi’s burning make all the necessary effort to celebrate it regularly.

## 1.11 SOCIAL SERVICE DELIVERY

### 1.11.1 Education

The District has 289 Schools. Out of which 109 are Kindergarten schools made up of 69 public and 40 private, 110 primary schools, this is made up of 70 public and 40 private, 66 Junior High Schools made up of 40 public and 26 private schools and 5 senior high schools made up of 1 public, 1 community initiated and 3 private. The breakdown of number of schools in terms of Public and Private schools is shown

Table 4: No of School in the District

| S/N | LEVEL | PUBLIC | PRIVATE | TOTAL |
| --- | --- | --- | --- | --- |
| 1 | KG | 69 | 40 | 109 |
| 2 | PRIMARY | 70 | 40 | 110 |
| 3 | JHS | 40 | 26 | 66 |
| 4 | SHS | 1 | 3 and 1community | 4 |

Table 5: Enrolments in Basic Schools

| S/N | LEVELS | PUBLIC |  | PRIVATE |  |
| --- | --- | --- | --- | --- | --- |
|  |  | BOYS | GIRLS | BOYS | GIRLS |
|  | KG | 2251 | 2138 | 2476 | 2566 |
|  | PRIMARY | 5485 | 5403 | 4656 | 4436 |
|  | JHS | 2459 | 2280 | 1242 | 1116 |
|  | SHS | 786 | 689 | 354 | 224 |
|  | TOTAL | 10,981 | 10,510 | 8,728 | 8342 |

Source: 2021Annual report GES Juaboso

Table 6: Basic Schools Enrolment and Staffing Levels – 2021

| School | Public |  |  | Private |  |  | Total |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Trained | Untrained | Total | Trained | Untrained | Total | Trained | Untrained | Total |
| Pre-School | 27 | 1 | 28 | 2 | 15 | 17 | 29 | 18 | 47 |
| Primary School | 235 | 15 | 253 | 5 | 128 | 135 | 240 | 143 | 383 |
| JHS | 122 | 2 | 124 | 2 | 48 | 51 | 144 | 50 | 194 |
| SHS |  |  |  |  |  |  |  |  |  |
| Total | 384 | 18 | 412 | 9 | 191 | 203 | 413 | 211 | 624 |
|  | Trained | Untrained | Total | Trained | Untrained | Total | Trained | Untrained | Total |

Source: Ghana education service,

#### 1.11.1.1 School Infrastructure

School facilities in Juaboso District are inadequate and deprived. At least 48% of all basic school classroom facilities need either reconstruction or rehabilitation. About 20% of the school infrastructure is community initiated which are in bad conditions.

Teacher accommodation is inadequate in most school, and as such many teachers have to commute to school from nearby towns. This has resulted in poor staffing situation in most of the remote schools because teachers refuse postings to such schools.

Chalkboards and furniture situation in most schools have improved through the interventions of other development partners.

The infrastructure situation at the only Public Senior Secondary School in the District is also appalling. Classrooms are not adequate; hostel facilities are lacking. It does not have good library and sanitary facilities.

### 1.11.2 Health Care

Just like any other rural community in Ghana, health care delivery in the Juaboso district is bedeviled with a lot of problems. Health care delivery in respect of incidence of diseases, availability of health professionals and infrastructure, status of the Health Insurance Scheme, access to health facilities, infant mortality rate maternal mortality etc. are discussed below:

### 1.11.3 Availability of health Professional

The district has only two Medical Doctors who work at the Juaboso District Hospital. The doctors service the entire district population (78,305- projected) which gives unreasonable doctor patient ratio of 1: 39,152 relative to the national doctor patient ratio of 1: 10,452. The paramedical staffs are also inadequate considering the size of the population and demand for health care in the district. The number of staff manning the health facilities is about two-thirds of their required levels. Many health personnel are not willing to accept postings to the district because of its deprived nature. The few that accept postings leave after serving two or three years.

### 1.11.4 Health facilities

The district has thirty-six (36) reporting facilities comprising one public Hospital, one public Health Centre, two mission Clinics, seven private maternity homes and twenty-five CHPS compounds. These facilities are within the four demarcated sub districts namely; Juaboso, Asempaneye, Jato, and Bonsu Nkwanta sub districts.

Table 7: Spatial distribution of health facilities by sub districts and types of facilities.

|  | SUB-DISTRICT |  | TYPE OF FACILTY |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Hospital |  | Health Centre | Clinics | Maternity homes | Functional CHPS | TOTAL |
| 1 | Juaboso | 1 |  | 0 | 1 | 1 | 5 | 8 |
| 2 | Asempaneye | 0 |  | 0 | 0 | 1 | 6 | 7 |
| 3 | Jato | 0 |  | 0 | 0 | 1 | 4 | 5 |
| 4 | Bonsu Nkwanta | 0 |  | 1 | 1 | 4 | 10 | 16 |
| TOTAL |  | 1 |  | 1 | 2 | 7 | 25 | 36 |

Source: DHD Annual Report 2020

1.11.5 Nutrition

The nutrition situation in the District is not bad but report from the District Health Directorate indicates that there is an upsurge of dietary related diseases like hypertension, diabetes, ete. This requires public education on healthy lifestyle such as eating more fruits and vegetables; drinking more water; consuming less sugar and salt; avoiding the use of drugs e.g Cigarette; and exercise the body regularly.

However, there are several strategies being rolled out to improve nutrition and health status of the people in the District. These include growth monitoring and promotion commonly known as weighing; infant and young Child feeding; control of micro-nutrient deficiencies such as (vitamin A supplementation among children of 6-59 months, anaemia among pregnant women and children below 5 years and iodine deficiency disorder); control of non-communicable diseases like diabetes and hypertension; nutrition assessment counselling and support; and monitoring the school feeding programme as well as other nutrition related programmes. The implication of nutrition on the health of the people which has direct influence on the productivity and production in the District is significant and needs to be embraced by stakeholders.

1.11.6. Water

Water continues to remain a basic need for human growth and development. Over the years, ensuring access to quality water has become a global agenda along the development front of many countries and districts. In Juaboso District, access to quality water for all remains a challenge. Currently about 36% of the facilities (i.e. Hand pumps) are functional, 12% are sub-optimally functional (one or more of its source are not functional) and 52% not functional.

The erratic rain fall pattern experience in recent past in the district also pose a threat to the water security in the district. All these facts would impose a long term effects on education, personal hygiene and agricultural productivity.

## 1.12 Social Protection

The Juaboso district has been implementing social protection interventions including formation of child protection clubs, implementation of Livelihood Empowerment against Poverty (LEAP), Ghana school feeding programme etc., most of these social interventions initiatives coverage remains every low due to limited funding and poor targeting of beneficiaries. As a rural district poverty is inevitable... In the Juaboso district People living in the urban areas can easily access infrastructure such as, schools, libraries, good roads, communication systems among others whilst those in the rural areas are deprived.

## 1.13 Structure of the Local Economy

Juaboso District is predominantly rural district with 85% of its population living in communities of less than 5,000 inhabitants. Like most rural communities the major economic of the district is an informal economy, with Agriculture employing more than half of the work force. According to the 2010 PHC about 76.2 percent are in skilled agricultural, forestry and fishing occupations, 8.5 percent are in service and sales occupations, 5.7 percent are in craft and its related trade occupations and the remaining 9.6 percent are in other occupations. In terms of sex segregation, male population has 79.5 percent in the skilled agricultural forestry and fishery occupations compared to 72.4 percent of the female counterparts. Relatively high proportions of females are in service and sales occupations (14.7%), craft and related trades occupations (6.7%) and managers (0.8%) compared with their male counterparts in those occupations (3.0%, 4.8% and 0.6%, respectively). In other occupations, the proportions of male are relatively higher than those of their female counterparts. Generally, higher proportions of employed males than females are in occupations that require special skills and training such as professionals, technicians and associate professionals and plant machine operators and assemblers.

### 1.13.1 Household Income and Expenditure

With agriculture sector been the main economy of the district, about 81% of earnings in the district come from agriculture with cocoa alone accounting for 78% of gross earnings. This is in sharp contrast to the average earning per household per month for non-cocoa farmers who form 26% of the population.  With an average of 4.3 persons per household, the per capita monthly income is lower than the minimum UN standard.

### 1.13.2 Agricultural Activities

#### 1.13.2.1 Crops Farming

The main economic activity in the district is Farming with people of all ages in the district been involved in it due to the high returns derived particularly from cocoa production.  Over 90% of the work force is engaged in this activity.  The major crops grown in the district are cash crops like cocoa, oil palm and coffee and food crops such as plantain, cocoyam cassava, maize and rice.  Fruits such as oranges, pear, coconut, pineapple and vegetable are also cultivated.

#### 1.13.2.2 Fish Farming

Less than one percent of the working population is engage in fish farming.  Some of the farmers construct fish ponds others also make use of stagnant streams for the purpose.

There are a number of wet lands in the district that facilitate fishing activities. The problem faced in the fish industry is lack of specialized breeding points for fingerings.

#### 1.13.2.3 Business

From the 2010 Population and Housing Census, the local economic of the district is largely the agriculture sub sector which employs about 76% of the total work force, followed by service and commerce 8.5%, 5.7% are in craft and its related trades and the remaining 9.6% are in other occupations. The situation of the local economy can be attributed to the rural nature of the district. About 46.6 percent of the employed population is self-employed without employees.

Notwithstanding, the are Other economic opportunities that exist to boast the local economy in the district this include Auto mechanics’, carpentry, hair dressing, dress making and tailoring, trading, bakery, kente waving etc. the auto mechanic, carpenters and other artisans are scattered in the community especially at the district Capital.

### 1.13.3 Job Creation

#### The major employment sectors in the district are agriculture 86%, commerce 5% and industry and service 9%. The district has no large-scale industrial establishment but they are two medium-scale lumbering companies (Yusam Ltd and SND Ltd) operating in the district.  The lumber extraction companies make a significant contribution in terms of creating employment opportunities for the growing youth in the district. There are also a number of small-scale industries dotted all over the district.  These include metal smelting, carpentry and joinery, oil extraction (palm oil and palm kernel), auto fitting, refrigeration, gari processing, cereal milling, bakery, shoemaking, wood processing, Akpeteshie distilling, tie & dye and batik-making, fuel sellers and gold winning.

Telecommunication facilities or services which were very limited in the past are now covering almost the entire district. Four cellular phone companies MTN, Tigo, Airtel and Vodafone provide services in the district.

The Business Advisory Centre (BAC) in the district also provides employable skill to the teaming youth in the district through the rural enterprise project. Since its inception, the project has succeeded in organizing a number of trainings which includes business orientation seminars, community-based skill training in soap making, mushroom production, cream/parazone production, improved shoe making and small business management in records keeping.

### 1.13.4 Market

The four (4) major markets namely Juaboso on Thursdays, Prosu on Tuesdays, Boinzan on Wednesday and Bonsu Nkwanta on Fridays is a avenue for employment within the district. These markets centers attract trader from Kumasi the regional capital of the Ashanti Region and other surrounding district in the region.

## 1.14 Transportation Networks

The District is bisected with about 241 km of roads. Out of which 78.5 km are primary roads (Roads that link the district to other major town within the District) and 65km linking the district to the rest of the country. The remaining is made up of feeder roads that link farming settlements.

Figure 5: JUABOSO DISTRICT- Road Network in the District

## 1.15 Telecommunication Coverage

### Telecommunication companies such as MTN, Vodafone, Aitel-Tigo operate in the district. Mobile network coverage is very low in the district. Most of the rural communities have serious challenges of accessing mobile network. Low network coverage poses serious challenges to security operations, business activities, adoption of modern farming methods among others.

### 1.15.1 Information and Communication Technology (ICT)

### There is low investment in ICT. Majority of the people do not have access to the internet. The schools in the district are the worse affected in terms of teaching and learning. The schools don’t have computer laboratories. This contributes greatly to poor performance in ICT in BECE exams.

### 1.15.2 Science, Technology and Innovation (STI)

### The application of science, technology and innovation in the production system and in businesses of the district is low and as result, majority of the people still resort to rudimentary methods of exploitation of the factors of production.

## 1.16 GOVERNANCE

The District Assembly sees good governance as one of the cornerstones of development in the district. The various administrative structures of enhancing governance and ensuring citizen participation in the development process in the Juaboso District Assembly includes the District Assembly, Decentralised Departments, Zonal Councils and Unit Committees and Traditional Authority. The District Assembly has a membership of 23. This include16 elected members and 7 Government appointees. The District has four (4) sub-structures, this include Boinzan area council, Proso Kofikrom area council, Benchema Nkatieso and Asempaneye-Breman area councils. All stakeholders are given opportunity to participate in decision making processes of the Assembly including the vulnerable and marginalized. However, women participation in decision making is very low as only 0ne (1) out of the 21 elected Assembly members is a woman.

### 1.16.1 Security

Peace and stability emanate from a well-co-ordinated and effective security apparatus in every society. The District is fortunate to have access to the Police Service, Immigration Service and BNI whose mandate are to enforce peace and order in a democratic dispensation. Armed robbery is not too rampant but the District occasionally records some cases.

### 1.16.2 Traditional Authority

The traditional rulers in the District play a pivotal role in the governance of the people. The District Assembly (DA) considers them as effective development partners and for that matter; they are always drawn to partake in any development oriented activity. There are dynamic, proactive, visionary and very co-operative traditional rulers in the district who are always ready to support any development agenda. This provides strong partnership among the Traditional Authorities, NGOs and DA including the Decentralised Departments in the development process of the district.

## 1.17 Key development problems/issues/gaps identified from the situation analysis

The following are Key development issues under CPESDP with implications for 2022-2025

Table 8: Summary of Key Issues Development Issues of CPESDP

| Development Dimension |  | Key Identified issues (as harmonised with inputs from the performance review, profiling and community needs and aspirations) |
| --- | --- | --- |
| Economic Development |  |  |
| Ensuring and Sustaining Macro-Economic Stability |  | - Low mobilisation of Internally Generated Funds (IGF) - Non-property valuation - Dwindling employment opportunities - Poorly developed tourist attractions - Limited social responsibility on the part of corporate entities |
| Enhancing competitiveness of Ghana’s Private Sector |  | - Low skills training and development - Low entrepreneurial skills - Non-formalisation of businesses - Lack of access to credit facilities MSMEs - Lack of data on the informal sector - Limited alternative livelihood programmes - Limited small scale industrial activities |
| Accelerated Agricultural Modernisation and Sustainable Natural Resource Management |  | - Lack of ready market for farm produce and price fluctuation - Bad road network - Low adoption of improved agricultural technology - Limited alternative livelihood programmes - Inadequate AEAs - Continuous depletion of forest Limited access to credit, e.g. money farm inputs in rural areas - High cost of agro-inputs e.g. chemicals, fertilizer etc - Lack of processing machines |
| Social Development |  |  |
| Health | - Inadequate means of transport - Inadequate funding support - Inadequate health facilities - Lack of regular capacity building training for staff - Lack of knowledge of the operations of GHS by communities when it comes to staff transfers - High HIV/AIDS infection - Stigmatization and discrimination against PLWHAS |  |
| Education | - Inadequate educational infrastructure - Inadequate school furniture - Inadequate training for teachers in the area of early childhood development & core subject - Inadequate guidance and counselling seminars - High teacher attrition rate - High absenteeism among pupils after covid-19 - Inadequate teaching and learning materials - Limited school feeding programme coverage |  |
| Population management and development | - High incidence of teenage pregnancy - High child marriage - Low birth and death registration coverage - High unemployment among youth |  |
| Child protection and vulnerability | - Child labour - Inadequate support to child development and child labour issues - Inadequate support to the aged and PWDs - High stigmatisation of PLWHAS. |  |
| Gender | - Gender disparities in access to economic opportunities - Low political participation and under representation in decision making of women |  |
| Environmental Infrastructure and Human Settlement | - Inadequate access to potable water - Poor road network - Poor environmental sanitation and hygiene practices - Inadequate hygiene education - Improper solid and liquid waste management - Inadequate sanitary goods - Inadequate access to electricity - Haphazard housing development (lack of development schemes) - Deplorable state of some existing infrastructure facilities - Land degradation & deforestation - Perennial bush fires - Lack of ICT facilities |  |
| Governance, Corruption and Public Accountability | - Lack of office space for some departments and agencies - Delays in the release of statutory funds - Inadequate logistics for personnel’s and security services - Many unapproved routes - Low coverage of mobile network - Low capacity of the Area Councils and Unit Committee Members\ - Inadequate logistics for the sub-structures - Inadequate logistics at the central administration - Low-capacity building of personnel - Low participation of women in decision making - Inadequate staff accommodation |  |
| Implementation, Coordination, Monitoring and Evaluation | - Inadequate funds to undertake regular M&E activities - Lack of dedicated means of transport for M&E activities - Low capacity of some M&E team members - Delay in completion of development projects - Lack of dedicated means of transport for M&E activities |  |
| Emergency Planning and Response (Including Covid-19 Recovery Plan) | - Limited awareness on natural and man-made disasters in the disasters - Climate change - Limited institutional capacity for prevention and management of disasters |  |
| Covid-19 | - Lack of isolation centre - Bad attitude of public towards compliance of covid-19 protocols - Low budget allocation for the prevention and treatment of covid-19 - Inadequate education of the general public on covid-19 - Low revenue generation |  |

# CHAPTER TWO

# PRIORITIZATION OF DEVELOPMENT ISSUES

# Introduction

On the basis of the summarised key development issues identified from the previous chapter, the DPCU undertook the following activities to determine prioritised development issues for 2022-2025. This chapter highlights the steps that were taken to determine the prioritized development issues of the Juaboso District for 2022-2025. The harmonized issues have been prioritized in accordance with the Medium-Term National Development Policy Framework (2022-2025) provided by the National Development Planning Commission (NDPC).

Thus, each of the needs and aspirations of the communities have been matched against the summarized key development issues to determine the level of relationship between the two and scored. The criteria for the harmonization are as follows;

## 2.0 Application of Potentials, Opportunities, Constraints and Challenges (POCC)

With this, the internal factors which will propel the solving of these problems are assessed as against the constraints which are the internal negative factors which will inhibit the interventions to address the issues. External factors as well were assessed to help mitigate the challenges which are external inhibiting factors.

Although, there are many development issues encountered in the District, the potentials and opportunities abound to minimize the constraints and challenges. This will pave way for the district to meet its developmental needs and achieve its vision to “reduced incidence of household poverty, reduced illiteracy levels, increased communal access to potable water, and reduced levels of diseases and involvement of the citizenry in all levels of decision making”.

## 2.1 Impact Analysis on Prioritized Issues from POCC

The prioritized issues from the POCC analysis were further assessed to identify their internal consistency through the following criteria;

- Significant multiplier effect on economic efficiency e.g attraction of investors, job creation, increases in incomes and growth.

- Significant linkage effect on meeting basic human needs and rights.

- Significant effects of sustainable spatial development of designated spaces or corridors.

- Severity and diversity of the problem and intended benefits (social, economic, environmental and political) of addressing it.

The issues were then ranked based on their total scores The adopted development issues with their corresponding scores and ranks are presented in:

# CHAPTER THREE

# DEVELOPMENT PROJECTIONS, ADOPTED GOALS AND STRATEGIES

# Introduction

In this chapter, the development issues were linked to four of the five goals of the National Medium Term Development Policy Framework (NMTDPF) 2018-2021 and prioritized. In this chapter, the development focus of the Juaboso District Assembly has been established and a clear district goal consistent with the MTNDPF 2018-2021 has also been stated. The chapter also includes development projections for 2022-2025. Relevant policy objectives and strategies have also been adopted from the NMTDPF 2025-2025 to achieve the objectives of the district and national goals.

## 3.0 Development Projections of the District for 2022-2025

This part looks at the current and future needs of the district for the period 2022-2025. The needs were derived from the POCC analysis and the population projections.

### 3.1 Population Projections

Population is the single most important factor for the distribution of development programmes among various groups of persons particularly for the distribution of social services. Population projections are crucial in development planning decisions.

Generally, assumptions under population projections affect investment decisions on schools, hospitals and roads as well as power, water and sanitation supplies. Clearly, the supply of these facilities are restricted to age group, both aggregate and desegregation (according to age, sex, occupation, etc.) of the population.

The projected population of the district serves as the basis for estimating service requirement of health, water, education etc. up to the end of the plan period 2021. They form the basis for the planning and programming phase of the development plan. The district population is projected by using the exponential method based on the absolute figures and age distribution figures for the district in 2010 Population and Housing Census.

The assumptions made about the projections are:

- The ratio of the district population will grow at a constant rate throughout the plan period.

- The district’s growth rate (of 2.5%) will remain almost the same or will not change much up to the year 2025.

- Child mortality rate records in the district will reduce further or not change during the plan period.

- Also, the life expectancy at birth for both male and female in Ghana of 61/64 years remains the same till 2025.

- Migration rate in the district will remain unchanged during the plan period.

The age-cohorts of the district will not change much during the period.

Table 9: Projected Total Population and Sex Composition of the District

| Table 8.1: AGE GROUP | 2010 | 2021 | 2022 | 2023 | 2024 | 2025 |
| --- | --- | --- | --- | --- | --- | --- |
| Total | 58,435 | 88,814 | 93,225 | 97,918 | 102,814 | 107,955 |
| Male | 29,742 | 45,722 | 47,560 | 49,938 | 52,435 | 55,057 |
| Female | 28,693 | 43,092 | 45,965 | 47,980 | 50,379 | 52,898 |

Source: DPCU, 2021

Table 10: Age Distribution and Projected Population in the District

| AGE GROUP | 2010 | 2021 | 2022 | 2023 | 2024 | 2025 |
| --- | --- | --- | --- | --- | --- | --- |
| 0-4 | 9116 | 9435 | 9638 | 9845 | 10057 | 10273 |
| 5-9 | 8154 | 8439 | 8621 | 8806 | 8996 | 9189 |
| 10-14 | 6912 | 7154 | 7308 | 7465 | 7625 | 7789 |
| 15-29 | 5851 | 6056 | 6186 | 6319 | 6455 | 6594 |
| 20-24 | 5569 | 5764 | 5888 | 6014 | 6144 | 6276 |
| 25 29 | 5429 | 5619 | 5740 | 5863 | 5989 | 6118 |
| 30 34 | 4132 | 4277 | 4369 | 4462 | 4558 | 4656 |
| 35 39 | 3550 | 3674 | 3753 | 3834 | 3916 | 4001 |
| 40 44 | 2565 | 2655 | 2712 | 2770 | 2830 | 2891 |
| 45 49 | 2099 | 2172 | 2219 | 2267 | 2316 | 2365 |
| 50 54 | 1702 | 17612 | 1799 | 1838 | 1878 | 1918 |
| 55 59 | 931 | 964 | 984 | 1005 | 1027 | 1049 |
| 60 64 | 754 | 780 | 797 | 814 | 832 | 850 |
| 65+ | 1671 | 1551 | 1585 | 1619 | 1654 | 1689 |
| TOTAL | 58435 | 60302 | 61598 | 62923 | 64275 | 65657 |

## 3.2 Development Projections

The development projection of the Juaboso District Assembly per the needs assessment serves as a guide to the formulation of the 4-year Medium Term Development Plan. It represents the overall scope within which the development of the district would take place. It is prepared base on the identified problems and potentials of the district, the development key focus areas and goals that are expected to transform the District to a desirable state at the end of the plan period (2022-2025).

## 3.3 Projection of Health Facilities Requirement

In order to determine the service requirements by 2025, the thresholds of the various services were identified as shown below:

The health projections for the district are based on the national standards. Below are the national standards for calculating health needs:

- Minimum population for hospital		 = 1:175,000

- Minimum population for health center	 = 1:5-19,000

- Minimum population for clinics 		 = 1:3-5,000

- Minimum population for CHPS Compound         = 3,000

Table 11: Projection of Health Facilities and Doctors Needed

| YEARS |  | 2021 | 2022 |  | 2023 |  | 2024 |  | 2025 |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total Population (Projected) |  | 76,673 | 78,595 |  | 80,582 |  | 82,569 |  | 84,614 |  |
| Maternity Home |  | 6 | 7 |  | 8 |  | 9 |  | 10 |  |
| CHPS |  | 36 | 38 |  | 40 |  | 42 |  | 44 |  |
| Clinic |  | 3 | 4 |  | 5 |  | 6 |  | 7 |  |
| Health Centre |  | 1 | 2 |  | 3 |  | 4 |  | 5 |  |
| Hospital |  | 1 | 1 |  | 1 |  | 1 |  | 1 |  |
| Projection of Doctors Needed |  |  |  |  |  |  |  |  |  |  |
| YEARS | 2021 |  |  | 2022 |  | 2023 |  | 2024 |  | 2025 |
| Total Population (Projected) | 76,673 |  |  | 78,595 |  | 80,582 |  | 82,569 |  | 84,614 |
| No. of Doctors | 3 |  |  | 4 |  | 5 |  | 6 |  | 7 |
| Additional No. Required | 5 |  |  | 8 |  | 12 |  | 15 |  | 17 |

Table 12: Population Projection of Water Facilities

| Table 7: Year | 2021 | 2022 | 2023 | 2024 | 2025 |
| --- | --- | --- | --- | --- | --- |
| Total Population | 76,673 | 78,595 | 80,582 | 82,569 | 84,614 |
| No. of water Facility Required | 267 | 358 | 503 | 765 | 1,214 |
| Number Present (Boreholes and Pipe Stands) | 112 | 120 | 130 | 140 | 170 |
| Additional Number | 155 | 246 | 319 | 350 | 390 |

## 3.4 Sanitation projections

In terms of sanitary facilities, majority of the communities are using public latrines which are not of standard and adequate.  However, due to the government policy to provide public latrine to commercial areas like markets, institutions and lorry parks, the DA will encourage the construction of household toilet facilities in an effort to improve sanitation in the communities. This will be done using Community Led Total Sanitation (CLTS) Tools

Table 13: Sanitation Projections

| AREA COUNCILS | Refuse Containers |  | Fee-Based Collection Containers |  |
| --- | --- | --- | --- | --- |
|  | Current No. | Needed No. | Current No. | Needed No. |
| BOINZAN | 7 | 0 | 120 | 40 |
| ASEMPANEYE/BREMAN | 0 | 3 | 50 | 50 |
| PROSO/KOFIKROM | 0 | 4 | 45 | 80 |
| BENCHIMA/NKATIESO | 0 | 2 | 20 | 30 |

# Projection of Education Facilities Requirement

Table 14: Basic School Classroom Infrastructure Projections – 2022-2025

| Category | Population of basic school cohort (2021) | Existing classrooms (2021) | GES classroom Requirement | Needed | Gap/to be provided |
| --- | --- | --- | --- | --- | --- |
| 2022 |  |  |  |  |  |
| KG | 5425 | 97 | 1:35 | 67 | 67 |
| PRIMARY | 11979 | 419 | 1:45 | 43 | 43 |
| JHS | 4914 | 149 | 1:35 | 11 | 11 |
| SHS | 1331 | 19 | 1:35 | 21 | 21 |
| 2023 |  |  |  |  |  |
| KG | 5587 | 97 | 1:35 | 71 | 71 |
| PRIMARY | 12338 | 419 | 1:45 | 55 | 55 |
| JHS | 5061 | 149 | 1:35 | 17 | 17 |
| SHS | 1370 | 149 | 1:35 | 23 | 23 |
| 2024 |  |  |  |  |  |
| KG | 5754 | 97 | 1:35 | 71 | 71 |
| PRIMARY | 12708 | 419 | 1:45 | 55 | 55 |
| JHS | 5212 | 419 | 1:35 | 17 | 17 |
| SHS | 1411 | 19 | 1:35 | 23 | 23 |
| 2025 |  |  |  |  |  |
| KG | 5926 | 97 | 1:35 | 75 | 75 |
| PRIMARY | 13089 | 419 | 1:45 | 61 | 61 |
| JHS | 5368 | 419 | 1:35 | 20 | 20 |
| SHS | 1453 | 19 | 1:35 | 25 | 25 |

Source: DPCU, (Planning Standards for GES)

Table 15: NUMBER OF TEACHERS TRAINED AND UNTRAINED

| # School | # Public |  |  | # Private |  |  | # Total |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | # Trained | # Untrained | # Total | # Trained | # Untrained | # Total | # Trained | # Untrained | # Total |
| # KG/PRE SCH | # 152 | # 57 | # 209 | # 2 | # 142 | # 144 | # 154 | # 199 | # 353 |
| # PRIMARY SCHOOL | # 390 | # 26 | # 416 | # 5 | # 218 | # 223 | # 395 | # 244 | # 639 |
| # JHS | # 211 | # 3 | # 214 | # 10 | # 86 | # 96 | # 221 | # 89 | # 310 |
| # SHS | # 79 | # 0 | # 79 | # 0 | # 0 | # 0 | # 79 | # 0 | # 79 |
| # TOTAL | # 832 | # 86 | # 918 | # 17 | # 446 | # 463 | # 849 | # 532 | # 1381 |

Table 16: ENROLMENT IN BASIC SCHOOLS

| # ENROLMENT IN BASIC SCHOOLS |  |  |  |  |
| --- | --- | --- | --- | --- |
| # S/N | # LEVEL | # PUBLIC | # PRIVATE | # TOTAL |
| # 1 | # KG | # 5425 | # 1947 | # 7372 |
| # 2 | # PRIMARY | # 11979 | # 3554 | # 15533 |
| # 3 | # JHS | # 4914 | # 986 | # 5900 |
| # 4 | # SHS | # 1331 | # 560 | # 1891 |

| # S/N | # LEVEL | # PUBLIC |  | # PRIVATE |  |
| --- | --- | --- | --- | --- | --- |
|  |  | # BOYS | # GIRLS | # BOYS | # GIRLS |
| # 1 | # KG | # 2692 | # 2733 | # 989 | # 958 |
| # 2 | # PRIMARY | # 6167 | # 5863 | # 1800 | # 1754 |
| # 3 | # JHS | # 2482 | # 2432 | # 492 | # 494 |
| # 4 | # SHS | # 698 | # 633 | # 277 | # 283 |
|  | # TOTAL | # 12039 | # 11661 | # 3558 | # 3489 |

Table 17: Revenue Projections for All Revenue Sources

| Revenue Sources | Year |  |  |  |
| --- | --- | --- | --- | --- |
|  | 2022 | 2023 | 2024 | 2025 |
| IGF | 699,929.51 | 710,970.00 | 730,010.00 | 763,970.00 |
| Compensation transfer | 2,214,455.00 | 2,354,513.00 | 2,449,200.00 | 2,593,500.00 |
| Goods & Services transfer (Decent. Dept) | 101,865.00 | 106,000.00 | 110,868.00 | 110,868.00 |
| DACF | 3,858,124.11 | 3,900,442.00 | 3,911,442.00 | 3,963,392.00 |
| DACF (RFG) | 963,487.39 | 1,000,000.00 | 1,000,000.00 | 1,000,000.00 |
| Other transfer (CIDA) | 107,454.00 | 107,454.00 | 107,454.00 | 107,454.00 |
| TOTAL | 7,945,315.01 | 8,179,279.00 | 8,308,974.00 | 8,539,184.00 |

Figure 6:Proposed Projects for 2022-2025 Medium Term Plan Period

Table 18: Expenditure Projections

| Table 8.8: Expenditure Items | 2022 | 2023 | 2024 | 2025 |
| --- | --- | --- | --- | --- |
| Compensation | 2,362,575.46 | 2,550,695.00 | 2,580,750.00 | 2,610,340.00 |
| Good & services | 2,054,340.25 | 2,010,660.00 | 2,020320.00 | 2,070,960.00 |
| Assets | 3,528,399.30 | 3,620,570.00 | 3,720,450.00 | 3,870,430.00 |
| TOTAL | 7,945,315.01 | 8,181,925.00 | 8,321,520.00 | 8,551,730.00 |

Table 19: District Goals, Prioritized Issues, Policy Objectives and Strategies for 2022-2025

| THEMATIC GOAL | FOCUS AREA | SUSTAINABLE PRIORITISED ISSUE | POLICY OBJECTIVE | STRATEGIES |
| --- | --- | --- | --- | --- |
| BUILD A PROSPEROUS SOCIETY | Strong and Resilient Economy | Limited available economic data and unwillingness of public to pay taxes | Ensure improved fiscal performance and sustainability | Enhance the production and dissemination of disaggregated data |
|  | Industrial Transformation | Lack of processing machines and industries | Enhance value addition and increased income | Support acquisition of agro-processing machines and facilitate PPP for production and processing of cassava, cocoa, maize, oil palm and rice products |
|  | Private Sector Development | Lack of capacity and limited access to credit by MSMEs | Support entrepreneurship and MSME development | Register and formalize MSMEs operations |
|  |  |  |  | Create an entrepreneurial culture, especially among women and youth |
|  |  |  |  | Develop modern markets and retail infrastructure in every district to enhance domestic trade |
| BUILD A PROSPEROUS SOCIETY |  | Lack of entrepreneurial skills for self-employment | Promote the creation of decent jobs | Build capacity of informal sector |
|  | Agriculture and Rural Development | Severe poverty and underdevelopment among rural communities | Pursue flagship industrial development initiatives | Implement PFJ, planting for food & jobs, rearing for food & jobs, One district, one factory initiatives |
|  |  | Poor marketing systems | Promote demand-driven approach to agricultural development | Facilitate capacity building in negotiations, standards, regulations and skills development in contracting for actors along the value chain |
|  |  | High cost of production inputs |  | Promote and expand organic farming to enable producers access the growing world demand for organic products |
|  | Agriculture and Rural Development | inadequate development of and investment in processing and value addition | Ensure Improved Public Investment | Resource and strengthen District Agriculture Advisory Services (DAAS) to provide advice on productivity enhancing technologies |
|  |  | Low application of technology especially among smallholder farmers leading to comparatively lower yields | Improve production efficiency and yield | Reinvigorate extension services |
|  | Tourism and Creative Arts Development | Lack of development of tourism infrastructure and Service | Diversify and expand tourism industry for economic development | Promote local tourism and develop available and potential sites |
| CREATE OPPORTUNITIES FOR ALL | Education and Training | Poor quality of education at all levels | Enhance inclusion and equitable access to, and participation in quality education at all levels | Expand infrastructure and facilities at all levels |
|  |  | Inadequate training for early childhood teachers and core subject teachers | Enhance quality of teaching and learning | Organize regular capacity and refresher training for some categories of teachers |
|  |  | High absenteeism among pupil after covid-19 |  | Organize regular sensitization in communities |
|  |  | Poor linkage between management processes and schools’ operations |  | Strengthen school management systems |
|  |  | Inadequate school furniture |  | Ensure adequate supply of teaching and learning materials |
|  | Health and Health Services | Gaps in physical access to quality health care | Ensure affordable, equitable, easily accessible and Universal Health Coverage (UHC) | Expand and equip health facilities and provide means of transport for out-reaches |
|  |  | Lack of regular training for health staff at all levels |  | Strengthen the sub-district health systems as the bed-rock of the national primary health care strategy |
|  |  | High incidence of malaria and home injury cases | Reduce morbidity and fatalities | Intensify implementation of malaria control and hygiene education programmes |
|  | Health and Health Services | High HIV/AIDS infection rate and stigmatization | Ensure the reduction of new HIV and AIDS/STIs infections and stigmatization especially among the vulnerable groups | Intensify HIV Counseling and Testing (HTC) and stigmatization programmes |
| CREATE OPPORTUNITIES FOR ALL |  | Lack of comprehensive knowledge of HIV and AIDS/STIs, especially among the vulnerable groups |  | Intensify behavioral change strategies especially for high-risk groups for HIV & AIDS |
|  | Population Management | High teenage pregnancies and early child marriages | Improve population management | Intensify public education on save sex and early child marriage |
|  |  | Low birth and death registration coverage |  | Strengthen birth and death unit embark on regular community visits and radio sensitization |
|  | Child and Family Welfare | Low awareness of child protection laws and policies | Ensure effective child protection and family welfare system | Increase awareness creation on child protection issues and enforce child protection laws |
|  |  | High incidence of child marriages |  | Under take public education and mainstream child protection interventions in the district planning and budget |
|  |  | Inadequate funding support for child development and child labour issues |  | Increase funding support for child development and child labour related issues |
|  | Gender Equality | Gender disparities in access to economic opportunities | Promote economic empowerment of women | Encourage women artisans and other tradesmen, including farmers to form associations for easy access to information and other forms of support. |
|  |  | Low political participation and under representation in decision making of women | Promote inclusiveness in participation and decision making | Mainstream gender activities in the district plan and budget |
|  | Social Protection | Inadequate and limited coverage of social protection programmes for vulnerable groups | Strengthen social protection, especially for children, women, persons with disability and the elderly | Strengthen and effectively implement existing social protection intervention programmes and expand their coverage to include all vulnerable groups |
| CREATE OPPORTUNITIES FOR ALL |  |  |  | Institute effective and accurate means of identifying and enrolling beneficiaries |
|  | Disability and Development | High unemployment rate amongst PWDs | Promote full participation of PWDs in social and economic development of the country | Create avenues for PWD to acquire skills, credit or capital |
|  | Employment and decent work | Lack of entrepreneurial skills for self-employment | Promote the creation of decent jobs | Build capacity of informal sector |
| SAFEGUARD THE NATURAL ENVIRONMENT AND ENSURE A RESILIENT BUILT ENVIRONMENT | Deforestation, Desertification and soil erosion | Illicit trade in forest and wildlife resources | Combat deforestation, desertification and Soil erosion | Promote alternative livelihoods, including eco-tourism in forest fringe communities. |
|  |  | Widespread pollution of surface water | Promote sustainable Water Resource Development and Management | Improve liquid and solid waste management |
|  | Water resources management | Increasing demand for household water supply | Improve access to safe and reliable water supply services for all | Provide mechanized borehole and small-town water systems |
|  |  | Inadequate maintenance of facilities |  | Improve water production and distribution systems |
|  | Protected Areas | Increasing loss of endangered species | Expand forest conservation areas | Map and assign conservation status through bye-laws to mangrove forests |
|  |  | Weak enforcement of regulations | Protect existing forest reserves | Strengthen involvement of local communities in the management of forests |
|  | Environmental sanitation | High prevalence of open defecation | Improve access to improved and reliable environmental sanitation services | Develop and implement strategies to end open defecation |
|  |  | Inadequate sanitary goods |  | Increase and equip front line staff for sanitation |
|  |  | Poor sanitation and waste management |  | Improve the management of existing waste disposal sites |
|  |  | Lack of slaughter house |  | Review, gazette and enforce MMDAs’ bye-laws on sanitation |
|  |  | Poor hygiene practices |  | Provide public education on best hygiene practices |
| SAFEGUARD THE NATURAL ENVIRONMENT AND ENSURE A RESILIENT BUILT ENVIRONMENT | Climate Variability and Change | Low economic capacity to adapt to climate change | Enhance climate change resilience | Promote climate smart indigenous agricultural knowledge |
|  |  | Loss of trees and vegetative cover | Reduce greenhouse gases | Promote tree planting and green landscaping in communities |
|  | Disaster Management | Lack of comprehensive disaster prevention, preparedness and response plan | Promote proactive planning for disaster prevention and mitigation | Prepare disaster prevention, preparedness and response plan and |
|  |  | Inadequate information on natural and man-made hazards and disaster risk reduction |  | Educate public and private institutions on natural and man-made hazards and disaster risk reduction |
|  | Transport Infrastructure | Poor road network | Improve efficiency and effectiveness of road transport infrastructure and services | Expand and maintain the road network |
|  | Information Communication Technology (ICT) | Inadequate ICT infrastructure | Expand the Digital landscape | Expand ICT infrastructure |
|  | Energy | Inadequate electricity coverage and inadequate street light | Ensure expansion of electricity and street light | Expand electricity network through rural electrification |
|  | Drainage and Flood Control | Recurrent incidence of flooding | Address recurrent devastating floods | Construct storm drains in towns to address the recurrent devastating floods |
|  |  | Poor waste disposal practices |  | Intensify public education on indiscriminate disposal of waste |
|  | Infrastructure Maintenance | Poor maintenance of infrastructure | Promote proper maintenance culture | Establish timely and effective maintenance plan for all public infrastructure |
|  | Human Settlements and Housing | Lack of development schemes and spatial plans | Promote sustainable, spatially integrated, balanced and orderly development of human settlements | Fully implement National Spatial Development Framework (NSDF) |
|  |  | Weak enforcement of planning and building regulations |  | Fully implement Land Use and Spatial Planning Act, 2016 (Act 925) |
|  |  | Inadequate human and institutional capacities for land use planning |  | Strengthen the human and institutional capacities for effective land use planning and management |
| SAFEGUARD THE NATURAL ENVIRONMENT AND ENSURE A RESILIENT BUILT ENVIRONMENT | Rural Development | Poor and inadequate rural infrastructure and services | Ensure even distribution of development and achieve quality of life in rural areas | Provide basic infrastructure such as potable water, sanitation, electricity, road networks, schools, health facilities, low-cost housing. |
|  |  | Unregulated exploitation of rural economic resources |  | Promote rural enterprise development, financial inclusion, service delivery, capacity building and local economic development |
| GOVERNMENT, CORRUPTION AND PUBLIC ACCOUNTABILITY | Local Government and Decentralization | Ineffective sub-district structures | Deepen Political and Administrative decentralization | Strengthen sub-district structures |
|  | Human Security and Public safety | Weak involvement and participation of citizenry in planning and budgeting | Improve popular participation at district and sub-structure levels | Promote effective stakeholder involvement in development planning process, local democracy and accountability |
|  |  |  |  | Strengthen People’s Assemblies concept to encourage citizens to participate in government |
|  |  | Inadequate infrastructure | Enhance Security service delivery | Provide security institution with modern infrastructure, including offices and residential accommodation, |
|  |  | Inadequate community and citizen involvement in public safety | Enhance public safety | Promote security awareness of the various communities through neighborhood watch schemes etc. |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) | Emergency management | Limited institutional capacity for prevention and management of disasters | Enhance capacity of institutions responsible for disaster management | Promote regular training of staff to educate and sensitize people on disaster related issues |
|  |  | Lack of reliable emergency funding system for disasters | Improve allocation of funds for disaster management | Increase budgetary allocations for disaster prevention and management |
|  |  |  |  | Provide needed logistics and personnel for the combat of disasters |
| IMPLEMENTATION, CO-ORDINATION, MONITORING AND EVALUATION | Increase percentage implementation of development Programmes | Inadequate funds to undertake regular M&E activities | Improve resource mobilization, plan implementation, monitoring and evaluation | Provide adequate funds for plan implementation, monitoring and evaluation |
|  |  | Lack of dedicated means of transport for M&E activities |  | Provide logistics and means of transport |
|  |  | Poor data and information management | Strengthen data collection and processing in the district | Provide adequate logistics for data collection, storage and record management |
|  |  | Delay in completion of development on schedule | Achieve value for money of projects | Ensure strict compliance to completion timelines and timely release of funds |
|  |  | Low capacity of some M&E team members | Strengthen capacity of M&E members to deliver on mandate | Organize regular capacity training and retooling |
| COVID-19 (CROSS-CUTTING ISSUES) | Prevention and Management Pandemics | Disregard for covid-19 protocols | Enhance public education on behavioral change | Improve community mobilization for effective education of the public on covid-19 |
|  |  | Lack of isolation center | Improve health management facilities | Improve infrastructure and support the management of covid-19 |

3.5 Sustainability Assessment of Programmes/Projects

The programs/projects in the MTDP were subjected to the Strategic Environmental Assessment (SEA). Strategic Environmental Assessment is a process by which environmental considerations are fully integrated into the preparation of plan, programs and projects.  SEA provides for a high level of protection of the environment and contributes to the integration of environmental considerations into the preparations and adoption of plans and programmes with a view of promoting sustainable development. Individual strategies were also subjected to the sustainable appraisal tests to identify their effects on natural resources, social and cultural conditions, economy and the institutions concerned.

### 3.5.1 The Compound Matrix

This is used to ascertain the effects of PPPs on the relevant Poverty- Environment criteria. It helps decision makers to refine the PPP to determine and or minimize any potential adverse effects on the environment. In the matrix, symbols are used to indicate the relationship between PPPs and the Environment-poverty criteria.

This record sheet assigns summarized scores obtained when the various projects were subjected to the environmental-poverty assessment criteria.

Table 20: Compound Matrix Record Sheet

| Table 8.10.1: Indicators | Summary | Score |
| --- | --- | --- |
| LIVELIHOOD |  |  |
| Skills training and access to land | Most projects in the MTDP impact positively on skills training and access to land. The projects that have adverse effect on the indicator will be refined to mitigate the impact. | + |
| Access to forestry resources | Some of the projects in the Plan are likely to have adverse effect on forestry resources. These projects need to be reformulated to reduce its potential impact on the indicator | - |
| Water availability | Projects in the plan are largely neutral to access to water. However, few of them impact positively access to or availability of water in the district. There is no project that negatively affects access to water. | 0 |
| Health |  |  |
| Sanitation | The various projects suggest that the plan has potential to improve the sanitation situation in the district | + |
| Water quality | The Plan is not likely to have any significant impact on water quality | - |
| Air quality | The Plan is not likely to have any significant impact on air quality | - |
| Vulnerability |  |  |
| Bush fires | The MTDP is not likely to impact either positively or negatively to the bush fires in the district | 0 |
| Flooding | The MTDP is likely to have potential to improve to the flooding situation in the district | + |
| Droughts | The MTDP is not likely to impact either positively or negatively to the drought in the district | 0 |
| Institutional |  |  |
| Participation | The Plan encourages popular participation | + |
| Human rights | The MTDP has potential to improve right in the district | + |

# CHAPTER FOUR

# COMPOSITE PROGRAMME OF ACTION

# INTRODUCTION

The development programmes for 2022-2025 were formulated based on the analysis of the key development problem identified and prioritized through consensus at different stakeholders meeting with community representatives, Assembly members and traditional authorities. The development issues were further subjected to POCC analysis in chapter two of this document.

The focus of the plan is to improve the wellbeing of the people of the district through infrastructure development and job creation

## 4.0 COMPOSITE PROGRAMME OF ACTION (POA)

The Broad Composite Programme of Action covers the 4-year planning period.  It consists of a prioritized set of programmes activities and their costs, which are intended to enhance the achievement of the objectives of the plan for the Medium-Term period under the NMTDPF (2022-2025)

The Programme of Action considered government policies, activities of NGO’s and action plans submitted by the various departments within the district assembly as shown in the matrix below

Table 21: Composite Programme of Action (POA) for Juaboso District (2022 – 2025)

| Table 8.10.2 Goal | Objectives | Programme (PBB) | Sub-programme (PBB) | Time frame (year) |  |  |  |  | Cost |  | Programme Status |  | Implementing Institution/Department |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 20 22 | 20 23 | 20 24 | 20 25 | GoG | IGF/ABFA | Others | New | Ongoing | Lead | Collaborating |
| Build resilient and prosperous local economy | Improve fiscal performance through sustained income generation | Management and Administration | Finance and Revenue Mobilization |  |  |  |  | 178,800.00 | 19,700.00 | 0.00 | New | - | DBA DFO | Central administration |
|  | Support Entrepreneurs-hip and MSMEs Development | Economic Development | Private sector development |  |  |  |  | 8,500.00 | 17.000.00 | 0.00 | New |  | BAC | GEA, MTI |
|  | Improve efficiency and competitiveness of MSMEs | Economic Development | Trade, Industrial Development |  |  |  |  | 97,600.00 | 0.00 | 0.00 | New |  | BAC | GEA, MTI |
|  | Improve market infrastructure | Economic Development | Trade, Industrial Development |  |  |  |  | 915,431.14 | 0.00 | 0.00 | New | - | JDA | MLGDRD |
|  | Improve production efficiency and yield | Economic Development | Agriculture and rural development |  |  |  |  | 489,000.00 | 8,000.00 | 234,500.00 |  | On-going | Dept of Agric | Central Admin, MoFA |
|  | Enhance the application of science, technology and innovation | Economic Development | Agriculture Development |  |  |  |  | 3,600.00 | 4,000.00 | 66,000.00 |  | On-going | Dept of Agric | Central Admin, MoFA |
| Create opportunities for all and through social development interventions | Enhance inclusive and equitable access to, and participation in education at all levels | Social development | Education and training |  |  |  |  | 4,393,944.95 |  |  | New | - | GES | Central Admi, MoE |
|  | Strengthen school management systems | Social development | Education and training |  |  |  |  | 1,038,000.00 | 32,000.00 |  | New |  | GES | Central Admi, MoE |
|  | Reduce disability morbidity, and mortality | Social development | Health Delivery |  |  |  |  | 28,000.00 |  |  | New |  | GHS | Central Admi, MoH |
|  | Ensure the reduction of new HIV and AIDS/STIs infections, especially among the vulnerable groups | Social development | Health Delivery |  |  |  |  | 78,000.00 |  |  | New |  | GHS | Central Admi, MoH, AIDS Commission |
|  | Ensure affordable, equitable, easily accessible and Universal Health Coverage (UHC) | Social development | Health Delivery |  |  |  |  | 2,318,000.00 |  |  | New |  | GHS | Central Admi, MoH |
|  | Enhance access to improved and sustainable environmental sanitation services | Social Development | Health Delivery |  |  |  |  | 207,900.00 |  |  | New |  | DEHU | Central Admi, CWSA, MESTI |
|  | Promote effective solid waste management at all levels | Social Development | Health Delivery |  |  |  |  | 1,412,283.40 |  |  | New |  | DEHU | Central Admi, CWSA, MWH, MLGDRD |
|  | Improve population management | Social development | Population management |  |  |  |  |  | 62,500.00 |  | New |  | GHS | GSS, Birth & Death Registry |
|  | Ensure effective child protection and family welfare system | Social development | Child protection and welfare |  |  |  |  | 14,842.00 | 5,800.00 |  | New |  | SW&CDD | Central Admi, MoGCSP, UNICEF |
|  | Promote equal opportunities for Persons with Disabilities in social and economic development | Social development | Disability-inclusive development |  |  |  |  | 22,068.00 |  |  | New |  | SW&CDD | Central Admi, MoGCSP, UNICEF |
|  | Attain gender equality and equity in political, social development systems | Social development | Gender equality |  |  |  |  | 15,500.00 |  |  | New |  | GDO | Central Admi, MoGCSP |
|  | Promote economic empowerment of women. | Economic Development | Trade, Industrial Development |  |  |  |  | 10,000.00 |  |  | New |  | BAC | GEA, MTI |
| Safeguard the natural environment and ensure a resilient built environment and emergency response activities | Protect existing forest reserves |  | Protected areas |  |  |  |  | 200,000.00 |  |  | New |  | FSD | Central Admin |
|  | Enhance climate change resilience |  | Climate variability and change |  |  |  |  | 164,500.00 | 80,000.00 |  | New |  | FSD | Central Admin |
|  | Improve access to safe, reliable and sustainable water supply services for all | Environment, Infrastructure and Human Settlements | Water resources management |  |  |  |  | 1,700,000.00 | 80,000.00 |  | New |  | DEHU | Central Admi, CWSA, MWH |
|  | Improve efficiency and effectiveness of road transport infrastructure and services | Environment, Infrastructure and human settlement | Transportation |  |  |  |  | 3,286,384.46 |  |  | New |  | JDA | MoR |
|  | Provide adequate, reliable and affordable energy | Environment, Infrastructure and Human Settlements | Energy |  |  |  |  | 837,000.00 | 35,000.00 | 1,800,000.00 | New |  | ECG | JDA, Energy Ministry |
|  | Promote a sustainable, spatially integrated, balanced and orderly development of human settlements | Environment, Infrastructure and Human Settlements | Human settlements and housing |  |  |  |  | 194,500.00 |  |  | New |  | PPD | Central administration, LUSPA, MLGDRD |
|  | Promote proactive planning for disaster prevention and mitigation | Environment, Infrastructure and Human Settlements | Disaster management |  |  |  |  | 66,000.00 | 40,000.00 |  | New |  | NADMO/GNFS | Central Admin, MWH |
|  | Promote proper maintenance culture | Environment, Infrastructure and Human Settlements | Infrastructure maintenance |  |  |  |  | 925,000.00 | 40,000.00 | 120,000.00 | New |  | DWD | Central Admin |
| Maintain a stable, united and safe society | Deepen political and administrative decentralization | Governance, corruption and public accountability | Democratic government |  |  |  |  | 440,000.00 |  |  | New |  | BEDA | MLGDRD, |
|  | Strengthen fiscal decentralization | Governance, corruption and public accountability | Democratic government |  |  |  |  | 44,000.00 |  |  | New |  | BEDA | MLGDRD, |
|  | Improve popular participation at regional and district levels | Governance, corruption and public accountability | Local governance & decentralization |  |  |  |  | 165,000.00 |  |  | New |  | BEDA | MLGDRD, |
|  | Enhance security service delivery | Governance, corruption and public accountability | Human security and public safety |  |  |  |  | 1,504,000.00 |  |  | New |  | GPS | BEDA, MLGDRD |
|  | Promote the fight against corruption and economic crimes | Governance, corruption and public accountability | Corruption and economic crimes |  |  |  |  | 78,000.00 |  |  | New |  | BEDA | CHRAG, CSOs, |
| Mainstream emergency planning and preparedness to respond to potential internal and external threats (including COVID-19) | Improve public education and funding for covid-19 related activities | Environmental and sanitation management | Hydrogeological threats and biological |  |  |  |  | 96,500.00 | 32,000.00 |  | New |  | GHS DEHU, NADMO | Central Admin, MoH, |
| Improve delivery of development outcomes at all levels | Strengthen planning and M&E processes at all levels | Governance, corruption and public accountability | Policy management |  |  |  |  | 360,000.00 |  |  | New |  | BEDA | MLGDRD, |
|  | Strengthen planning and M&E processes at all levels | Production and Utilization of Statistics | Production and Utilization of Statistics |  |  |  |  | 214,000.00 |  |  | New |  | BEDA | MLGDRD, GSS |

4.1 Indicative Financial Plan (2022-2025)

The well designed and coordinated poverty reduction programmes/strategies towards improving the living standards of the people are meaningless if the needed resources are not mobilised both locally and externally to execute them within the plan period of 2022-2025. The Indicative Financial strategy for the planned period is prepared to deal with the means for mobilising and utilising financial resources for the implementation of the MTDP. The Major expenditure areas of the District to the Medium-Term Development Plan relates to financing the Projects, Programme and activities under four major programme areas namely Social Services Delivery, Infrastructural Development, Environmental Management and Management and Administration for the period. The Assembly intends to finance the planned projects and programmes mainly from three major sources of funding which includes projected Central Government inflows made up of the DACF, DDF, GoG, GETFund etc, the Internally Generated Fund mainly funds mobilised by the Assembly from revenues accruing from activities in the District which include rates, rents, fines, licences, fees etc and Donor funds from Development Partners and the Private Sectors who operate within the District. Part of the “One Million Dollars per Constituency” though not administered under the MMDAs has been considered as other sources of funding which will help address the issues identified. This is resulting from the fact that almost the same issues came up during the needs assessment by the secretariat.

The Rural Enterprises Project (REP) with funds from the African Development Bank would provide funds for skills training programmes. Also, other funding agencies are the Ministry of Education, Ministry of Health, Ministry of Food and Agriculture, as well as the Ministry of Energy.

4.2.1 Strategies to Bridge Funding Gap

The Juaboso District Assembly intends to bridge the funding gap in the implementation of the 2022-2025 DMTDP through three main strategies:

- Engagements with the District Assembly Common Fund Secretariat Currently, the Ministry of Finance (MoF) issues yearly budget ceilings to MMDAs for budgeting purposes. The ceilings given are woefully inadequate to fund programmes and projects of the FNDA, therefore the Assembly intends to lobby the Administrator of DACF through proposals to support the Assembly with its special DACF which deals with critical development issues.

- Proposals to Development Partners for funding other projects that cannot executed with DACF OR DACF/RFG.

The Assembly also intends to identify partners in decentralization and governance and reach out to them through proposals for funding for programmes and projects.

The Assembly will continue to seek support from Embassies and their Development Partners (DPs) to fund capacity building activities and other technical and logistical support.

The Assembly will continue to pursue partnerships with Civil Societies such as CARE – Ghana,.World Vision, Solidaridad – Ghana and other Non-Governmental Organizations to offer support that will help close the budgetary gap.

3. Engagement with the Private Sector through Public-Private Partnerships to implement some projects through arrangements like Build Operate and Transfer among others.

4.2.2 Spatial and Structure Plan

Spatial and Structure Plan portrays spatial dimension of the Medium-Term Development Plans (MTDP) and other relevant national and regional-level policies, plans and programs. Currently, the Juaboso District Assembly does not have Spatial and Structure Plan that outlines the spatial profile of the District by showing the built-up and Natural Environment with respect to Location and Size in the national and regional context, Climate and Vegetation, topography, soil type, Settlements and their locations, tourism, health facilities, educational infrastructure, population projection, accessibility to health and educational facilities, hospitality industry (hotels and guest houses), water facilities and road networks. The Assembly therefore intends to hire the services of a consultant to carry out this major assignment to assist the district to capture this relevant data of the district.

Table 22: Programme Financing

| Table 8.10.3 DEVELOPMENT DIMENTION | PROGRAMME (PBB) | PROG. COST | ESPECTED REVENUE & SOURCE OF FUNDING |  |  |  | TOTAL | GAP | MECHANISM TO FILL GAB |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | GOG | IGF | DACF | DACF-RFG |  |  |  |
| ECONOMIC DEVELOPMENT | Economic Development | 3,032,500.00 | 1,731,152.48 | 85,000 | 797,850.12 |  | 2,614,002.60 | 418,497.4 | - Intensify and support revenue taskforce - Development of proposal to development partners |
| SOCIAL DEVELOPMENT | Social Service Delivery | 9,623,038..35 | 400,994.28 | 86,000 | 6,598,980.73 | 650,000 | 7,735,975.01 | 1,887,063.34 |  |
| EMERGENCY PLANNING AND RESPONSE (INCLUDING COVID-19 RECOVERY PLAN) |  | 125,800.00 |  |  | 100,000.00 |  | 100,000.00 | 25,800 |  |
| ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS | Environmental and Sanitation Management | 3,456,500.00 | 769,029.12 | 571,071.85 | 2,823,707.06 |  | 4,163,808.03 |  |  |
|  | Infrastructure Delivery and Management | 7,237,884.46 | 732,128.12 | 105,000.00 | 5,6683,071.56 | 1,256,858.30 | 7,777,057.98 |  |  |
| GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY | Management and Administration | 2,231,500.00 |  | 250,000 | 650,000 |  | 900,000 | 1,331,500 |  |
| IMPLEMENTATION, COORDINATION, MONITORING AND EVALUATION |  | 574,000.00 | 4,288,018 | 2,647,288.53 | 2,616,762.86 | 157,577.00 | 9,709,646.39 |  |  |
| TOTAL |  | 26,281,222.35 | 7,921,322.00 | 3,744,360.38 | 19,270,372.33 | 2,064,435.30 | 33,000,490.01 |  |  |

# CHAPTER FIVE

# ANNUAL ACTION PLAN

# Introduction

The programmes/projects/activities in the Composite Programme of Action are detailed in the Annual Action Plans (AAPs) to be implemented from 2022 to 2025. The AAPs are the actual implementable document which stipulates programme, sub-programme, broad activities, timeframe, cost, programme status and implementing institution/department.  The Plan implementation will involve the Departments and Units of the Assembly, Non-decentralized Agencies as well as CSOs/NGOs, Communities and the Private Sector players. Also, Traditional Authorities, Assembly members, youth groups and other concerned stakeholders will form part of the plan implementation.

## 5.1 Plan Implementation Arrangements

In order to ensure effective implementation of the District Medium Term Development plan, all institutional and administrative issues need to be addressed to enhance the participation of all relevant stakeholders.  Plan implementation arrangement particularly issues relating to capacity building and strategies has to be improved to ensure the smooth implementation of the proposed projects and programmes.

## 5.2 Institutional Arrangements

To guarantee effectiveness and efficiency of the implementation of the plan, the district assembly must ensure that departments/units established in the Local Governance Act 2016, Act 936 but nonexistent are established and provided office accommodation and those less resourced provided the requisite staff and logistics.

## 5.3 Administrative Arrangements

It is expected that the Juaboso District Assembly will effectively streamline and coordinate the activities of the departments/units and other institutions operating within the district assembly to ensure efficiency.

## 5.4 Community Participation

The community members made up of males and females, the disable, youth, religious and opinion leaders will be fully part of the plan implementation process. All these people will be very useful for community mobilization and education and must be encouraged to offer such services. This effective collaboration will ensure community support and guarantee the sustainability of all programmes and projects.

Table 23: Shows the Composite Annual Action Plans

| Table 8.10.4 Programme (PBB) | Sub-Programme (PBB) | Broad Activities | Location | Timeframe (2022) |  |  |  | Cost |  |  | Programme Status |  | Implementing Institution/Department |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF/ABFA | Others | New | Ongoing | Lead | Collaborating |
| DEVELOPMENT DIMENSION: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Strong and Resilient Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management administration | Finance and Revenue Mobilization | Revise and update data on revenue sources | Juaboso |  |  |  |  | 9,000.00 |  |  | New | - | Finanace Dept | MLGDRD |
| Management administration | Finance and Revenue Mobilization | Organize fresher training for revenue collectors | Juaboso |  |  |  |  | 8,000.00 |  | - | New | - | DBA, DFO | Central admin |
| Focus area: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, tourism and industrial development | Organize social media marketing training for women and men | District wide |  |  |  |  |  | 5,000.00 |  |  | On-going | BAC | JDA, GEA, MOTI |
| Economic Development | Trade, tourism and industrial development | Organize stakeholders forum on business counseling | Juaboso |  |  |  |  | 3,500.00 |  |  |  | On-going | BAC | JDA, GEA, MOTI |

| Economic Development | Trade, tourism and industrial development |  | Organize 2 training workshop on technology improvement in cosmetics and bead making | Bonsu Nkwanta |  |  |  |  | 9,000.00 |  |  |  |  |  | On-going |  | BAC | GEA/DA |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Economic Development | Trade, tourism and industrial development |  | Organize 1Training session on Credit Management | Juaboso |  |  |  |  | 3,200.00 |  |  |  |  |  | On-going |  | BAC | Trobenbos Ghana |
| Economic Development | Trade, tourism and industrial development |  | Completion of 1No. 24 market shed | Sayerano |  |  |  |  | 15,431.14 |  |  |  |  |  | On-going |  | JDA | BAC |
| Economic Development | Trade, tourism and industrial development |  | Formalize Business registration and certification | Districtwide |  |  |  |  | 4,000.00 |  |  |  |  |  | On-going |  | BAC | GEA/ Clients |
|  |  |  | Develop and waterfall site for tourism purpose | Boinzan |  |  |  |  | 20,000.00 |  |  |  |  |  | New |  | BAC | JDA |
| Focus area: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agricultural Development | Training of staff and farmers on improved agricultural technology, FBO formation, HIV/AIDS and malaria prevention, etc. |  | 20 Communities |  |  |  |  | 1,800.00 |  | 2,000.00 | 15,000.00 |  |  | On-going | Agric. dept |  | RADU, GHS, Researchers, MAG |
| Economic Development | Agricultural Development | Organization of community and district planning session |  | Juaboso |  |  |  |  |  |  |  | 4050.00 |  |  | On-going | Agric. dept |  | RADU, Research, NGOs, DA, Farmers |
| Economic Development | Agricultural Development | Establish 5 yield plots for the 5 major crops |  | 10 Communities |  |  |  |  | 2,000.00 |  |  | 1,000.00 |  |  | On-going | Agric. dept |  | SRID, RADU Farmers |
| Economic Development | Agricultural Development | Maintenance of official vehicle and motorbikes |  | Juaboso |  |  |  |  | 6,000.00 |  |  |  |  |  | On-going | Agric. dept |  | D.A |
| Economic Development | Agricultural Development | Maintenance of office complex and DDA residence |  | Juaboso |  |  |  |  |  |  | 2,000.00 |  |  | New |  | Agric. dept |  | D.A |
| Economic Development | Agricultural Development | Acquisition of equipment for SRID activities |  | Juaboso |  |  |  |  | 4,000.00 |  |  |  |  | New |  | Agric. dept |  | D.A |
| Economic Development | Agricultural Development | Organization of District Farmers Day |  | District wide |  |  |  |  |  |  |  | 50,000.00 |  |  | On-going | Agric. dept |  | D.A |

| Economic Development | Agricultural Development | Acquisition of Coconut for PERD programme |  | District wide |  |  |  |  |  | 50,000.00 |  |  |  |  |  | On-going | Agric. dept |  | D.A |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Economic Development | Agricultural Development | Carry out oil palm plantation project |  |  |  |  |  |  |  | 100,000.00 |  |  |  |  | On-going |  | D.A |  | Ghana Prod’tive safety Net 2 |  |  |
| Economic Development | Agricultural Development | Carry out coconut plantation project |  |  |  |  |  |  |  | 100,000.00 |  | 2,000.00 |  |  | On-ging |  | D.A |  | Gh. Prod’tive safety Net 2 |  |  |
| Economic Development | Agric Development | Conduct monitoring and supervision (home visits) |  | Juaboso |  |  |  |  |  | 17,200.00 |  |  |  |  | New |  | Agric. dept |  | D.A |  |  |
| Economic Development | Agric Development | Maintenance of official vehicle and motorbikes |  | Juaboso |  |  |  |  |  | 6,000.00 |  |  |  |  |  | On-going | Agric. dept |  | D.A |  |  |
| Economic Development | Agric Development | Conduct 7 trainings and workshops for staff and farmers |  | Juaboso |  |  |  |  |  | 17,000.00 |  |  | 40,000.00 |  | New |  | Agric. dept |  | D.A |  |  |
| Economic Development | Agric Development | Provide PPEs for staff |  | District wide |  |  |  |  |  |  |  | 60,000.00 |  |  |  | On-going | Agric. dept |  | D.A |  |  |
| Economic Development | Agric Development | Conduct demonstration and monitoring of PFJ activities |  | Juaboso |  |  |  |  |  | 40,000.00 |  |  |  |  | New |  | Agric. dept |  | D.A |  |  |
| Economic Development | Agric Development | Procure and supply rice thresher |  | District wide |  |  |  |  |  |  |  | 35,000.00 |  |  | New |  | Agric. dept |  | D.A |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  | 171,131.14 |  | 119,000 | 60,500.00 |  |  |  |  |  |  |  |  |
| Development Dimension: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Education and Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organise Science, Technology, Mathematics, and Innovative Education (STMIE) clinics | Juaboso |  |  |  |  |  |  | 3.000.00 | 2,000.00 |  |  |  |  | On-going |  | GES | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Support the District Education Oversight Committee to monitor teaching and learning in schools | Juaboso |  |  |  |  |  |  | 4,500.00 |  |  |  |  |  | On-going |  | GES | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organisation of Independence day celebration | Juaboso |  |  |  |  |  |  | 35,000.00 |  |  |  |  |  | On-going |  | GES | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organize reading festivals to create awareness and encourage children to read | Juaboso |  |  |  |  |  |  |  | 5,000.00 |  |  |  |  | On-going |  | GES | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Extension of school feeding programme | District wide |  |  |  |  |  |  | 12,000.00 |  |  |  |  |  | On-going |  | GES | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organise mock examination for JHS three students | District wide |  |  |  |  |  |  | 18,000.00 |  |  |  |  |  | On-going |  | GES | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Social Services Delivery Education and Youth Dev’t. | District wide |  |  |  |  |  |  | 150,000.00 |  |  |  |  |  | On-going |  | GES | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1 No. 3 Unit Classroom Block , 3 KVIP & 3 Urinal at | Danyame |  |  |  |  |  |  | 154,234.80 |  |  |  |  |  | On-going |  | GES | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Reactivation & Completion of 1No. 6 Unit Classroom Block and ancillary | Benchima |  |  |  |  |  |  | 51,758.96 |  |  |  |  |  | On-going |  | GES | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1No. 3Unit Classroom Block & Ancillary Facility | Komeamaa |  |  |  |  |  |  | 14,399.08 |  |  |  |  |  | On-going |  | GES | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1 No. 6 Unit Classroom block & Ancillary facility | Yawagyimkrom |  |  |  |  |  |  | 93,227.15 |  |  |  |  |  | On-going |  | GES | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Supply of 600 hexagonal table & chairs for KG, 500 dual desks for Pry. School and 500 mono desks for JHS | District-wide |  |  |  |  |  |  | 250,000.00 |  |  |  | New |  |  |  | GES | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1 No 6Unit classroom block | Mantukwa |  |  |  |  |  |  | 41,103.00 |  |  |  |  |  | On-going |  | GES | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1 No 6Unit classroom block | Eteso |  |  |  |  |  |  | 54,963.99 |  |  |  |  |  | On-going |  | GES | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of on1 No. six unit classroom block | Juaboso (Juaboso SHS) |  |  |  |  |  |  | 405,000.00 |  |  |  | New |  |  |  | GES | JDA |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Provision of 20 desktop computers | District wide |  |  |  |  |  |  | 65,000.00 | - |  | - | New |  | - |  | JDA | GIFEC |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Provide financial support to promote ICT education | District wide |  |  |  |  |  |  | 15,000.00 |  |  |  | New |  |  |  | JDA | GIFEC |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Undertake career guidance seminar in 2 Senior High Schools | District wide |  |  |  |  |  |  | 15,000 |  |  |  | New |  |  |  | GDO | SWCD |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Undertake stakeholder and consultative meeting on scaling up effective mechanisms to promote and build sustainable TVET among women | Juaboso |  |  |  |  |  |  | 10,000 |  |  |  | New |  |  |  | GDO | GES |  |  |
| Focus area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Development | Support the organisation of inter district sports festival | Juaboso |  |  |  |  |  |  | 12,000.00 |  |  |  | New |  |  |  | GES | JDA |  |  |
| Focus area: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Renovation of CHPS Compound and quarters |  | Agyemangdiem |  |  |  |  |  | 60,000.00 |  |  |  | New |  |  |  | District Health | DA |  |  |
| Social Services Delivery | Health Delivery | Construction of 2N0. CHPS Compounds |  | Selected communities |  |  |  |  |  | 450,000.00 |  |  |  | New |  |  |  | District Health | DA |  |  |
| Social Services Delivery | Health Delivery | Posting of Health personnel to sub Districts |  | District wide |  |  |  |  |  | 2,000.00 |  |  |  | New |  |  |  | District Health Dir | DA |  |  |
| Social Services Delivery | Health Delivery | Intensify public education on causes, prevention and control of Malaria |  | District wide |  |  |  |  |  | 3,500.00 |  |  |  | New |  |  |  | District Health Dir | DA |  |  |
| Focus area: HIV/AIDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | HIV/AIDS | Organize know your status campaigns in selected communities |  | District-wide |  |  |  |  |  | 6,000 |  |  |  | New |  |  |  | District Health Dir | DA |  |  |
| Social Services Delivery | HIV/AIDS | Ensure celebration of World HIV/AIDS day and Know your status Campaigns |  | Bonsu Nkwanta |  |  |  |  |  | 7,500 |  |  |  | New |  |  |  | District Health Dir | DA |  |  |
| Social Services Delivery | HIV/AIDS | Organize radio sensitization on the effect of stigmatization against PLWHA |  | District-wide |  |  |  |  |  | 5,500 |  |  |  |  |  | On-going |  | District Health Dir | DA |  |  |
| Social Services Delivery | Health Delivery | Provide support for organization of health education on communicable and non-communicable diseases on local FM station |  | Juaboso |  |  |  |  |  | 3,000.00 |  |  |  | New |  |  |  | District Health Dir | DA |  |  |
| Social Services Delivery | Health Delivery | Carry out 2 school talk on healthy nutrition |  | Selected Schools |  |  |  |  |  | 6,000 |  |  |  | New |  |  |  | GDO | District Health Dir. |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  | 1,872,686.98 | 7,000.00 |  |  |  |  |  |  |  |  |  |  |
| Focus area: Environmental and Sanitation Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Organised medical screening exercise |  | District wide |  |  |  |  |  | 6,000.00 |  |  |  |  |  | On-going |  | DEHU | DA |  |  |
| Social Services Delivery | Health Delivery | Facilitate the organisation of monthly national sanitation day |  | District wide |  |  |  |  |  | 60,000 |  |  |  |  |  | On-going |  | DEHU | DA |  |  |
| Social Services Delivery | Health Delivery | Quarterly pushing/leveling of final dumping site |  | District wide |  |  |  |  |  | 80,000.00 |  |  |  |  |  | On-going |  | DEHU | DA |  |  |
| Social Services Delivery | Health Delivery | Undertake premises inspection |  | District wide |  |  |  |  |  | 3,000.00 |  |  |  |  |  | On-going |  | DEHU | DA |  |  |
| Social Services Delivery | Health Delivery | Construction of 1No. slaughter house |  |  |  |  |  |  |  | 12,283.40 |  |  |  |  |  | On-going |  | DEHU | DA |  |  |
| Focus area: Population Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Population management | Sensitize people on reproductive health to increase family planning acceptor rate |  | District-wide |  |  |  |  |  |  | 5,000.00 |  |  | New |  |  |  | GHS | Birth & Death department |  |  |
| Social Services Delivery | Population management | Organize radio and community information center discussions on birth and death registration |  | District-wide |  |  |  |  |  |  | 6,000.00 |  |  |  |  | On-going |  | Birth & Death department | GHS, communities, traditional and religious leaders |  |  |
| Social Services Delivery | Population management | Registration of births and deaths in the district |  | District-wide |  |  |  |  |  |  | 4,500.00 |  |  | New |  |  |  | Birth & Death department | GHS, |  |  |
| Focus area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Child development and protection | Create 4 awareness campaigns for parents to desist from child neglect, discrimination, exposure to physical and moral threats |  | District-wide |  |  |  |  |  |  | 1,400.00 |  |  |  |  | On-going |  | SWCD Central Admin | CRI, Mondelez ILO |  |  |
| Social Services Delivery | Child development and protection | Promote public-private partnerships in the provision of alternative care services |  | 20 Communities |  |  |  |  |  | 2,200.00 |  |  |  |  |  | On-going |  | SWCD Central Admin | CRI, Mondelez ILO |  |  |
| Social Services Delivery | Child development and protection | Formation of four (4) new women groups and monitoring twelve (12) of the existing groups and to link them to Additional Livelihoods Training |  | District-wide |  |  |  |  |  | 1,550.00 |  |  |  |  |  | On-going |  | SWCD Central Admin | Planning Unit / Gender Desk Officer |  |  |
| Disability and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | Organise 4 Community durbars to assist to prepare their community action plan quarterly |  | Four (4) communities |  |  |  |  |  | 1,500.00 |  |  |  |  |  | On-going |  | SWCD Central Admin | NGOs |  |  |
| Social Services Delivery | Social Welfare and Community Development | Create 4awareness campaign on voluntary participation in community initiated projects |  | 20 Communities |  |  |  |  |  | 1,642.00 |  |  |  |  |  | On-going |  | SWCD Central Admin | NGOs |  |  |
| Social Services Delivery | Gender Empoermenrt | Organise radio talk show programmes to advocate for girl child education |  | 5 communities |  |  |  |  |  | 1,500.00 |  |  |  |  |  | On-going |  | SWCD Central Admin | NGOs |  |  |
| Social Services Delivery | Disability and Development | Facilitate the registration and renewal of 400 vulnerable groups such as PWDs, LEAP beneficiaries etc. onto NHIS |  | District wide |  |  |  |  |  | 1,500.00 |  |  |  |  |  | On-going |  | SWCD Central Admin | NGOs |  |  |
| Social service Delivery | Disability and Development | To support and to train 60% of registered PWDs in the District to engage in economic and business ventures |  | District wide |  |  |  |  |  | 1,000.00 |  |  |  |  |  | On-going |  | SWCD Central Admin | NGOs |  |  |
| Social Services Delivery | Gender Empoermenrt | To Establish four (4) Village Savings and Loans Associations (VSLA) |  | District wide |  |  |  |  |  | 1,000.00 |  |  |  |  |  | On-going |  | SWCD Central Admin | NGOs |  |  |
| Social Services Delivery | Gender Empowerment | Hold special dialogue on women with disability |  | Selected Communities |  |  |  |  |  | 6,000 |  |  |  |  |  | New |  | GDO | SWCD |  |  |
| Social Services Delivery | Social Welfare and Community Development | To organize training workshops for the NGOs working within the District to understand the need to be registered with the department |  | Juaboso |  |  |  |  |  | 2,000.00 |  |  |  |  |  | On-going |  | SWCD Central Admin | NGOs |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  | 181,175.54 | 16,900.00 |  |  |  |  |  |  |  |  |  |  |
| Development Dimension: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Protected Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Promote planting of other trees in cocoa farms |  | District wide |  |  |  |  |  | 30,000.00 |  |  |  | New |  |  | Forestry Commission |  |  | DA |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out tree planting exercise in schools and other institutions |  | District wide |  |  |  |  |  | 13,000.00 |  |  |  | New |  |  | Forestry Commission |  |  | DA |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out afforestation of depleted forest reserve |  | District wide |  |  |  |  |  | 50,000.00 |  |  |  | New |  |  | Forestry Commission |  |  | DA |  |
| Key Focus Area: Climate variability and change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Organised awareness creation workshop on climate change for Assembly Members, staff and other stakeholders |  | District wide |  |  |  |  |  | 13,000.00 |  |  |  | New |  |  | JDA |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Supply 8,000 coconut seedlings to 300 farmers and 20,000 oil palm seedlings to 80 farmers. |  | District wide |  |  |  |  |  | 50,000.00 |  |  |  | New |  |  | MoFA |  |  | JDA |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Train male and female farmers on climate-smart agribusiness |  | District wide |  |  |  |  |  | 10,000.00 |  |  |  | New |  |  | MoFA |  |  | JDA |  |
| FOCUS Area :Water Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Water resources management | Construct 13No. Mechanised boreholes |  | District wide |  |  |  |  |  | 260,000.00 |  |  |  | New |  |  | DWE |  |  | CWSA, DP |  |
| Environment, Infrastructure and Human Settlements | Water resources management | Maintain broken down boreholes |  | District wide |  |  |  |  |  | 150,000.00 |  |  |  | New |  |  | DWE |  |  | CWSA, DP |  |
| Environmental and Sanitation Management | Water resources management | Train WATSAN committees and for and new ones and train them |  | 20 Communities |  |  |  |  |  |  | 20,00.00 |  |  | New |  |  | DWST |  |  | CWSA, DP |  |
| Focus area: Transport Infrastructure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance and reshaping of 135 km feeder roads |  | District Wide |  |  |  |  |  | 345,000.00 |  |  |  | New |  |  | DWE |  |  | Central Admi |  |
| Infrastructure Delivery and Management | Infrastructure Development | Construction of 2No. culverts |  | Sayeraso Mafia |  |  |  |  |  | 180,000.00 |  |  |  | New |  | On-going | DWE |  |  | Central Admi |  |
| Infrastructure Delivery and Management | Infrastructure Development | Construction of 2No. culverts |  | Kotosaa |  |  |  |  |  | 22,023.76 |  |  |  | New |  | On-going | DWE |  |  | Central Admi |  |
| Infrastructure Delivery and Management | Infrastructure Development | Construction of 2No. culverts |  | Yaw Agyem |  |  |  |  |  | 87,358.00 |  |  |  |  |  | On-going | DWE |  |  | Central Admi |  |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance of Assembly vehicle |  | Juaboso |  |  |  |  |  | 34,000.00 |  |  |  | New |  |  | DWE |  |  | Central Admi |  |
| Infrastructure Delivery and Management | Infrastructure Development | Maintenance of Assembly grader |  | Juaboso |  |  |  |  |  | 80,000.00 |  |  |  | New |  |  | DWE |  |  | Central Admi |  |
| Focus area: Infrastructure and Infrastructure Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure delivery | Construction of durbar ground |  | Asempanye Bonsu Nkwanta |  |  |  |  |  | 160,000.00 |  |  |  | New |  |  | DWE |  |  | Central Admi |  |
| Management and administration | General administration | Maintenance of office laptops, printers and photo copiers |  | Juaboso |  |  |  |  |  | 25,000 | 10,000 |  | - | - |  | On-going | ICT officer |  |  | Central admi store keeper |  |
| Management and administration | General administration | Maintenance of official buildings and accommodation |  | Juaboso |  |  |  |  |  | 45,000 | 20,000 |  | - | New |  | - | JDA |  |  | MLGDRD |  |
| Focus area: Energy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Procure/ Maintain 200 Street light bulbs |  | District-wide |  |  |  |  |  | 55,000 | 5,000 |  |  | New |  |  | JDA, ECG |  |  | Energy Ministry |  |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Provide support for extension of electricity to the communities without lights |  | Selected communities |  |  |  |  |  | 10,000.00 |  |  |  | New |  |  | JDA, ECG |  |  | Energy Ministry |  |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Expansion of telecommunication network |  | District-wide |  |  |  |  |  | 100,000.00 |  |  |  | New |  |  | JDA, ECG |  |  | Energy Ministry |  |
| Focus area: Human Settlements and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Organize radio sensitization on building permit |  | Juaboso |  |  |  |  |  | 5,000.00 |  |  | New |  |  | On-going | Works/Planning |  |  | LUSPA |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Expansion of street naming and property addressing system |  | Juaboso |  |  |  |  |  | 30,000.00 |  |  | New |  |  | On-going | Works/Planning |  |  | Central Admi |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Enforce planning and building regulations |  | District-wide |  |  |  |  |  | 6,000.00 |  |  |  |  |  | On-going | Works/Planning |  |  | Central Admi |  |
| Focus area: Disaster Prevention and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Hold disaster management committee meeting |  | District-wide |  |  |  |  |  | 3,500.00 |  |  |  | New |  |  | NADMO |  |  | Central Admi |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Reformation of DVG’s |  | District-wide |  |  |  |  |  | 5,000.00 |  |  | 5,000 | New |  |  | NADMO |  |  | Central Admi |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Organize anti-bush fire campaign on radio and communities |  | District-wide |  |  |  |  |  | 8,000.00 |  |  |  | New |  |  | NADMO, GNFS |  |  | Central Admi |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Form and train disaster clubs |  | Schools in the district |  |  |  |  |  |  | 9,500.00 |  |  | New |  |  | NADMO, GNFS |  |  | Central Admi |  |
| TOTAL |  |  |  |  |  |  |  |  |  | 1,646,881.76 | 84,500.00 |  |  |  |  |  |  |  |  |  |  |
| Development Dimension: Governance, Corruption and Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Local Government and Decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Organize sub-committee, general assembly meeting, and management meetings |  | Juaboso |  |  |  |  |  | 60,000.00 |  |  |  | New |  |  | Central Admi |  |  |  | MLGDRD NALAG |
| Management and administration | General administration | Prepare and gazette Assembly by-laws and fee fixing resolution |  | Juaboso |  |  |  |  |  | 35,000.00 |  |  |  | New |  |  | Central Admi |  |  |  | MLGDRD NALAG |
| Management and administration | General administration | Procure and supply office logistics and equipment |  | Juaboso |  |  |  |  |  | 30,000.00 |  |  |  | New |  |  | Procurement officer |  |  |  | Central Admi, stores |
| Management and administration | General administration | Procure 5N0. Laptop computers |  | Juaboso |  |  |  |  |  | 20,000.00 |  |  |  | New |  |  | Procurement officer |  |  |  | Central Admi, stores |
| Management and administration | General administration | Prepare and submit monthly and quarterly progress reports |  | Juaboso |  |  |  |  |  | 10,000.00 |  |  |  |  |  | Ongoing | DPCU |  |  |  |  |
| Management and administration | General administration | Organised quarterly Audit Committee meetings |  | Juaboso |  |  |  |  |  | 23,000.00 |  |  |  |  |  | Ongoing | Audit committee |  |  |  |  |
| Management and administration | General administration | Financial management and revenue training mobilation for Area councils |  | Juaboso |  |  |  |  |  | 11,000.00 |  |  |  | New |  |  | Finance Dept |  |  |  |  |
| Focus area: Security and public safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Provide financial support for conflict and DISEC activities |  | District wide |  |  |  |  |  | 30,000.00 |  |  |  |  |  | Ongoing | JDA |  |  | Security Agencies |  |
| Management and administration | General administration | Sensitize the public on violent extremism, security consciousness through radio and community visits |  | Juaboso |  |  |  |  |  | 15,000.00 |  |  |  | New |  |  | NCCE, GPS |  |  | Central Admi |  |
| Management and administration | General administration | Construction of 2No. Police post |  | Dangermu Proso Kofikrom |  |  |  |  |  | 350,000.00 |  |  |  | New |  |  | GPS |  |  | Central Admi |  |
| Emergency Planning And Response (Include COVID-19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Emergency Planning and response | Health delivery | Organize social, behavior and communication change |  | District-wide |  |  |  |  |  | 7,000 | 3,000 |  |  | New |  |  | DHD NCCE |  |  | JDA |  |
| Emergency Planning and response | Health delivery | Carry out active surveillance of diseases of public health importance |  | District-wide |  |  |  |  |  | 9,000 | 2,000 |  |  | New |  |  | DHD |  |  | NADMO, JDA |  |
| Emergency Planning and response | Health delivery | Conduct outbreak investigation |  | District-wide |  |  |  |  |  | 6,000 | 3,000 |  |  | New |  |  | DHD |  |  | NADMO |  |
| Focus area: IMPLEMENTATION, CO-ORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Prepare 2023 Annual Action Plan |  | Juaboso |  |  |  |  |  | 10,000.00 |  |  |  | New |  |  | DPCU |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Prepare 2023 composite budget and procurement plan |  | Juaboso |  |  |  |  |  | 35,000.00 |  |  |  | New |  |  | DPCU |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Organize 4 Town Hall meetings |  | Juaboso |  |  |  |  |  | 40,000.00 |  |  |  | New |  |  | DPCU |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Ensure Monitoring of all development projects/programmes |  | Juaboso |  |  |  |  |  | 40,000.00 |  |  |  | New |  |  | DPCU |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Prepare and dissemination M&E reports |  | Juaboso |  |  |  |  |  | 13,000.00 |  |  |  | New |  |  | DPCU |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  | 744,000.00 | 8,000.00 |  |  |  |  |  |  |  |  |  |  |

DPCU 2021

Table 24: Composite Annual Action Plan 2023

| Programme (PBB) | Sub-Programme (PBB) |  | Broad Activities |  |  | Location | Timeframe (2023) |  |  |  |  | Cost |  |  | Programme Status |  |  | Implementing Institution/Department |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | Q1 |  | Q2 | Q3 | Q4 | GoG | IGF/ABFA | Others | New | Ongoing |  | Lead | Collaborating |  |  |  |
| DEVELOPMENT DIMENSION: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Strong and Resilient Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management administration | Finance and Revenue Mobilization |  | Revise and update data on revenue sources |  |  | Juaboso |  |  |  |  |  | 10,000.00 |  |  | New | - |  | Finanace Dept | MLGDRD |  |  |  |
| Management administration | Finance and Revenue Mobilization |  | Organize fresher training for revenue collectors |  |  | Juaboso |  |  |  |  |  | 12,000.00 |  | - | New | - |  | DBA, DFO | Central admi |  |  |  |
| Focus area: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize social media marketing training for women and men |  |  | District wide |  |  |  |  |  |  | 5,000.00 |  |  | On-going |  | BAC | JDA, GEA, MOTI |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organise stakeholders forum on business counselling |  |  | Juaboso |  |  |  |  |  | 3,500.00 |  |  |  | On-going |  | BAC | JDA, GEA, MOTI |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Construction of 2No Market sheds |  |  | Selected Communities |  |  |  |  |  | 300,000.00 |  |  | New |  |  | BAC | JDA |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize I Training session on Credit Management |  |  | Juaboso |  |  |  |  |  | 3,200.00 |  |  |  | On-going |  | BAC | Trobenbos Ghana |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Formalize Business registration and certification |  |  | Districtwide |  |  |  |  |  | 4,000.00 |  |  |  | On-going |  | BAC | GEA/ Clients |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize 2 training workshop on technology improvement in cosmetics and bead making |  |  | Selected communities |  |  |  |  |  | 11,000.00 |  |  |  | On-going |  | BAC | GEA/DA |  |  |  |
| Focus area: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agricultural Development | Training of staff and farmers on improved agricultural technology, FBO formation, HIV/AIDS and malaria prevention, etc. |  |  |  | 20 Communities |  |  |  |  |  | 1,800.00 | 2,000.00 | 15,000.00 |  | On-going |  | Agric. dept | RADU, GHS, Researchers, MAG |  |  |  |
| Economic Development | Agricultural Development | Organization of community and district planning session |  |  |  | Juaboso |  |  |  |  |  |  |  | 4050.00 |  | On-going |  | Agric. dept | RADU, Research, NGOs, DA, Farmers |  |  |  |
| Economic Development | Agricultural Development | Establish 5 yield plots for the 5 major crops |  |  |  | 10 Communities |  |  |  |  |  | 2,000.00 |  | 1,000.00 |  | On-going |  | Agric. dept | SRID, RADU Farmers |  |  |  |
| Economic Development | Agricultural Development | Maintenance of official vehicle and motorbikes |  |  |  | Juaboso |  |  |  |  |  | 6,000.00 |  |  |  | On-going |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Maintenance of office complex and DDA residence |  |  |  | Juaboso |  |  |  |  |  |  | 2,000.00 |  | New |  |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Acquisition of equipment for SRID activities |  |  |  | Juaboso |  |  |  |  |  | 4,000.00 |  |  | New |  |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Organization of District Farmers Day |  |  |  | District wide |  |  |  |  |  |  |  | 50,000.00 |  | On-going |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Undertake oil palm plantation project |  |  |  | District wide |  |  |  |  |  | 100,000.00 |  |  | New |  |  | D.A | Ghana Prod’tive safety Net 2 |  |  |  |
| Economic Development | Agricultural Development | Undertake coconut plantation project |  |  |  | District wide |  |  |  |  |  | 100,000.00 | 2,000.00 |  | New |  |  | D.A | Gh. Prod’tive safety Net 2 |  |  |  |
| Economic Development | Agricultural Development | Undertake capacity building training on climate change mitigation strategies for women in crop production |  |  |  | District wide |  |  |  |  |  | 10,000 |  | 5,000 | New |  |  | GDO | Agric. Dept |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  | 527,500.00 | 9,000.00 | 75,050.00 |  |  |  |  |  |  |  |  |
| Development Dimension: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Education and Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organise Science, Technology, Mathematics, and Innovative Education (STMIE) clinics |  |  | Juaboso |  |  |  |  |  |  | 3,000.00 | 2,000.00 |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Support the District Education Oversight Committee to monitor teaching and learning in schools |  |  | Juaboso |  |  |  |  |  |  | 4,500.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organisation of Independence day celebration |  |  | Juaboso |  |  |  |  |  |  | 35,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organise reading festivals to create awareness and encourage children to read |  |  | Juaboso |  |  |  |  |  |  |  | 5,000.00 |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Extension of school feeding programme |  |  | District wide |  |  |  |  |  |  | 12,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organise mock examination for JHS three students |  |  | District wide |  |  |  |  |  |  | 18,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Social Services Delivery Education and Youth Dev’t. |  |  | District wide |  |  |  |  |  |  | 150,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1 No. 3 Unit Classroom Block , 3 KVIP & 3 Urinal at |  |  | Danyame |  |  |  |  |  |  | 187,234.8 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Reactivation & Completion of 1No. 2 Unit K.G Block |  |  | Selected commuities |  |  |  |  |  |  | 172,000.00 |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1 No. 6 Unit Classroom block & Ancillary facility |  |  | Nsinsem |  |  |  |  |  |  | 393,227 |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Supply of 600 hexagonal table & chairs for KG, 500 dual desks for Pry. School and 500 mono desks for JHS |  |  | District-wide |  |  |  |  |  |  | 250,000.00 |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Provision of 20 desktop computers |  |  | District wide |  |  |  |  |  |  | 65,000.00 | - | - | New | - |  | JDA | GIFEC |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Provide financial support to promote ICT education |  |  |  |  |  |  |  |  |  | 15,000.00 |  |  | New |  |  | JDA | GIFEC |  |  |  |
| Focus area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Development | Support the organisation of inter district sports festival |  |  | Juaboso |  |  |  |  |  |  | 12,000.00 |  |  | New |  |  | GES | JDA |  |  |  |
| Focus area: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Construction of 2N0. CHPS Compounds |  |  |  | Komemaa Sayereno |  |  |  |  |  | 600,000.00 |  |  | New |  |  | District Health | DA |  |  |  |
| Social Services Delivery | Health Delivery | Posting of Health personnel to sub Districts |  |  |  | District wide |  |  |  |  |  | 2,000.00 |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | Health Delivery | Intensify public education on causes, prevention and control of Malaria |  |  |  | District wide |  |  |  |  |  | 3,500.00 |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | Health Delivery | Undertake demonstration activity of best cooking practices at weighing centers for breast feeding mothers. |  |  |  | Selected Centers |  |  |  |  |  | 15,000 |  |  | New |  |  | GDO | DHD |  |  |  |
| Focus area: HIV/AIDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | HIV/AIDS | Organize know your status campaigns in selected communities |  |  |  | District-wide |  |  |  |  |  | 6,000 |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | HIV/AIDS | Ensure celebration of World HIV/AIDS day and Know your status Campaigns |  |  |  | District-wide |  |  |  |  |  | 7,500 |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | HIV/AIDS | Organize radio sensitization on the effect of stigmatization against PLWHA |  |  |  | District-wide |  |  |  |  |  | 5,500 |  |  |  | Ongoing |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | Health Delivery | Provide support for organization of health education on communicable and non-communicable diseases on local FM station |  |  |  | District-wide |  |  |  |  |  | 3,000.00 |  |  | New |  |  | District Health Dir | DA |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  | 1,959,461.18 | 7,000.00 |  |  |  |  |  |  |  |  |  |
| Focus area: Environmental and Sanitation Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Organized medical screening exercise |  |  |  | District wide |  |  |  |  |  | 6,000.00 |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Facilitate the organization of monthly national sanitation day |  |  |  | District wide |  |  |  |  |  | 60,000 |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Quarterly pushing/leveling of final dumping site |  |  |  | District wide |  |  |  |  |  | 80,000.00 |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Undertake premises inspection |  |  |  | District wide |  |  |  |  |  | 3,000.00 |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Construction of 3 No. public toilet |  |  |  | District wide |  |  |  |  |  | 360,000.00 |  |  | New |  |  | DEHU | DA |  |  |  |
| Focus area: Population Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Population management | Sensitize people on reproductive health to increase family planning acceptor rate |  |  |  | District-wide |  |  |  |  |  |  | 5,000.00 |  | New |  |  | GHS | Birth & Death department |  |  |  |
| Social Services Delivery | Population management | Organize radio and community information center discussions on birth and death registration |  |  |  | District-wide |  |  |  |  |  |  | 6,000.00 |  |  | On-going |  | Birth & Death department | GHS, communities, traditional and religious leaders |  |  |  |
| Social Services Delivery | Population management | Registration of births and deaths in the district |  |  |  | District-wide |  |  |  |  |  |  | 4,500.00 |  | New |  |  | Birth & Death department | GHS, |  |  |  |
| Focus area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Child development and protection | Create 4 awareness campaigns for parents to desist from child neglect, discrimination, exposure to physical and moral threats |  |  |  | District-wide |  |  |  |  |  |  | 1,400.00 |  |  | Ongoing |  | SWCD Central Admin | CRI, Mondelez ILO |  |  |  |
| Social Services Delivery | Child development and protection | Promote public-private partnerships in the provision of alternative care services |  |  |  | 20 Communities |  |  |  |  |  | 2,200.00 |  |  |  | Ongoing |  | SWCD Central Admin | CRI, Mondelez ILO |  |  |  |
| Social Services Delivery | Child development and protection | Formation of four (4) new women groups and monitoring twelve (12) of the existing groups and to link them to Additional Livelihoods Training |  |  |  | District-wide |  |  |  |  |  | 1,550.00 |  |  |  | Ongoing |  | SWCD Central Admin | Planning Unit / Gender Desk Officer |  |  |  |
| Disability and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | Organise 4 Community durbars to assist to prepare their community action plan quarterly |  |  |  | Four (4) communities |  |  |  |  |  | 1,500.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | Create 4awareness campaign on voluntary participation in community initiated projects |  |  |  | 20 Communities |  |  |  |  |  | 1,642.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Gender Empoermenrt | Organise radio talk show programmes to advocate for girl child education |  |  |  | 5 communities |  |  |  |  |  | 1,500.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Disability and Development | Facilitate the registration and renewal of 400 vulnerable groups such as PWDs, LEAP beneficiaries etc. onto NHIS |  |  |  | District wide |  |  |  |  |  | 1,500.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social service Delivery | Disability and Development | To support and to train 60% of registered PWDs in the District to engage in economic and business ventures |  |  |  | District wide |  |  |  |  |  | 1,000.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Poverty and Inequality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Gender Empowerment | To Establish four (4) Village Savings and Loans Associations (VSLA) |  |  |  | District wide |  |  |  |  |  | 1,000.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Gender Empowerment | To facilitate 2 community dialogue and school outreaches on redefining gender roles to harness women participation in politics, science and technology |  |  |  | District wide |  |  |  |  |  | 1,000.00 |  |  |  | New |  | GDO | NGOs SWCD Central Admin GES |  |  |  |
| Social Services Delivery | Gender Empowerment | Carry out sensitization of climate change vulnerabilities in 5 communities and school |  |  |  | District wide |  |  |  |  |  | 1,000.00 |  |  |  | New |  | SWCD Central Admin | NGOs Agric. dept |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | To organize training workshops for the NGOs working within the District to understand the need to be registered with the department |  |  |  | Juaboso |  |  |  |  |  | 2,000.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  | 524,892.0 | 16,900.00 |  |  |  |  |  |  |  |  |  |
| Development Dimension: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Protected Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Promote planting of other trees in cocoa farms |  |  |  | District wide |  |  |  |  |  | 30,000.00 |  |  | New |  | Forestry Commission |  |  |  |  | DA |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out tree planting exercise in schools and other institutions |  |  |  | District wide |  |  |  |  |  | 13,000.00 |  |  | New |  | Forestry Commission |  |  |  |  | DA |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out afforestation of depleted forest reserve |  |  |  | District wide |  |  |  |  |  | 50,000.00 |  |  | New |  | Forestry Commission |  |  |  |  | DA |
| Focus Area: Water Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Water resources management | Construct 20No. new boreholes |  |  |  | District wide |  |  |  |  |  | 300,000.00 |  |  | New |  | DWE |  |  |  |  | CWSA, DP |
| Environment, Infrastructure and Human Settlements | Water resources management | Maintain broken down boreholes |  |  |  | District wide |  |  |  |  |  | 150,000.00 |  |  | New |  | DWE |  |  |  |  | CWSA, DP |
| Environmental and Sanitation Management | Water resources management | Train WATSAN committees and for and new ones and train them |  |  |  | 20 Communities |  |  |  |  |  |  | 20,00.00 |  | New |  | DWST |  |  |  |  | CWSA, DP |
| Key Focus Area: Climate variability and change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Organised awareness creation workshop on climate change for Assembly Members, staff and other stakeholders |  |  |  | District wide |  |  |  |  |  | 13,000.00 |  |  | New |  | JDA |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Supply 8,000 Oil Palm seedlings to 300 farmers and 20,000 oil palm seedlings to 80 farmers. |  |  |  | District wide |  |  |  |  |  | 18,000.00 | 20,000.00 |  | New |  | MoFA |  |  |  |  | JDA |
| Environmental and Sanitation Management | Natural Resource Conservation | Train male and female farmers on climate-smart agribusiness |  |  |  | District wide |  |  |  |  |  | 10,000.00 |  |  | New |  | MoFA |  |  |  |  | JDA |
| Focus area: Transport Infrastructure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance and reshaping of 135 km feeder roads |  |  |  | District Wide |  |  |  |  |  | 345,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Construction of 2No. culverts |  |  |  | Selected communities |  |  |  |  |  | 300,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance of Assembly vehicle |  |  |  | Juaboso |  |  |  |  |  | 36,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Maintenance of Assembly grader |  |  |  | Juaboso |  |  |  |  |  | 80,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Focus area: Infrastructure and Infrastructure Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure delivery | Construction of durbar ground |  |  |  | Selected communities |  |  |  |  |  | 160,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Management and administration | General administration | Maintenance of office laptops, printers and photo copiers |  |  |  | Juaboso |  |  |  |  |  | 25,000 | 10,000 | - | - | On-going | ICT officer |  |  |  |  | Central admi store keeper |
| Management and administration | General administration | Maintenance of official buildings and accommodation |  |  |  | Juaboso |  |  |  |  |  | 45,000 | 20,000 | - | New | - | JDA |  |  |  |  | MLGDRD |
| Focus area: Energy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Procure/ Maintain 600 Street light bulbs |  |  |  | District-wide |  |  |  |  |  | 130,000 | 10,000 |  | New |  | JDA, ECG |  |  |  |  | Energy Ministry |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Extend electricity to the communities without lights |  |  |  | Selected communities |  |  |  |  |  | 30,500 |  | 450,000 | New |  | JDA, ECG |  |  |  |  | Energy Ministry |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Expansion of telecommunication network |  |  |  | District-wide |  |  |  |  |  | 100,000.00 |  |  | New |  | JDA, ECG |  |  |  |  | Energy Ministry |
| Focus area: Human Settlements and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Organize radio sensitization on building permit |  |  |  | Juaboso |  |  |  |  |  | 5,000.00 |  |  |  | On-going | Works/Planning |  |  |  |  | LUSPA |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Expansion of street naming and property addressing system |  |  |  | Bonsu Nkwanta Boinzan |  |  |  |  |  | 40,000.00 |  |  |  | On-going | Works/Planning |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Enforce planning and building regulations |  |  |  | District-wide |  |  |  |  |  | 6,000.00 |  |  |  | On-going | Works/Planning |  |  |  |  | Central Admi |
| Focus area: Disaster Prevention and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Hold disaster management committee meeting |  |  |  | District-wide |  |  |  |  |  | 3,500 |  |  | New |  | NADMO |  |  |  |  | Central Admi |
| Environmental and Sanitation Management | Disaster Prevention and Management | Reformation of DVG’s |  |  |  | District-wide |  |  |  |  |  | 5,000 |  | 5,000 | New |  | NADMO |  |  |  |  | Central Admi |
| Environmental and Sanitation Management | Disaster Prevention and Management | Organize anti-bush fire campaign on radio and communities |  |  |  | District-wide |  |  |  |  |  | 8,000 |  |  | New |  | NADMO, GNFS |  |  |  |  | Central Admi |
| Environmental and Sanitation Management | Disaster Prevention and Management | Form and train disaster clubs |  |  |  | Schools in the district |  |  |  |  |  |  | 9,500.00 |  | New |  | NADMO, GNFS |  |  |  |  | Central Admi |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  | 1,823,000 | 89,500.00 | 455,000.00 |  |  |  |  |  |  |  |  |
| Development Dimension: Governance, Corruption and Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Local Government and Decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Organize sub-committee, general assembly meeting, and management meetings |  |  |  | Juaboso |  |  |  |  |  | 60,000.00 |  |  | New |  | Central Admi |  |  | MLGDRD NALAG |  |  |
| Management and administration | General administration | Prepare and gazette Assembly by-laws and fee fixing resolution |  |  |  | Juaboso |  |  |  |  |  | 35,000.00 |  |  | New |  | Central Admi |  |  | MLGDRD NALAG |  |  |
| Management and administration | General administration | Procure and supply office logistics and equipment |  |  |  | Juaboso |  |  |  |  |  | 30,000.00 |  |  | New |  | Procurement officer |  |  | Central Admi, stores |  |  |
| Management and administration | General administration | Procure 5N0. Laptop computers |  |  |  | Juaboso |  |  |  |  |  | 20,000.00 |  |  | New |  | Procurement officer |  |  | Central Admi, stores |  |  |
| Management and administration | General administration | Prepare and submit monthly and quarterly progress reports |  |  |  | Juaboso |  |  |  |  |  | 10,000.00 |  |  |  | Ongoing | DPCU |  |  |  |  |  |
| Management and administration | General administration | Organised quarterly Audit Committee meetings |  |  |  | Juaboso |  |  |  |  |  | 12,000.00 |  |  |  | Ongoing | Audit committee |  |  |  |  |  |
| Management and administration | General administration | Provide financial support for anti-corruption activities |  |  |  | Juaboso |  |  |  |  |  | 10,000.00 |  |  | New |  | NACAP Desk Officer |  |  | Central Admi, CHRAG, NCCE |  |  |
| Management and administration | General administration | Financial management and revenue training mobilation for Area councils |  |  |  | Juaboso |  |  |  |  |  | 11,000.00 |  |  | New |  | Finance Dept |  |  |  |  |  |
| Focus area: Security and public safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Provide financial support for conflict and DISEC activities |  |  |  | District wide |  |  |  |  |  | 11,000.00 |  |  |  | Ongoing | JDA |  |  |  | Security Agencies |  |
| Management and administration | General administration | Sensitize the public on violent extremism, security consciousness through radio and community visits |  |  |  | Juaboso |  |  |  |  |  | 15,000.00 |  |  | New |  | NCCE, GPS |  |  |  | Central Admi |  |
| Management and administration | General administration | Construction of 2No. Police check points |  |  |  | Selected Communities |  |  |  |  |  | 350,000.00 |  |  | New |  | GPS |  |  |  | Central Admi |  |
| Emergency Planning And Response (Include COVID-19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Emergency Planning and response | Health delivery | Organize social, behavior and communication change |  |  |  | District-wide |  |  |  |  |  | 7,500 | 3,000 |  | New |  | DHD NCCE |  |  |  | JDA |  |
| Emergency Planning and response | Health delivery | Carry out active surveillance of diseases of public health importance |  |  |  | District-wide |  |  |  |  |  | 10,000 | 2,000 |  | New |  | DHD |  |  |  | NADMO, JDA |  |
| Emergency Planning and response | Health delivery | Conduct outbreak investigation |  |  |  | District-wide |  |  |  |  |  | 7,000 | 3,000 |  | New |  | DHD |  |  |  | NADMO |  |
| Focus area: IMPLEMENTATION, CO-ORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination |  |  | Prepare 2024 Annual Action Plan |  | Juaboso |  |  |  |  |  | 10,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination |  |  | Prepare 2024 composite budget and procurement plan |  | Juaboso |  |  |  |  |  | 35,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination |  |  | Organize 4 Town Hall meetings |  | Juaboso |  |  |  |  |  | 40,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination |  |  | Ensure Monitoring of all development projects/programmes |  | Juaboso |  |  |  |  |  | 40,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination |  |  | Prepare and dissemination M&E reports |  | Juaboso |  |  |  |  |  | 13,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  | 726,500.00 | 8,000.00 |  |  |  |  |  |  |  |  |  |

DPCU

Table 25: Composite Annual Action Plan 2024

| Table 8.10.5: Programme (PBB) | Sub-Programme (PBB) |  | Broad Activities |  | Location | Timeframe (2023) |  |  |  |  |  |  | Cost |  |  | Programme Status |  |  | Implementing Institution/Department |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Q1 |  | Q2 | Q3 |  | Q4 |  | GoG | IGF/ABFA | Others | New | Ongoing |  | Lead | Collaborating |  |  |  |
| DEVELOPMENT DIMENSION: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Strong and Resilient Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management administration | Finance and Revenue Mobilization |  | Revise and update data on revenue sources |  | Juaboso |  |  |  |  |  |  |  | 12,000.00 |  |  | New | - |  | Finanace Dept | MLGDRD |  |  |  |
| Management administration | Finance and Revenue Mobilization |  | Organize fresher training for revenue collectors |  | Juaboso |  |  |  |  |  |  |  | 15,000.00 |  | - | New | - |  | DBA, DFO | Central admi |  |  |  |
| Focus area: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize social media marketing training for women and men |  | District wide |  |  |  |  |  |  |  |  | 7,000.00 |  |  | On-going |  | BAC | JDA, GEA, MOTI |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize stakeholders forum on business counselling |  | Juaboso |  |  |  |  |  |  |  | 4,500.00 |  |  |  | On-going |  | BAC | JDA, GEA, MOTI |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Construction of 2No Market sheds |  | Selected Communities |  |  |  |  |  |  |  | 300,000.00 |  |  | New |  |  | BAC | JDA |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize 1Training session on Credit Management |  | Juaboso |  |  |  |  |  |  |  | 4,200.00 |  |  |  | On-going |  | BAC | Trobenbos Ghana |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Formalize Business registration and certification |  | Districtwide |  |  |  |  |  |  |  | 5,000.00 |  |  |  | On-going |  | BAC | GEA/ Clients |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize 2 training workshop on technology improvement in cosmetics and bead making |  | Selected Communities |  |  |  |  |  |  |  | 11,000.00 |  |  |  | On-going |  | BAC | GEA/DA |  |  |  |
| Focus area: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agricultural Development | Training of staff and farmers on improved agricultural technology, FBO formation, HIV/AIDS and malaria prevention, etc. |  |  | 20 Communities |  |  |  |  |  |  |  |  |  | 17,000.00 |  | On-going |  | Agric. dept | RADU, GHS, Researchers, MAG |  |  |  |
| Economic Development | Agricultural Development | Organization of community and district planning session |  |  | Juaboso |  |  |  |  |  |  |  |  |  | 4050.00 |  | On-going |  | Agric. dept | RADU, Research, NGOs, DA, Farmers |  |  |  |
| Economic Development | Agricultural Development | Establish 5 yield plots for the 5 major crops |  |  | 10 Communities |  |  |  |  |  |  |  | 2,000.00 |  | 3,000.00 |  | On-going |  | Agric. dept | SRID, RADU Farmers |  |  |  |
| Economic Development | Agricultural Development | Maintenance of official vehicle and motorbikes |  |  | Juaboso |  |  |  |  |  |  |  | 6,000.00 |  |  |  | On-going |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Maintenance of office complex and DDA residence |  |  | Juaboso |  |  |  |  |  |  |  |  | 2,000.00 |  | New |  |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Acquisition of equipment for SRID activities |  |  | Juaboso |  |  |  |  |  |  |  | 4,000.00 |  |  | New |  |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Organization of District Farmers Day |  |  | District wide |  |  |  |  |  |  |  |  |  | 50,000.00 |  | On-going |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Acquisition of Coconut for PERD programme |  |  | District wide |  |  |  |  |  |  |  | 65,000.00 |  |  |  | On-going |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Supply of farmer inputs |  |  | District wide |  |  |  |  |  |  |  | 70,000,00 |  |  | New |  |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Carry out impact analysis studies of agroforestry interventions on gender |  |  | Selected Communities |  |  |  |  |  |  |  | 10, 000 |  | 5,000 | New |  |  | GDO | Agric dept |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  | 508,700.00 | 9,000.00 | 79,050.00 |  |  |  |  |  |  |  |  |
| Development Dimension: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Education and Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organise Science, Technology, Mathematics, and Innovative Education (STMIE) clinics |  | Juaboso |  |  |  |  |  |  |  |  | 4,000.00 | 3,000.00 |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Support the District Education Oversight Committee to monitor teaching and learning in schools |  | Juaboso |  |  |  |  |  |  |  |  | 4,500.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organisation of Independence day celebration |  | Juaboso |  |  |  |  |  |  |  |  | 40,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organise reading festivals to create awareness and encourage children to read |  | Juaboso |  |  |  |  |  |  |  |  |  | 5,000.00 |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Extension of school feeding programme |  | District wide |  |  |  |  |  |  |  |  | 15,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organise mock examination for JHS three students |  | District wide |  |  |  |  |  |  |  |  | 18,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Social Services Delivery Education and Youth Dev’t. |  | District wide |  |  |  |  |  |  |  |  | 150,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1 No. 6 Unit Classroom block & Ancillary facility |  | Selected communities |  |  |  |  |  |  |  |  | 700,227 |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Supply of 600 hexagonal table & chairs for KG, 500 dual desks for Pry. School and 500 mono desks for JHS |  | District-wide |  |  |  |  |  |  |  |  | 300,000.00 |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Provision of 20 desktop computers |  | District wide |  |  |  |  |  |  |  |  | 70,000.00 | - | - | New | - |  | JDA | GIFEC |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Provide financial support to promote ICT education |  |  |  |  |  |  |  |  |  |  | 15,000.00 |  |  | New |  |  | JDA | GIFEC |  |  |  |
| Focus area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Development | Support the organisation of inter district sports festival |  | Juaboso |  |  |  |  |  |  |  |  | 15,000.00 |  |  | New |  |  | GES | JDA |  |  |  |
| Focus area: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Construction of 2N0. CHPS Compounds |  |  | Selected communities |  |  |  |  |  |  |  | 600,000.00 |  |  | New |  |  | District Health | DA |  |  |  |
| Social Services Delivery | Health Delivery | Posting of Health personnel to sub Districts |  |  | District wide |  |  |  |  |  |  |  | 2,000.00 |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | Health Delivery | Intensify public education on causes, prevention and control of Malaria |  |  | District wide |  |  |  |  |  |  |  | 3,500.00 |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | Health Delivery | Carry out school talk on healthy nutrition |  |  | Selected schools |  |  |  |  |  |  |  | 6,000 |  |  | New |  |  | GDO | SWCD, Health Service |  |  |  |
| Focus area: HIV/AIDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | HIV/AIDS | Organize know your status campaigns in selected communities |  |  | District-wide |  |  |  |  |  |  | 6,000 |  |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | HIV/AIDS | Ensure celebration of World HIV/AIDS day and Know your status Campaigns |  |  | District-wide |  |  |  |  |  |  | 7,500 |  |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | HIV/AIDS | Organize radio sensitization on the effect of stigmatization against PLWHA |  |  | District-wide |  |  |  |  |  |  | 5,500 |  |  |  |  | Ongoing |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | Health Delivery | Provide support for organization of health education on communicable and non-communicable diseases on local FM station |  |  | District-wide |  |  |  |  |  |  | 3,000.00 |  |  |  | New |  |  | District Health Dir | DA |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  | 959,2271.00 |  | 8,000 |  |  |  |  |  |  |  |  |  |
| Focus area: Environmental and Sanitation Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Organized medical screening exercise |  |  | District wide |  |  |  |  |  |  |  | 6,000.00 |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Facilitate the organisation of monthly national sanitation day |  |  | District wide |  |  |  |  |  |  |  | 60,000 |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Quarterly pushing/leveling of final dumping site |  |  | District wide |  |  |  |  |  |  |  | 80,000.00 |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Undertake premises inspection |  |  | District wide |  |  |  |  |  |  |  | 3,000.00 |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Construction of 3 No. public toilet at market centres |  |  | Selected communities |  |  |  |  |  |  |  | 360,000.00 |  |  | New |  |  | DEHU | DA |  |  |  |
| Focus area: Population Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Population management | Sensitize people on reproductive health to increase family planning acceptor rate |  |  | District-wide |  |  |  |  |  |  |  |  | 5,000.00 |  | New |  |  | GHS | Birth & Death department |  |  |  |
| Social Services Delivery | Population management | Organize radio and community information center discussions on birth and death registration |  |  | District-wide |  |  |  |  |  |  |  |  | 6,000.00 |  |  | On-going |  | Birth & Death department | GHS, communities, traditional and religious leaders |  |  |  |
| Social Services Delivery | Population management | Registration of births and deaths in the district |  |  | District-wide |  |  |  |  |  |  |  |  | 4,500.00 |  | New |  |  | Birth & Death department | GHS, |  |  |  |
| Focus area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Child development and protection | Create 4 awareness campaigns for parents to desist from child neglect, discrimination, exposure to physical and moral threats |  |  | District-wide |  |  |  |  |  |  |  |  | 1,400.00 |  |  | Ongoing |  | SWCD Central Admin | CRI, Mondelz ILO |  |  |  |
| Social Services Delivery | Child development and protection | Promote public-private partnerships in the provision of alternative care services |  |  | 20 Communities |  |  |  |  |  |  |  | 2,200.00 |  |  |  | Ongoing |  | SWCD Central Admin | CRI, Mondelz ILO |  |  |  |
| Social Services Delivery | Child development and protection | Formation of four (4) new women groups and monitoring twelve (12) of the existing groups and to link them to Additional Livelihoods Training |  |  | District-wide |  |  |  |  |  |  |  | 1,550.00 |  |  |  | Ongoing |  | SWCD Central Admn | Planning Unit / Gender Desk Officer |  |  |  |
| Disability and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | Organise 4 Community durbars to assist to prepare their community action plan quarterly |  |  | Four (4) communities |  |  |  |  |  |  |  | 1,500.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | Create 4awareness campaign on voluntary participation in community initiated projects |  |  | 20 Communities |  |  |  |  |  |  |  | 1,642.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Gender Empowerment | Organise radio talk show programmes to advocate for girl child education |  |  | 5 communities |  |  |  |  |  |  |  | 1,500.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Disability and Development | Facilitate the registration and renewal of 400 vulnerable groups such as PWDs, LEAP beneficiaries etc. onto NHIS |  |  | District wide |  |  |  |  |  |  |  | 1,500.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social service Delivery | Disability and Development | To support and to train 60% of registered PWDs in the District to engage in economic and business ventures |  |  | District wide |  |  |  |  |  |  |  | 1,000.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Poverty and Inequality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Gender Empowerment | To Establish four (4) Village Savings and Loans Associations (VSLA) |  |  | District wide |  |  |  |  |  |  |  | 1,000.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Gender Empowerment | Enhance youth capabilities in building sustainable livelihoods |  |  | District wide |  |  |  |  |  |  |  | 6,000.00 |  |  |  | New |  | GDO | SWCD NGO’s BAC |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | To organize training workshops for the NGOs working within the District to understand the need to be registered with the department |  |  | Juaboso |  |  |  |  |  |  |  | 2,000.00 |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  | 528,892.00 | 16,900.00 |  |  |  |  |  |  |  |  |  |
| Development Dimension: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Protected Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Promote planting of other trees in cocoa farms |  |  | District wide |  |  |  |  |  |  |  | 30,000.00 |  |  | New |  | Forestry Commission |  |  |  |  | DA |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out tree planting exercise in schools and other institutions |  |  | District wide |  |  |  |  |  |  |  | 13,000.00 |  |  | New |  | Forestry Commission |  |  |  |  | DA |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out afforestation of depleted forest reserve |  |  | District wide |  |  |  |  |  |  |  | 50,000.00 |  |  | New |  | Forestry Commission |  |  |  |  | DA |
| Focus Area: Water Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Water resources management | Construct 20No. new boreholes |  |  | District wide |  |  |  |  |  |  |  | 260,000.00 |  |  | New |  | DWE |  |  |  |  | CWSA, DP |
| Environment, Infrastructure and Human Settlements | Water resources management | Maintain broken down boreholes |  |  | District wide |  |  |  |  |  |  |  | 150,000.00 |  |  | New |  | DWE |  |  |  |  | CWSA, DP |
| Environmental and Sanitation Management | Water resources management | Train WATSAN committees and for and new ones and train them |  |  | 20 Communities |  |  |  |  |  |  |  |  | 20,00.00 |  | New |  | DWST |  |  |  |  | CWSA, DP |
| Key Focus Area: Climate variability and change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Organized awareness creation workshop on climate change for Assembly Members, staff and other stakeholders |  |  | District wide |  |  |  |  |  |  |  | 13,000.00 |  |  | New |  | JDA |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Supply 8,000 Oil Palm seedlings to 300 farmers and 20,000 oil palm seedlings to 80 farmers. |  |  | District wide |  |  |  |  |  |  |  | 18,000.00 | 20,000.00 |  | New |  | MoFA |  |  |  |  | JDA |
| Environmental and Sanitation Management | Natural Resource Conservation | Train male and female farmers on climate-smart agribusiness |  |  | District wide |  |  |  |  |  |  |  | 10,000.00 |  |  | New |  | MoFA |  |  |  |  | JDA |
| Focus area: Transport Infrastructure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance and reshaping of 135 km feeder roads |  |  | District Wide |  |  |  |  |  |  |  | 345,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Construction of 2No. culverts |  |  | Etese Mafia |  |  |  |  |  |  |  | 290,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance of Assembly vehicle |  |  | Juaboso |  |  |  |  |  |  |  | 36,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Maintenance of Assembly grader |  |  | Juaboso |  |  |  |  |  |  |  | 80,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Focus area: Infrastructure and Infrastructure Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure delivery | Construction of durbar ground |  |  | Selected communities |  |  |  |  |  |  |  | 160,000.00 |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Management and administration | General administration | Maintenance of office laptops, printers and photo copiers |  |  | Juaboso |  |  |  |  |  |  |  | 25,000 | 10,000 | - | - | On-going | ICT officer |  |  |  |  | Central admi store keeper |
| Management and administration | General administration | Maintenance of official buildings and accommodation |  |  | Juaboso |  |  |  |  |  |  |  | 45,000 | 20,000 | - | New | - | JDA |  |  |  |  | MLGDRD |
| Focus area: Energy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Procure/ Maintain 500 Street light bulbs |  |  | District-wide |  |  |  |  |  |  |  | 120,000 | 10,000 |  | New |  | JDA, ECG |  |  |  |  | Energy Ministry |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Extend electricity to the communities without lights |  |  | Selected communities |  |  |  |  |  |  |  | 30,500 |  | 450,000 | New |  | JDA, ECG |  |  |  |  | Energy Ministry |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Expansion of telecommunication network |  |  | District-wide |  |  |  |  |  |  |  | 100,000.00 |  |  | New |  | JDA, ECG |  |  |  |  | Energy Ministry |
| Focus area: Human Settlements and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Organize radio sensitization on building permit |  |  | Juaboso |  |  |  |  |  |  |  | 5,000.00 |  |  |  | On-going | Works/Planning |  |  |  |  | LUSPA |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Expansion of street naming and property addressing system |  |  | Bonsu Nkwanta Bonzain |  |  |  |  |  |  |  | 40,000.00 |  |  |  | On-going | Works/Planning |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Enforce planning and building regulations |  |  | District-wide |  |  |  |  |  |  |  | 6,000.00 |  |  |  | On-going | Works/Planning |  |  |  |  | Central Admi |
| Focus area: Disaster Prevention and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Hold disaster management committee meeting |  |  | District-wide |  |  |  |  |  |  |  | 3,500 |  |  | New |  | NADMO |  |  |  |  | Central Admi |
| Environmental and Sanitation Management | Disaster Prevention and Management | Reformation of DVG’s |  |  | District-wide |  |  |  |  |  |  |  | 5,000 |  | 5,000 | New |  | NADMO |  |  |  |  | Central Admi |
| Environmental and Sanitation Management | Disaster Prevention and Management | Organize anti-bush fire campaign on radio and communities |  |  | District-wide |  |  |  |  |  |  |  | 8,000 |  |  | New |  | NADMO, GNFS |  |  |  |  | Central Admi |
| Environmental and Sanitation Management | Disaster Prevention and Management | Form and train disaster clubs |  |  | Schools in the district |  |  |  |  |  |  |  |  | 10,500.00 |  | New |  | NADMO, GNFS |  |  |  |  | Central Admi |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  | 1,843,000 | 90,500.00 | 455,000.00 |  |  |  |  |  |  |  |  |
| Development Dimension: Governance, Corruption and Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Local Government and Decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Organize sub-committee, general assembly meeting, and management meetings |  |  | Juaboso |  |  |  |  |  |  |  | 60,000.00 |  |  | New |  | Central Admi |  |  | MLGDRD NALAG |  |  |
| Management and administration | General administration | Prepare and gazette Assembly by-laws and fee fixing resolution |  |  | Juaboso |  |  |  |  |  |  |  | 35,000.00 |  |  | New |  | Central Admi |  |  | MLGDRD NALAG |  |  |
| Management and administration | General administration | Procure and supply office logistics and equipment |  |  | Juaboso |  |  |  |  |  |  |  | 30,000.00 |  |  | New |  | Procurement officer |  |  | Central Admi, stores |  |  |
| Management and administration | General administration | Procure 5N0. Laptop computers |  |  | Juaboso |  |  |  |  |  |  |  | 20,000.00 |  |  | New |  | Procurement officer |  |  | Central Admi, stores |  |  |
| Management and administration | General administration | Prepare and submit monthly and quarterly progress reports |  |  | Juaboso |  |  |  |  |  |  |  | 10,000.00 |  |  |  | Ongoing | DPCU |  |  |  |  |  |
| Management and administration | General administration | Organised quarterly Audit Committee meetings |  |  | Juaboso |  |  |  |  |  |  |  | 12,000.00 |  |  |  | Ongoing | Audit committee |  |  |  |  |  |
| Management and administration | General administration | Provide financial support for anti-corruption activities |  |  | Juaboso |  |  |  |  |  |  |  | 10,000.00 |  |  | New |  | NACAP Desk Officer |  |  | Central Admi, CHRAG, NCCE |  |  |
| Management and administration | General administration | Financial management and revenue training mobilation for Area councils |  |  | Juaboso |  |  |  |  |  |  |  | 11,000.00 |  |  | New |  | Finance Dept |  |  |  |  |  |
| Focus area: Security and public safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Provide financial support for conflict and DISEC activities |  |  | District wide |  |  |  |  |  |  |  | 11,000.00 |  |  |  | Ongoing | JDA |  |  |  | Security Agencies |  |
| Management and administration | General administration | Sensitize the public on violent extremism, security consciousness through radio and community visits |  |  | Juaboso |  |  |  |  |  |  |  | 15,000.00 |  |  | New |  | NCCE, GPS |  |  |  | Central Admi |  |
| Management and administration | General administration | Construction of 2No. Police check points |  |  | Selected Communities |  |  |  |  |  |  |  | 350,000.00 |  |  | New |  | GPS |  |  |  | Central Admi |  |
| Emergency Planning And Response (Include COVID-19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Emergency Planning and response | Health delivery | Organize social, behavior and communication change |  |  | District-wide |  |  |  |  |  |  |  | 7,500 | 3,000 |  | New |  | DHD NCCE |  |  |  | JDA |  |
| Emergency Planning and response | Health delivery | Carry out active surveillance of diseases of public health importance |  |  | District-wide |  |  |  |  |  |  |  | 10,000 | 2,000 |  | New |  | DHD |  |  |  | NADMO, JDA |  |
| Emergency Planning and response | Health delivery | Conduct outbreak investigation |  |  | District-wide |  |  |  |  |  |  |  | 7,000 | 3,000 |  | New |  | DHD |  |  |  | NADMO |  |
| Focus area: IMPLEMENTATION, CO-ORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Prepare 2025 Annual Action Plan |  |  | Juaboso |  |  |  |  |  |  |  | 10,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Prepare 2025 composite budget and procurement plan |  |  | Juaboso |  |  |  |  |  |  |  | 35,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Organize 4 Town Hall meetings |  |  | Juaboso |  |  |  |  |  |  |  | 40,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Ensure Monitoring of all development projects/programmes |  |  | Juaboso |  |  |  |  |  |  |  | 40,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Prepare and dissemination M&E reports |  |  | Juaboso |  |  |  |  |  |  |  | 13,000.00 |  |  | New |  | DPCU |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  |  |  | 726,500.00 | 8,000.00 |  |  |  |  |  |  |  |  |  |

Table 26: Composite Annual Action Plan 2025

| Table 8.10.6: Programme (PBB) | Sub-Programme (PBB) |  | Broad Activities |  | Location | Timeframe (2023) |  |  |  |  | Cost |  |  |  | Programme Status |  |  | Implementing Institution/Department |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Q1 |  | Q2 | Q3 | Q4 | GoG | IGF/ABFA |  | Others | New | Ongoing |  | Lead | Collaborating |  |  |  |
| DEVELOPMENT DIMENSION: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Strong and Resilient Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management administration | Finance and Revenue Mobilization |  | Revise and update data on revenue sources |  | Juaboso |  |  |  |  |  | 12,500.00 |  |  |  | New | - |  | Finanace Dept | MLGDRD |  |  |  |
| Management administration | Finance and Revenue Mobilization |  | Organize fresher training for revenue collectors |  | Juaboso |  |  |  |  |  | 20,000.00 |  |  | - | New | - |  | DBA, DFO | Central admi |  |  |  |
| Focus area: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize social media marketing training for women and men |  | District wide |  |  |  |  |  | 8,500.00 |  |  |  |  | On-going |  | BAC | JDA, GEA, MOTI |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize stakeholders forum on business counselling |  | Juaboso |  |  |  |  |  | 5,000.00 |  |  |  |  | On-going |  | BAC | JDA, GEA, MOTI |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Construction of 2No Market sheds |  | Selected Communities |  |  |  |  |  | 300,000.00 |  |  |  | New |  |  | BAC | JDA |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize 1Training session on Credit Management |  | Juaboso |  |  |  |  |  | 4,500.00 |  |  |  |  | On-going |  | BAC | Trobenbos Ghana |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Formalize Business registration and certification |  | Districtwide |  |  |  |  |  | 5,000.00 |  |  |  |  | On-going |  | BAC | GEA/ Clients |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize 2 training workshop on technology improvement in cosmetics and bead making |  | Selected Communities |  |  |  |  |  | 12,000.00 |  |  |  |  | On-going |  | BAC | GEA/DA |  |  |  |
| Focus area: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agricultural Development | Training of staff and farmers on improved agricultural technology, FBO formation, HIV/AIDS and malaria prevention, etc. |  |  | 20 Communities |  |  |  |  |  |  |  |  | 19,000.00 |  | On-going |  | Agric. dept | RADU, GHS, Researchers, MAG |  |  |  |
| Economic Development | Agricultural Development | Organization of community and district planning session |  |  | Juaboso |  |  |  |  |  |  |  |  | 4,350.00 |  | On-going |  | Agric. dept | RADU, Research, NGOs, DA, Farmers |  |  |  |
| Economic Development | Agricultural Development | Establish 5 yield plots for the 5 major crops |  |  | 10 Communities |  |  |  |  |  | 2,000.00 |  |  | 3,000.00 |  | On-going |  | Agric. dept | SRID, RADU Farmers |  |  |  |
| Economic Development | Agricultural Development | Maintenance of official vehicle and motorbikes |  |  | Juaboso |  |  |  |  |  | 7,000.00 |  |  |  |  | On-going |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Maintenance of office complex and DDA residence |  |  | Juaboso |  |  |  |  |  |  | 2,000.00 |  |  | New |  |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Acquisition of equipment for SRID activities |  |  | Juaboso |  |  |  |  |  | 4,000.00 |  |  |  | New |  |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Organization of District Farmers Day |  |  | District wide |  |  |  |  |  |  |  |  | 60,000.00 |  | On-going |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Acquisition of Coconut for PERD programme |  |  | District wide |  |  |  |  |  | 75,000.00 |  |  |  |  | On-going |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Supply of farmer inputs |  |  | District wide |  |  |  |  |  | 70,000,00 |  |  |  | New |  |  | Agric. dept | D.A |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  | 525,500.00 | 2,000.00 |  | 86,350.00 |  |  |  |  |  |  |  |  |
| Development Dimension: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Education and Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organize Science, Technology, Mathematics, and Innovative Education (STMIE) clinics |  | Juaboso |  |  |  |  |  |  | 5,000.00 | 4,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Support the District Education Oversight Committee to monitor teaching and learning in schools |  | Juaboso |  |  |  |  |  |  | 4,500.00 |  |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organization of Independence day celebration |  | Juaboso |  |  |  |  |  |  | 45,000.00 |  |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organize reading festivals to create awareness and encourage children to read |  | Juaboso |  |  |  |  |  |  |  | 6,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Extension of school feeding programme |  | District wide |  |  |  |  |  |  | 15,000.00 |  |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organize mock examination for JHS three students |  | District wide |  |  |  |  |  |  | 20,000.00 |  |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Social Services Delivery Education and Youth Dev’t. |  | District wide |  |  |  |  |  |  | 150,000.00 |  |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1 No. 6 Unit Classroom block & Ancillary facility |  | Selected communities |  |  |  |  |  |  | 700,227 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Supply of 600 hexagonal table & chairs for KG, 500 dual desks for Pry. School and 500 mono desks for JHS |  | District-wide |  |  |  |  |  |  | 400,000.00 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Provision of 20 desktop computers |  | District wide |  |  |  |  |  |  | 90,000.00 | - |  | - | New | - |  | JDA | GIFEC |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Provide financial support to promote ICT education |  |  |  |  |  |  |  |  | 18,000.00 |  |  |  | New |  |  | JDA | GIFEC |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Undertake stakeholder and consultative meeting on scaling up effective mechanisms to promote and build sustainable TVET among women |  | District wide |  |  |  |  |  |  | 6,000.00 |  |  |  | New |  |  | GDO | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Carry out sensitization of climate change vulnerabilities in selected communities and school |  | District wide |  |  |  |  |  |  | 6,000 |  |  |  | New |  |  | GDO | JDA |  |  |  |
| Focus area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Development | Support the organization of inter district sports festival |  | Juaboso |  |  |  |  |  |  | 20,000.00 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Development | Construction of football pitch |  | Juaboso Kotosah Antobia |  |  |  |  |  |  | 250,000.00 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Focus area: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Construction of 2N0. CHPS Compounds |  |  | Selected communities |  |  |  |  |  | 600,000.00 |  |  |  | New |  |  | District Health | DA |  |  |  |
| Social Services Delivery | Health Delivery | Posting of Health personnel to sub Districts |  |  | District wide |  |  |  |  |  | 2,000.00 |  |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | Health Delivery | Intensify public education on causes, prevention and control of Malaria |  |  | District wide |  |  |  |  |  | 4,500.00 |  |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Focus area: HIV/AIDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | HIV/AIDS | Organize know your status campaigns in selected communities |  |  | District-wide |  |  |  |  |  | 7,000 |  |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | HIV/AIDS | Ensure celebration of World HIV/AIDS day and Know your status Campaigns |  |  | District-wide |  |  |  |  |  | 7,500 |  |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | HIV/AIDS | Organize radio sensitization on the effect of stigmatization against PLWHA |  |  | District-wide |  |  |  |  |  | 6,500 |  |  |  |  | Ongoing |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | Health Delivery | Provide support for organization of health education on communicable and non-communicable diseases on local FM station |  |  | District-wide |  |  |  |  |  | 3,500.00 |  |  |  | New |  |  | District Health Dir | DA |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  | 2,360,727 | 10,000.00 |  |  |  |  |  |  |  |  |  |  |
| Focus area: Environmental and Sanitation Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Organized medical screening exercise |  |  | District wide |  |  |  |  |  | 8,000.00 |  |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Facilitate the organization of monthly national sanitation day |  |  | District wide |  |  |  |  |  | 60,500.00 |  |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Quarterly pushing/leveling of final dumping site |  |  | District wide |  |  |  |  |  | 80,000.00 |  |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Undertake premises inspection |  |  | District wide |  |  |  |  |  | 3,500.00 |  |  |  |  | Onging |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Construction of 3 No. public toilet at market centres |  |  | Selected communities |  |  |  |  |  | 360,000.00 |  |  |  | New |  |  | DEHU | DA |  |  |  |
| Focus area: Population Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Population management | Sensitize people on reproductive health to increase family planning acceptor rate |  |  | District-wide |  |  |  |  |  |  | 5,000.00 |  |  | New |  |  | GHS | Birth & Death department |  |  |  |
| Social Services Delivery | Population management | Organize radio and community information center discussions on birth and death registration |  |  | District-wide |  |  |  |  |  |  | 6,500.00 |  |  |  | On-going |  | Birth & Death department | GHS, communities, traditional and religious leaders |  |  |  |
| Social Services Delivery | Population management | Registration of births and deaths in the district |  |  | District-wide |  |  |  |  |  |  | 4,500.00 |  |  | New |  |  | Birth & Death department | GHS, |  |  |  |
| Focus area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Child development and protection | Create 4 awareness campaigns for parents to desist from child neglect, discrimination, exposure to physical and moral threats |  |  | District-wide |  |  |  |  |  |  | 1,600.00 |  |  |  | Ongoing |  | SWCD Central Admin | CRI, Mondelez ILO |  |  |  |
| Social Services Delivery | Child development and protection | Promote public-private partnerships in the provision of alternative care services |  |  | 20 Communities |  |  |  |  |  | 2,600.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | CRI, Mondelez ILO |  |  |  |
| Social Services Delivery | Child development and protection | Formation of four (4) new women groups and monitoring twelve (12) of the existing groups and to link them to Additional Livelihoods Training |  |  | District-wide |  |  |  |  |  | 1,550.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | Planning Unit / Gender Desk Officer |  |  |  |
| Disability and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | Create 4 awareness campaign on voluntary participation in community initiated projects |  |  | 20 Communities |  |  |  |  |  | 1,642.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Gender Empowerment | Organize radio talk show programmes to advocate for girl child education |  |  | 5 communities |  |  |  |  |  | 2, 000.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Disability and Development | Facilitate the registration and renewal of 400 vulnerable groups such as PWDs, LEAP beneficiaries etc. onto NHIS |  |  | District wide |  |  |  |  |  | 2, 000.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social service Delivery | Disability and Development | To support and to train 60% of registered PWDs in the District to engage in economic and business ventures |  |  | District wide |  |  |  |  |  | 1,500.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Poverty and Inequality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Gender Empowerment | To Establish four (4) Village Savings and Loans Associations (VSLA) |  |  | District wide |  |  |  |  |  | 1,500.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Gender Empowerment | To facilitate community dialogue and school outreaches on redefining gender roles to harness women participation in politics, science and technology |  |  | District wide |  |  |  |  |  | 1,500.00 |  |  |  | New |  |  | GDO | SWCD NGO’s GES |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | To organize training workshops for the NGOs working within the District to understand the need to be registered with the department |  |  | Juaboso |  |  |  |  |  | 2,000.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  | 528,292.00 | 22,600.00 |  |  |  |  |  |  |  |  |  |  |
| Development Dimension: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Protected Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Promote cocoa agroforestry activities |  |  | District wide |  |  |  |  |  | 35,000.00 |  |  |  | New |  | Forestry Commission |  |  |  |  | DA |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out tree planting exercise in schools and other institutions |  |  | District wide |  |  |  |  |  | 13,000.00 |  |  |  | New |  | Forestry Commission |  |  |  |  | DA |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out afforestation of depleted forest reserve |  |  | District wide |  |  |  |  |  | 50,000.00 |  |  |  | New |  | Forestry Commission |  |  |  |  | DA |
| Key Focus Area: Climate variability and change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Organized awareness creation workshop on climate change for Assembly Members, staff and other stakeholders |  |  | District wide |  |  |  |  |  | 13,500.00 |  |  |  | New |  | JDA |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Supply 8,000 Oil Palm seedlings to 300 farmers and 20,000 oil palm seedlings to 80 farmers. |  |  | District wide |  |  |  |  |  | 18,000.00 | 20,000.00 |  |  | New |  | MoFA |  |  |  |  | JDA |
| Environmental and Sanitation Management | Natural Resource Conservation | Train male and female farmers on climate-smart agribusiness |  |  | District wide |  |  |  |  |  | 10,000.00 |  |  |  | New |  | MoFA |  |  |  |  | JDA |
| Focus Area: Water Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Water resources management | Construct 20No. new boreholes |  |  | District wide |  |  |  |  |  | 260,000.00 |  |  |  | New |  | DWE |  |  |  |  | CWSA, DP |
| Environment, Infrastructure and Human Settlements | Water resources management | Maintain broken down boreholes |  |  | District wide |  |  |  |  |  | 170,000.00 |  |  |  | New |  | DWE |  |  |  |  | CWSA, DP |
| Environmental and Sanitation Management | Water resources management | Train WATSAN committees and form new ones and train them |  |  | 20 Communities |  |  |  |  |  |  | 20,00.00 |  |  | New |  | DWST |  |  |  |  | CWSA, DP |
| Focus area: Transport Infrastructure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance and reshaping of 135 km feeder roads |  |  | District Wide |  |  |  |  |  | 345,000.00 |  |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Construction of 2No. culverts |  |  | Selected communities |  |  |  |  |  | 290,000.00 |  |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance of Assembly vehicle |  |  | Juaboso |  |  |  |  |  | 36,000.00 |  |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Infrastructure Development | Maintenance of Assembly grader |  |  | Juaboso |  |  |  |  |  | 80,000.00 |  |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Focus area: Infrastructure and Infrastructure Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure delivery | Construction of durbar ground |  |  | Selected communities |  |  |  |  |  | 160,000.00 |  |  |  |  |  | DWE |  |  |  |  | Central Admi |
| Management and administration | General administration | Maintenance of office laptops, printers and photo copiers |  |  | Juaboso |  |  |  |  |  | 25,000 | 10,000 |  | - | - | On-going | ICT officer |  |  |  |  | Central admi store keeper |
| Management and administration | General administration | Maintenance of official buildings and accommodation |  |  | Juaboso |  |  |  |  |  | 50,000 | 20,000 |  | - | New | - | JDA |  |  |  |  | MLGDRD |
| Focus area: Energy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Procure/ Maintain 500 Street light bulbs |  |  | District-wide |  |  |  |  |  | 120,000 | 10,000 |  |  | New |  | JDA, ECG |  |  |  |  | Energy Ministry |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Extend electricity to the communities without lights |  |  | Selected communities |  |  |  |  |  | 30,500 |  |  | 450,000 | New |  | JDA, ECG |  |  |  |  | Energy Ministry |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Expansion of telecommunication network |  |  | District-wide |  |  |  |  |  | 100,000.00 |  |  |  | New |  | JDA, ECG |  |  |  |  | Energy Ministry |
| Focus area: Human Settlements and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Organize radio sensitization on building permit |  |  | Juaboso |  |  |  |  |  | 5, 500.00 |  |  |  |  | On-going | Works/Planning |  |  |  |  | LUSPA |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Expansion of street naming and property addressing system |  |  | Proso Kofikrom |  |  |  |  |  | 40,000.00 |  |  |  |  | On-going | Works/Planning |  |  |  |  | Central Admi |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Enforce planning and building regulations |  |  | District-wide |  |  |  |  |  | 6,000.00 |  |  |  |  | On-going | Works/Planning |  |  |  |  | Central Admi |
| Focus area: Disaster Prevention and Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Hold disaster management committee meeting |  |  | District-wide |  |  |  |  |  | 3,500 |  |  |  | New |  | NADMO |  |  |  |  | Central Admi |
| Environmental and Sanitation Management | Disaster Prevention and Management | Reformation of DVG’s |  |  | District-wide |  |  |  |  |  | 5,000 |  | 5,000 |  | New |  | NADMO |  |  |  |  | Central Admi |
| Environmental and Sanitation Management | Disaster Prevention and Management | Organize anti-bush fire campaign on radio and communities |  |  | District-wide |  |  |  |  |  | 8,000 |  |  |  | New |  | NADMO, GNFS |  |  |  |  | Central Admi |
| Environmental and Sanitation Management | Disaster Prevention and Management | Form and train disaster clubs |  |  | Schools in the district |  |  |  |  |  |  | 10,500.00 |  |  | New |  | NADMO, GNFS |  |  |  |  | Central Admi |
| TOTAL |  |  |  |  |  |  |  |  |  |  | 1,874,000.00 | 95,000.00 |  |  |  |  |  |  |  |  |  |  |
| Development Dimension: Governance, Corruption and Public Accountability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Local Government and Decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Organize sub-committee, general assembly meeting, and management meetings |  |  | Juaboso |  |  |  |  |  | 60,000.00 |  |  |  | New |  | Central Admi |  |  | MLGDRD NALAG |  |  |
| Management and administration | General administration | Prepare and gazette Assembly by-laws and fee fixing resolution |  |  | Juaboso |  |  |  |  |  | 35,000.00 |  |  |  | New |  | Central Admi |  |  | MLGDRD NALAG |  |  |
| Management and administration | General administration | Procure and supply office logistics and equipment |  |  | Juaboso |  |  |  |  |  | 30,000.00 |  |  |  | New |  | Procurement officer |  |  | Central Admi, stores |  |  |
| Management and administration | General administration | Procure 5N0. Laptop computers |  |  | Juaboso |  |  |  |  |  | 20,000.00 |  |  |  | New |  | Procurement officer |  |  | Central Admi, stores |  |  |
| Management and administration | General administration | Prepare and submit monthly and quarterly progress reports |  |  | Juaboso |  |  |  |  |  | 10,000.00 |  |  |  |  | Ongoing | DPCU |  |  |  |  |  |
| Management and administration | General administration | Organized quarterly Audit Committee meetings |  |  | Juaboso |  |  |  |  |  | 12,000.00 |  |  |  |  | Ongoing | Audit committee |  |  |  |  |  |
| Management and administration | General administration | Provide financial support for anti-corruption activities |  |  | Juaboso |  |  |  |  |  | 10,000.00 |  |  |  | New |  | NACAP Desk Officer |  |  | Central Admi, CHRAG, NCCE |  |  |
| Management and administration | General administration | Financial management and revenue training mobilization for Area councils |  |  | Juaboso |  |  |  |  |  | 11,000.00 |  |  |  | New |  | Finance Dept |  |  |  |  |  |
| Focus area: Security and public safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Provide financial support for conflict and DISEC activities |  |  | District wide |  |  |  |  |  | 11,000.00 |  |  |  |  | Ongoing | JDA |  |  |  | Security Agencies |  |
| Management and administration | General administration | Sensitize the public on violent extremism, security consciousness through radio and community visits |  |  | Juaboso |  |  |  |  |  | 15,000.00 |  |  |  | New |  | NCCE, GPS |  |  |  | Central Admi |  |
| Management and administration | General administration | Construction of 2No. Police check points |  |  | Selected Communities |  |  |  |  |  | 350,000.00 |  |  |  | New |  | GPS |  |  |  | Central Admi |  |
| Emergency Planning And Response (Include COVID-19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Emergency Planning and response | Health delivery | Organize social, behavior and communication change |  |  | District-wide |  |  |  |  |  | 7,500 | 3,000 |  |  | New |  | DHD NCCE |  |  |  | JDA |  |
| Emergency Planning and response | Health delivery | Carry out active surveillance of diseases of public health importance |  |  | District-wide |  |  |  |  |  | 11, 000 | 2,000 |  |  | New |  | DHD |  |  |  | NADMO, JDA |  |
| Emergency Planning and response | Health delivery | Conduct outbreak investigation |  |  | District-wide |  |  |  |  |  | 7,000 | 3,000 |  |  | New |  | DHD |  |  |  | NADMO |  |
| Focus area: IMPLEMENTATION, CO-ORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Prepare 2026 Annual Action Plan |  |  | Juaboso |  |  |  |  |  | 10,000.00 |  |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Prepare 2026 composite budget and procurement plan |  |  | Juaboso |  |  |  |  |  | 35,000.00 |  |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Organize 4 Town Hall meetings |  |  | Juaboso |  |  |  |  |  | 45,000.00 |  |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Ensure Monitoring of all development projects/programmes |  |  | Juaboso |  |  |  |  |  | 40,000.00 |  |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Prepare and disseminate M&E reports |  |  | Juaboso |  |  |  |  |  | 15,000.00 |  |  |  | New |  | DPCU |  |  |  |  |  |
| TOTAL |  |  |  |  |  |  |  |  |  |  | 824,500.00 | 98,500.00 |  | 455,000.00 |  |  |  |  |  |  |  |  |

SOURCE: DPCU 2021

# CHAPTER SIX

# IMPLEMENTATION, MONITORING AND EVALUATION

# Introduction

Implementation of the District Medium Term Development Plan (2022-2025) requires monitoring and evaluation of programs, projects and activities captured in the plan. This chapter indicates Monitoring and Evaluation Matrix, calendar, budget, data collection, collation and analysis in the Service. It also provides information on M&E report and findings, dissemination, participatory monitoring and evaluation processes among others.

## 6.1 Purpose of the Monitoring and Evaluation

Monitoring and evaluation can be continually improved through informed decision-making, leading to social and economic transformation to improve the standards of living in the district.   Recognizing the fact that, resources are limited and the demand for results-based M&E has grown rapidly in recent times. Emphases are now being placed on public sector transparency and accountability for effective services delivery. M&E in the country has therefore shifted from being implementation based (concerned with the implementation. of activities) to being results-based (assessing if real changes have occurred). The purpose of M &E includes:

• Identify achievements, constraints and failures so that improvements can be made to the MTDP and project designs to achieve better impact.

• Identify the appropriate interventions that will increase the responsiveness of targeted beneficiaries.

• Improve service delivery, influence allocation of resources in the districts, and demonstrate results as part of accountability and transparency to Ghanaians and other stakeholders.

• Demonstrate result to stakeholders as part of accountability and transparency.

• Provide information for effective coordination of district development at the regional level.

• Provide district authorities, the government, development partners, community project management teams and the public with better means for learning from experience.

•   Assess the MTDP developmental targets are being met.

## 6.2 Stakeholder Analysis

Stakeholder analysis is an integral part of the planning process where various stakeholders were identified in the District. The stakeholders are all the organizations and groups of people involve in issues and strategies connected to development. This is relevant in the sense that, the identification and participation of these stakeholders will lead to sustained capacity building, dissemination and demand for Monitoring and Evaluation results. In doing this, all the stakeholders were identified and analyzed. The analysis took into consideration their background information and their various roles, needs and responsibilities.

Table 27: Analysis of Stakeholders

| Table 26 No. | Stakeholders | classification | Roles and Responsibilities | Involvement |
| --- | --- | --- | --- | --- |
| 1. | MLGDRD / NDPC other Extra-Ministerial Institutions (e.g. GAC) | Primary | Provision of guidelines for planning, Monitoring and Evaluation and Budgeting Mediates on the DAs behalf with Donors Monitors and coordinates Das Programmes Support capacity building programmes Formulates policies | M & E plan Preparation Monitoring & Evaluation of Das M & E results dissemination |
| 2 | Office of the Administrator of DACF | Primary | Receives and disburses at least 5% of the Consolidated fund to Sub-national structures Monitors DAs Programmes | Mid-term M&E Organise Development evaluation |
| 3 | Regional Coordinating Council (R.C.C.) | Primary | Policy Planning Development coordination among districts in the Region Harmonization of DMTDP Supervision of administration of the DAs Monitoring and Evaluation of projects | Field visit, Progress reports, Workshops, Seminars |
| 4 | District Administration | Primary | Policy formulation Development Planning and budgeting Make laws Direct implementation Provision of key personnel for monitoring Coordinates the activities of Decentralized Departments Revenue mobilization | M& E plan Preparation M &E Seminars & meetings Supervision and inspection of projects /programmes M & E results reporting and dissemination |
| 5 | Area Council Members | Primary | Champion the needs of electorates (Area Councils) Coordinates unit committees in their Zones Revenue mobilization Initiate and monitor projects | Data Collection Dissemination of information Monitoring and evaluation of projects and programmes |
| 6 | Unit Committee /Local Communities | Primary | Champion the needs of electorates/ units (communities) Revenue mobilization Initiate and monitor projects Collect data | Data Collection Dissemination of information Monitoring and evaluation of projects and programmes |
| 7 | GES and private providers | Primary | Provision of quality education Monitoring, Evaluation and Supervision of schools Schools children as key disseminators of information Collection, collation and analysis of data | Data Collection Dissemination of information Reporting |
| 8 | Other Departments | Primary | Implementing government policy at the local level Provision of social, economic, security, legal and other services Provision of adult education | Data Collection Dissemination of information Reporting |
| 9 | District Health Administration and Service Providers | Primary | Providers of curative and public health services Monitor and supervise services provided Collection, collation and analysis of data Play roles as members of district monitoring team | Data Collection Dissemination of information Reporting |
| 10 | District Agriculture Dept. | Primary | Provision of veterinary services Crop protection services Monitor and supervise services provided Collection, collation and analysis of data Play roles as members of district monitoring team Provide extension services Ensures food security | Data Collection Dissemination of information Reporting |
| 11 | MP | Primary | To brief constituents on activities in parliament Decision making Collates the concerns of the people for parliament and higher authority Monitors development Lobbies for development programmes | M &E Seminars & meetings Supervision and inspection of projects /programmes M & E results reporting and dissemination |
| 12 | Political Parties | Primary | Acts pressure groups Evaluate the performance of government | Dissemination of information Evaluation of projects and programmes |
| 13 | Development partners | Secondary | Act as donors for various projects Initiate and monitor projects Provide employment Provide social infrastructure for health, education and others | Monitoring and evaluation of projects and programmes Reporting |
| 14 | Media | Secondary | Transparency and Accountability Information to the public Means of collecting information | Projects inspections Dissemination and communication of M & E results |
| 15 | Civil Society Groups (NGOs, FBOs, CBOs) | Secondary | Information dissemination Act as advocates Initiate projects Collect and provide data and other information Demand accountability and transparency | Capacity building for M&E staff Data Collection Monitoring and evaluation of projects and programmes Dissemination of information |
| 16 | Traditional Authority | Primary | Influence decision making, Initiate development projects Lobby for projects, Influence the political systems Custodians of land | Durbar, Meetings |

SOURCE: DPCU 2021

#### 6.3 Monitoring and Evaluation Matrix

The matrix, which is an important component in every M&E plan, provides a format for presenting the inputs, outputs, outcomes, and impacts (and their corresponding activities) for each DMTDP objective.  It provides a summary of the overall monitoring and evaluation and a list of methods to be used in collecting the data.

Table 28: Monitoring Matrix

| Table 8.10.6 : GOAL 1: PROMOTE PROSPEROUS AND INCLUSIVE LOCAL ECONOMY |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Indicators |  | Indicator Definition |  | Indicator Type | Baseline 2021 | Targets |  |  |  | Disaggregation | Monitoring Frequency |  | Responsibility |
|  |  |  |  |  |  | 2022 | 2023 | 2024 | 2025 |  |  |  |  |
| Programme 1: Economic Development Sub-programme 1: Agriculture Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Total output in agriculture production (Tonnage) |  | Measure of agriculture output |  | Outcome |  |  |  |  |  | Selected Crops | Quarterly | DDA / DPCU |  |
| - Maize |  |  |  |  | 28% | 30% | 33% | 35% | 37% |  |  |  |  |
| - Cassava |  |  |  |  | 7.9% | 10% | 12% | 15% | 17% |  |  |  |  |
| - Yam |  |  |  |  | 4.81% | 6% | 8% | 11% | 13% |  |  |  |  |
| - Plantain |  |  |  |  | 11.26% | 13% | 14% | 16% | 18% |  |  |  |  |
| - Cattle |  |  |  |  | 51% | 55% | 62% | 67% | 71% |  |  |  |  |
| - Sheep |  |  |  | Outcome | 70% | 75% | 77% | 80% | 82% |  |  |  |  |
| - Pig |  |  |  | Outcome | 49% | 52% | 56% | 60% | 64% |  |  |  |  |
| - Poultry |  |  |  |  | 1:2,616 | 1:2800 | 1:3000 | 1:3200 | 1:3400 |  |  |  |  |
| 2 Percentage Change in IGF |  | The amount of IGF generated as against the previous years’ amount expressed as a percentage |  | Outcome | 55.2% | 61% | 62.9% | 65.1% | 69.3% |  | Quarterly | Finance Department |  |
| 3. Percentage of annual Action Plan implemented |  | Number of projects and programmes implemented out of the total planned for a given year expressed as a percentage |  | Outcome | 90.5% | 91.5 | 92 | 92.5 | 93 |  |  | D/A |  |
| 4. Percentage of arable land under cultivation |  | Measure of arable land |  | Outcome | 69.5% | 76% | 81% | 86% | 93% |  | Quarterly | DDA / DPCU |  |
| 5. Number of jobs created under agriculture |  | Count of people employed |  | Outcome | 800 | 950 | 1100 | 1200 | 1300 | Male: 450 Female: 350 | Quarterly | BAC |  |
| 6. Number of new industries established created under agriculture |  | Count of industries |  | Outcome | 1 | 1 | 1 | 1 | 1 |  | Annually | DPCU |  |
| 7.Change in tourist arrivals (%) |  | Change in the tourist who arrives in the District in a given year expressed as a percentage of the previous year's number of tourist arrivals |  | Outcome | 35% | 40% | 50% | 55% | 65% |  | Quarterly | DPCU |  |
| PROGRAMME: Social Services delivery SUB-PROGRAMME: Education and training and youth development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. B.E.C.E Pass rate JHS | Number of candidates who passed BECE over the total registered candidates expressed as a percentage |  |  | Outcome | 62% | 71% | 81% | 90% | 96% |  | Quarterly | GES |  |
| 8. Net enrolment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Primary | Total |  | Pupils in schools | Outcome | 110% | 115% | 119% | 120% | 121% |  | Quarterly | GES |  |
|  | Male |  |  |  | 56% | 59% | 60% | 62% | 63% |  | Quarterly | GES |  |
|  | Female |  |  |  | 54% | 56% | 59% | 58% | 58% |  | Quarterly | GES |  |
| JHS | Total |  | Pupils in schools |  | 68.70% | 90% | 90% | 100% | 100% |  | Quarterly | GES |  |
|  | Male |  |  |  | 39.6% | 49.6% | 51.6% | 50.5% | 52.5% |  | Quarterly | GES |  |
|  | Female |  |  |  | 29.4% | 40.4% | 38.4% | 49.4% | 47.5% |  | Quarterly | GES |  |
| 9. Pupil teacher ratio |  |  |  |  |  |  |  |  |  |  |  |  |  |
| KG | Total |  | Pupils and teachers in school | Outcome | 62:1 | 58:1 | 50:1 | 45:1 | 40:1 |  | Quarterly | GES |  |
|  | Public |  |  |  | 47:1 | 42:1 | 35:1 | 30:1 | 30:1 |  | Quarterly | GES |  |
|  | Private |  |  |  | 15:1 | 25:1 | 25:1 | 25:1 | 25:1 |  | Quarterly | GES |  |
| Primary | Total |  | Pupils and teachers in school | Outcome | 50:1 | 45:1 | 40:1 | 35:1 | 30:1 |  | Quarterly | GES |  |
|  | Public |  |  |  | 29:1 | 25:1 | 25:1 | 25:1 | 25:1 |  | Quarterly | GES |  |
|  | Private |  |  |  | 19:1 | 19:1 | 19:1 | 25:1 | 25:1 |  | Quarterly | GES |  |
| JHS | Total |  | Pupils and teachers in school | Outcome | 34:1 | 30:1 | 25:1 | 20:1 | 20:1 |  | Quarterly | GES |  |
|  | Public |  |  |  | 20:1 | 25:1 | 25:1 | 25:1 | 25:1 |  | Quarterly | GES |  |
|  | Private |  |  |  | 14:1 | 25:1 | 25:1 | 25:1 | 25:1 |  | Quarterly | GES |  |
| 10. Gender Parity Index |  |  | Males and females in school | Outcome | N/A |  |  |  |  |  | Quarterly | GES |  |
| Kindergarten |  |  |  |  | 0.87 | 1 | 1 | 1 | 1 |  | Quarterly | GES |  |
| Primary |  |  |  |  | 0.80 | 1 | 1 | 1 | 1 |  | Quarterly | GES |  |
| JHS |  |  |  |  | 0.82 | 1 | 1 | 1 | 1 |  | Quarterly | GES |  |
| SHS |  |  |  |  | 0.80 | 1 | 1 | 1 | 1 |  |  |  |  |
| 11. Completion rate |  |  |  |  |  |  |  |  |  |  | Quarterly | GES |  |
| Primary | Total |  | Pupil who completed school | Outcome | 75% | 85% | 90% | 93% | 95% |  | Quarterly | GES |  |
|  | Male |  |  |  | 32.39% | 45% | 46% | 49% | 50% |  | Quarterly | GES |  |
|  | Female |  |  |  | 42.61% | 40% | 44% | 44% | 45% |  | Quarterly | GES |  |
| JHS | Total |  | Pupil who completed school | Outcome | 84.6% | 89% | 90% | 95% | 100% |  | Quarterly | GES |  |
|  | Male |  |  |  | 55.2% | 60% | 65% | 70% | 80% |  | Quarterly | GES |  |
|  | Female |  |  |  | 29.4% | 40% | 45% | 50% | 50% |  | Quarterly | GES |  |
| PROGRAMME: Health services delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12. Maternal mortality ratio (number of deaths due to pregnancy and children per 100,000 live births) |  | No. of births and deaths |  | Outcome | 0 (cases are handled by Bia west hospital) | 0 | 0 | 0 | 0 |  | Quarterly | GHS |  |
| 13. Under-five mortality rate (number of deaths occurring between birth and exact age five per 1000 live births) |  | No. of death occurring between birth and exact age 5 |  | Outcome | 0 | 0 | 0 | 0 | 0 |  | Quarterly | GHS |  |
| 14. Malaria case fatality in children under five years per 10,000 population |  | No. of death occurring children under 5 years |  | Outcome | 0 | 0 | 0 | 0 | 0 |  | Quarterly | GHS |  |
| PROGRAMME: Infrastructure Delivery and Management SUB-PROGRAMME: Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15. Proportion/length of roads maintained/rehabilitated |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Trunk roads (in km) |  | Kilometer s of motorable roads |  | Outcome |  |  |  |  |  |  |  |  |  |
| Urban roads (in km) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Feeder roads (in km) |  |  |  |  | 80KM | 100KM | 100KM | 100KM | 100KM |  | Annually | Annually |  |
| 16. Percentage of communities covered by electricity |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - District |  | Number of communities with electricity |  | Outcome | 70% | 80% | 87% | 94% | 100% |  | Quarterly | ECG |  |
| - Urban |  |  |  |  | N/A | N/A | N/A | N/A | N/A |  | Quarterly | ECG |  |
| - Rural |  |  |  |  | 60% | 65% | 70% | 75% | 85% |  | Quarterly | ECG |  |
| PROGRAMME: Environmental and Sanitation Management SUB-PROGRAMME: Water resources management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17. Percentage of population with sustainable access to safe drinking water sources |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - District |  | Number of communities with safe drinking water |  | Outcome | 71% | 73% | 76% | 80% | 82% |  | Quarterly | DPCU |  |
| - Urban |  |  |  | Outcome | N/A | N/A | N/A | N/A | N/A |  | Quarterly | DPCU |  |
| - Rural |  |  |  | Outcome | 71% | 73% | 76% | 80% | 82% |  | Quarterly | DPCU |  |
| PROGRAMME: Environmental Sanitation SUB-PROGRAMME: Environmental and Sanitation Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18. Proportion of population with access to improved sanitation service |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - District |  | Number of communities with sanitation facilities |  | Outcome | 56% | 63% | 68% | 73% | 80% |  | Quarterly | DPCU |  |
| - Urban |  |  |  |  | N/A | N/A | N/A | N/A | N/A |  | Quarterly | DPCU |  |
| - Rural |  |  |  |  | 56% | 63% | 68% | 73% | 80% |  | Quarterly | DPCU |  |
| SUB-PROGRAMME: Disaster management and prevention |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 19. Number of disasters |  | Count of disasters |  | Output | 11 | 9 | 8 | 7 | 5 |  | Quarterly | NADMO |  |
| 20. Police citizen ratio |  | Count of police officers |  | Output | 1:1,587 | 1:500 | 1:500 | 1:500 | 1:500 |  | Quarterly | GPS |  |
| PROGRAMME: Social Services Delivery SUB-PROGRAMME: Social Welfare and Community Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 21. Number of reported cases of abuse (children, women and men) |  | Count of crime cases |  | Output | 140 | 124 | 100 | 80 | 65 | Men: 75 Women: 215 Children: 210 | Quarterly | GPS, SWCD CHRAJ |  |

## M & E Work Plan and Calendar

## 6.4 M & E Work Plan

The M & E work plan is to guide the implementation of the District Medium Term Plan. It contains all the programmes envisaged for the four year planned period of a policy or intervention. It assigns responsibilities, timeframes and cost of all the activities identified. Details of the M&E work plan for Juaboso District (2022-2025) as indicated below.

Table 29: M & E Work Plan 2022 – 2025

| M & E ACTIVITIES | TIMELINE 2022 – 2025 | ACTORS |
| --- | --- | --- |
| M& E PLAN PREPARATION |  |  |
| Review and selection of indicators | Every 4th Quarter | DPCU |
| IMPLEMENTATION MONITORING |  |  |
| Field visits | Quarterly | DPCU |
| Review Meetings | Mid – year | DPCU |
| PREPARATION OF M & E REPORTS |  |  |
| Preparation of Annual Progress Reports | 15TH January | DPCU |
| Data Collection | Quarterly | DPCU |
| Data Collation | Every Quarter | DPCU |
| Data Analysis | Every quarter | DPCU |
| Organize APR validation workshops and Internal review on draft APR and printing of the ARP | Every quarter | DPCU, RCC, CSOs |
| RPCU Monitoring | Every quarter | DPCU, RPCU |
| DISSEMINATION AND COMMUNICATION OF M & E RESULTS |  |  |
| Organize APR dissemination workshops | Every 2nd quarter | RCC, CSOs, etc. |
| Feedback on DMTP implementation | 3rd Quarter of 2023 | DPCU |
| PM&E |  |  |
| Build M & E capacity | Yearly | DPCU |
| EVALUATION |  |  |
| Selected Evaluation Activities | Every Year | DPCU, RCC |

## 6. 5 M & E Calendar

The M&E calendar outlines the scheduled activities for effective monitoring of activities in the Medium Term Development Plan (MTDP). It shows the specific activities

Table 30: M & E Calendar for 2022-2025

| M& E Activities | Jan | Feb | Mar | Apr | May | Jun | July | Aug | Sept | Oct | Nov | Dec |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Review and selection of indicators |  |  |  |  |  |  |  |  |  |  |  |  |
| Field visits |  |  |  |  |  |  |  |  |  |  |  |  |
| Review Meetings |  |  |  |  |  |  |  |  |  |  |  |  |
| Public Education |  |  |  |  |  |  |  |  |  |  |  |  |
| Preparation of Progress Reports |  |  |  |  |  |  |  |  |  |  |  |  |
| Data Collection |  |  |  |  |  |  |  |  |  |  |  |  |
| Data Collation |  |  |  |  |  |  |  |  |  |  |  |  |
| Data Analysis |  |  |  |  |  |  |  |  |  |  |  |  |
| Organize APR validation workshops |  |  |  |  |  |  |  |  |  |  |  |  |
| Internal review of draft APR |  |  |  |  |  |  |  |  |  |  |  |  |
| Peer Review of APR |  |  |  |  |  |  |  |  |  |  |  |  |
| Organize APR dissemination workshops |  |  |  |  |  |  |  |  |  |  |  |  |

Sources: DPCU, 2021

Table 31: M & E Budget 2022 - 2025

| Item | Activities | Inputs | Qty. or No of People | Freq. | Unit Cost | Amount |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | (Gh¢) | (Gh¢) |
| M & E PLAN PREPARATION | Preparation of the M & E plan | Facilitators | 4 | 5 | 100 | 2000 |
|  |  | Conference Package | 20 | 4 | 100 | 8000 |
|  |  | Travel | 10 | 4 | 100 | 4000 |
|  |  | fuel |  |  |  | 1500 |
|  |  | Logistics | 20 | 4 | 20 | 1200 |
|  |  | Sub– Total |  |  |  | 16,700.00 |
| M & E IMPLEMENTATION | Organize quarterly field visits | Facilitators |  |  |  |  |
|  |  | fuel |  | 11 | 1500 | 16,500 |
|  |  | Travel | 15 | 20 | 100 | 30,000.00 |
|  |  | Logistics | 15 | 20 | 20 | 6,000.00 |
|  |  | Sub– Total |  |  |  | 52,500.00 |
|  | Review Meetings | Facilitators | 2 | 5 | 100 | 1000 |
|  |  | Conference Package | 20 | 5 | 50 | 5000 |
|  |  | Travel | 0 | 0 | 0 | 2000 |
|  |  | Logistics | 20 | 5 | 20 | 2000 |
|  |  | Sub– Total |  |  |  | 10,000.00 |
|  | Organize QPR Preparation and validation workshops | Facilitators | 2 | 11 | 100 | 2200 |
|  |  | Conference Package | 15 | 10 | 50 | 7,500 |
|  |  | Travel | 0 | 0 | 0 | 2000 |
|  |  | Logistics | 15 | 16 | 20 | 4800 |
|  |  | Sub– Total |  |  |  | 16,500.00 |
|  | Organize Quarterly and Annual Progress Report dissemination workshops / Feedback on DMTDP Implementation | Facilitators |  |  |  |  |
|  |  | Conference Package | 20 | 4 | 50 | 4,000.00 |
|  |  | Travel |  |  |  | 2,000.00 |
|  |  | Logistics | 30 | 4 | 20 | 2,400.00 |
|  |  | Sub– Total |  |  |  | 8,400.00 |
| M & E REVIEW MEETINGS | Quarterly Review Meetings with DPCU and RPCU | Facilitators |  |  |  |  |
|  |  | Conference Package | 15 | 16 | 50 | 12,000.00 |
|  |  | Travel | 1 | 1 | 2000 | 2,000.00 |
|  |  | Logistics | 15 | 16 | 20 | 4,800.00 |
|  |  | Sub– Total |  |  |  | 18,800.00 |
| BUILD M & E CAPACITY | Organize M&E Training Workshops | Facilitators | 3 | 4 | 100 | 1,200.00 |
|  |  | Conference Package | 15 | 4 | 50 | 3,000.00 |
|  |  | Travel |  |  |  | 0.00 |
|  |  | Logistics | 15 | 4 | 20 | 1,200.00 |
|  |  | Sub– Total |  |  |  | 5,400.00 |
| EVALUATION | Selected Evaluation Activities |  |  |  |  | 15,000.00 |
| GRAND TOTAL |  |  |  |  |  | 143,300.00 |

# CHAPTER SEVEN

# COMMUNICATION STRATEGY

# Introduction

# Reporting/disseminating the right information on the status of implementation of the formulated development programmes, projects and activities to stakeholders at the local, regional and national levels respectively at the right time plays crucial role in the successful execution of the 2022-2025 DMTDP. This is because the various stakeholders can only play their roles and responsibilities well towards the implementation of the plan when they are adequately informed.

## 7.1 Strategies

The strategies the Juaboso District has adopted to communicate or disseminate information on the status of implementation of the plan within the plan period 2022-2025 include:

    - Quarterly, mid-term and end of year M&E exercises will be conducted after which Quarterly, mid –year and annually progress reports will be compiled on the status of implementation on the development programmes/projects whiles both hard and soft copies of the main plan will be distributed to RCC and NDPC.

At the local level, copies of the progress reports will be distributed to P.M, DA sub-committees especially F&A, Works and Economic Planning sub-committees, local NGOs, Decentralized Departments etc. and copies kept at the DPCU Secretariat for reference.

At the regional and national levels, copies of the reports will be sent to RCC, MLGRD, and NDPC.

    - Quarterly, mid-year and annual review meetings will also be held to brief DPCU members and other stakeholders and the progress reports.

On the creation of awareness on the roles and expectations of stakeholders in the implementation of development programmes to improve their living standards for the plan period, the various stakeholders will be informed during the public hearings on the plan especially the second one. These have been clearly spelt out under chapter five i.e. implementation of Annual Action Plans where the specific roles, contributions, expectations, lead and collaborating agencies for the plan period have all been stated.

General dialogue will be promoted and feedbacks on performance of the district will be received through mid-year composite and end of year reviews meetings, reports from Area councils, Unit Committees, opinion leaders, Public Complaint Unit of the Assembly, General Assembly meetings and the Development Communication Committee that will be formed.

However, a more detailed communication strategy that provides a more visual and easier understanding of how the information on the implementation of the plan will be sent to stockholders and feedback mechanisms. The matrix also shows how the strategy can be used to mobilise funds for the district.

All the strategies outlined in the matrix are really geared towards identifying the relevant stakeholders, their roles/ responsibilities, the various level of involvement in the various activities relating the communication strategy set out for the 2022-2025 DMTDP for the Juaboso district.

Furthermore, the strategy is meant to showcase the results of the programmes and projects in the plan which is supposed to transform the living conditions of the people. By disseminating the results or impacts of the plan to relevant stakeholders and providing feedbacks, they would be encouraged to provide the necessary resources for the district to implement the plan. This will help the vigorous resource mobilisation drive set out in the revenue mobilisation Action Plan.

Table 32: Communication Strategy Matrix

| Table 26: ACTIVITY | PURPOSE | TARGET GROUP | METHOD/TOOL | TIMEFRAME | RESPONSIBILITY |
| --- | --- | --- | --- | --- | --- |
| Town Hall Meetings | To create awareness to the public on projects, expenditure and revenue of the Assembly | Traditional Authority, community members, media, Assembly members etc. | Meetings with audio-visuals on projects and programmes | Quarterly | DPO, DBA |
| Performance Review meetings | To inform stakeholders on status of MTDP implementation | DPCU, RCC, Heads of Department etc. | Round – Table discussions and Power Point Presentations | Quarterly | DPCU |
| Community Engagement | To bridge the gap between the Management and the Communities members to receive first-hand information and feedback on identified issues | Community members, media, CSOs | Meeting with audio-visuals, participatory rural appraisal tools | Monthly | DPCU |
| Community Sensitization | To create public awareness on their rights and responsibilities on monitoring etc. | Community members, Assembly members, unit committee members etc. | Radio discussions and phone-in programmes | Monthly Quarterly | DPCU |
| Public Hearing | To update the MTDP to ensure that projects and programmes conform with prioritized needs of the communities | Community Members, Traditional Authority, Media etc. | Meetings with audio-visuals on projects and programmes | Once every year | DPCU |

# SOURCE: DPCU 2021

All the strategies outlined in the matrix are really geared towards identifying the relevant stakeholders, their roles/ responsibilities, the various level of involvement in the various activities relating the communication strategy set out for the 2022 – 2025 DMTDP for the Juaboso District Assembly.

### 7.1.1 Approaches/Channels for Communication

The methodologies outlined below will focus on group and individual approaches or organizational through interaction, information dissemination, training, management development programmes, team building and survey feedback techniques.

The approaches to be used to achieve the above-objectives are:

- Local Government Information Digest

- Radio, public service announcements and phone-ins;

- Workshops/Seminars

- Focus Group Discussions

- Consultative Meetings

- Town Hall Meetings

- Briefing of RCCs and General Assembly during meetings

- District Website Updating www.juada.gov.gh)

The Communication channels envisaged are:

Using Discussion Programmes

- Electronic Media: Radio (selected FM stations in the District)

- Print Media: Selected Newspaper for publication of Articles

- Information Service Division

Table 33: Operation and Maintenance Plan (2022-2025)

| Type of Infrastructure/ Assets | Type of maintenance | Schedule of Maintenance (start date – end date) | Estimated cost of maintenance | Location | Responsibility |
| --- | --- | --- | --- | --- | --- |
| Residential Accommodation | Renovation & Furnishing | # 2022-2025 | # 220,000.00 | # Juaboso | Works/procurement |
| Office Accommodation | Renovation &Furnishing | # 2022-2025 | # 240,000.00 | # Juaboso | Works/procurement |
| Official Vehicles | Servicing and routine maintenance | # 2022-2025 | # 272,000.00 | # Juaboso | Transport/Procurement |
| Office Equipment | Servicing and routine maintenance | # 2022-2025 | # 180,000.00 | # Juaboso | Procurement/ MIS |
| Street Lights | Change of electric bulbs, general repairs | # 2022-2025 | # 720,000.00 | # District wide | # ECG and Works Dept |
| Markets | Rehabilitation and Renovation | # 2022-2025 | # 432,000.00 | # Juaboso, Proso, Kofikrom, Boinzan | Works & feeder roads |
| Feeder Roads | Rehabilitation, reshaping, construction and re-construction of bridges | # 2022-2025 | # 1,000.000.00 | # District wide | Works and Feeder roads Dept. |
| School buildings | Renovation | # 2022-2025 | # 600,000.00 | # District wide | Health/Works |
| Maintenance of Boreholes | Rehabilitation & Renovation | # 2022-2025 | # 240,000.00 | # District wide | # Works Department |
| Solid waste management | Evacuation of refuse dump in the district | # 2022-2025 | # 1,200,000.00 | Juaboso,Bonsu Nkwanta, Proso Kofikrom | # Works Department and Environmental Health |
| Liquid waste management | Routine maintenance | # 2022-2025 | # 1,280,000.00 | Juaboso, Bonsu Nkwanta Benchema Nkateso, Proso Kofikrom, Asempaneye | # Env. Health Unit # Works Department |

# BIBLIOGRAPHY

# National Development Planning Commission: Medium-Term National Development Policy

# Framework 2022-2025: Agenda for Job PF, Ghana Beyond Aid Charter and Strategy,

# Emergency Planning and Response (Including Covid -19 Recovery Plan) and the ACFTA.

# National Disaster Management Organization, 2013 Owusu, George; Oteng-Ababio, Martin:

# : 2012 Annual Progress report on the implementation of GSDA 1I. National Development

# Planning commission, 2013.

# Ghana Statistical Service, (2013) 2010 population and housing census: national and district

# analytical report. Ghana Statistical Service, Sefwi Wiawso district

# Inter-Ministerial Coordinating Committee: Progress Report: Implementation of the

# Decentralization Policy Framework. Inter-Ministerial Coordinating Committee (IMCC) on

# Decentralization, 2012

# Ministry of Environment, Science and Technology (2011), Manual for the preparation of spatial

# plans, Town and Country Department

# Ministry of Environment, Science and Technology (2011), Manual for the preparation of spatial

# plans, Town and Country Department

# Ministry of Lands and Natural Resources: Ghana Forest and Wildlife Policy. Ministry of Lands

# and Natural Resources (2012) National Disaster Management Organization: Report on the major

# activities in 2013.

# Drechsel, Pay; Keraita, Bernard (Editors): Irrigated Urban Vegetable Production in Ghana:

# Characteristics, Benefits and Risk Mitigation. International Water Management Institute,

# Environmental Protection Agency: Africa Adaptation Programme (AAP) on Climate Change

# Ghana Final Project Review. Environmental Protection Agency, 2013 Environmental Protection

# Agency: Vulnerability, Impact and Adaptation Assessment Report under NCAP II.

# Environmental Protection Agency,

# Ministry of Lands and Natural Resources: Ghana Forest and Wildlife Policy. Ministry of Lands

# and Natural Resources (2012) National Disaster Management Organization: Report on the major

# activities in 2013.

# Ministry of Local Government and Rural Development: National Environmental Sanitation

# Strategy and Action Plan. Environmental Health and Sanitation Directorate, Ministry of Local

# Government and Rural Development, 2010

# Ministry of Local Government and Rural Development: National Environmental Sanitation

# Strategy and Action Plan. Environmental Health and Sanitation Directorate, Ministry of Local

# Government and Rural Development, 2010

# Ministry of Water Resources Works and Housing: National Water Policy. Ministry of Water

# Resources Works and Housing, 2007

# National Development Planning Commission (2014): National Monitoring and Evaluation

# Manual

# National Development Planning Commission (2014): National Monitoring and Evaluation

# Manual

# National Development Planning Commission: Annual Progress Report on the Implementation of

# the Ghana Shared Growth Development Agenda 2013-2017. NDPC, 2010

# National Development Planning Commission: Annual Progress Report on the Implementation of

# the Ghana Shared Growth Development Agenda 2010-2013. NDPC, 2010

# National Development Planning Commission: Medium-Term National Development Policy

# Framework: Agenda for Job 2022-2025.

# The legal and policy framework regulating the practice of decentralization include Chapter 20 of

# the Constitution of Ghana (1992); the National Development Planning (System) Act (1994) Act

# 480; Local Governance Act 2016 (936); National Development Planning Regulation Instrument

# 2232

CWSA defines access to safe water to include the following elements:

- Ensuring that each person in a community served has access to no less than 20 liters of water per day

- Ensure that walking distance to a water facility does not exceed 500 meters from the furthest house in the community

- That each sprout of borehole or pipe system must serve no more than 300 persons and 150 for a hand dug well

- The water system is owned and managed by the community

- Water facility must provide all year-round potable water to community members