JUABOSO DISTRICT ASSEMBLY

REVISED ANNUAL ACTION PLAN FOR 2025

| DEVELOPMENT DIMENSION | NUMBER OF ACTIVITIES |
| --- | --- |
| ECONOMIC DEVELOPMENT | 19 |
| SOCIAL DEVELOPMENT | 72 |
| ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENT | 30 |
| EMERGENCY PLANNING AND RESPONSE (INCLUDE COVID-19) | 5 |
| GOOD GOVERNANCE AND PUBLIC ACCOUNTABILITY | 11 |
| IMLEMENTATION, COORDINATION, MONITORING AND EVALUATION | 6 |
| TOTAL | 143 |

Composite Annual Action Plan 2025

| Programme (PBB) | Sub-Programme (PBB) |  | Broad Activities |  | Location | Timeframe (2023) |  |  |  | Cost |  |  |  | Programme Status |  |  | Implementing Institution/Department |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  | Q1 | Q2 | Q3 | Q4 | GoG | IGF/ABFA |  | Others | New | Ongoing |  | Lead | Collaborating |  |  |  |
| DEVELOPMENT DIMENSION: ECONOMIC DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Strong and Resilient Economy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management administration | Finance and Revenue Mobilization |  | Revise and update data on revenue sources |  | Juaboso |  |  |  |  | 12,500.00 |  |  |  | New | - |  | Finance Dept | MLGDRD |  |  |  |
| Management administration | Finance and Revenue Mobilization |  | Organize fresher training for revenue collectors |  | Juaboso |  |  |  |  | 20,000.00 |  |  | - | New | - |  | DBA, DFO | Central admi |  |  |  |
| Focus area: Private Sector Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize social media marketing training for women and men |  | District wide |  |  |  |  | 8,500.00 |  |  |  |  | On-going |  | BAC | JDA, GEA, MOTI |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Completion of Juaboso Community centre |  | Juaboso |  |  |  |  | 500,000.00 |  |  |  |  | Ongoing |  | DWD | JDA |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Redevelopment of old market into 24hr economy market (100Units Lockable stores, 1No. Police post, 1No. K.G Block, 24 Units Toilets with bathrooms and social Centre) |  | Juaboso |  |  |  |  | 4,269,602.00 |  |  |  | New |  |  | DWD | DA |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize business forum and business counselling |  | Juaboso |  |  |  |  | 5,000.00 |  |  |  |  | On-going |  | BAC | JDA, GEA, MOTI |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Construction of 2No 12 Market sheds |  | Sayerano |  |  |  |  | 150,000.00 |  |  |  | New |  |  | BAC | JDA |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize 1Training session on Credit Management |  | Juaboso |  |  |  |  | 4,500.00 |  |  |  |  | On-going |  | BAC | Trobenbos Ghana |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Formalization of Business registration and certification |  | Districtwide |  |  |  |  | 5,000.00 |  |  |  |  | On-going |  | BAC | GEA/ Clients |  |  |  |
| Economic Development | Trade, tourism and industrial development |  | Organize 2 training workshop on technology improvement in bee keeping |  | Selected Communities |  |  |  |  | 12,000.00 |  |  |  |  | On-going |  | BAC | GEA/DA |  |  |  |
| Focus area: Agriculture and Rural Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Economic Development | Agricultural Development | Training of staff and farmers on IMO technology |  |  | 20 Communities |  |  |  |  |  |  |  | 19,000.00 |  | On-going |  | Agric. dept | RADU, Farmers, Staff |  |  |  |
| Economic Development | Agricultural Development | Organization of community and district planning session |  |  | Juaboso |  |  |  |  |  |  |  | 4,350.00 |  | On-going |  | Agric. dept | RADU, Research, NGOs, DA, Farmers |  |  |  |
| Economic Development | Agricultural Development | Train Farmers on Vegetable production |  |  | 10 Communities |  |  |  |  | 2,000.00 |  |  | 3,000.00 |  | On-going |  | Agric. dept | RADU Farmers, AEAs |  |  |  |
| Economic Development | Agricultural Development | Maintenance of official vehicle and motorbikes |  |  | Juaboso |  |  |  |  | 7,000.00 |  |  |  |  | On-going |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Maintenance of office complex and DDA residence |  |  | Juaboso |  |  |  |  |  | 2,000.00 |  |  | New |  |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Training farmers on post-harvest management |  |  | Juaboso |  |  |  |  | 4,000.00 |  |  |  | New |  |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Organization of District Farmers Day |  |  | District wide |  |  |  |  |  |  |  | 200,000.00 |  | On-going |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Acquisition of 1,200 Palm oil for PERD program |  |  | District wide |  |  |  |  | 15,000.00 |  |  |  |  | On-going |  | Agric. dept | D.A |  |  |  |
| Economic Development | Agricultural Development | Organise workshop and staff train climate smart agricultural |  |  | District wide |  |  |  |  | 10,000,00 |  |  |  | New |  |  | Agric. dept | D.A |  |  |  |
| Development Dimension: SOCIAL DEVELOPMENT |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Education and Training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organize Science, Technology, Mathematics, and Innovative Education (STMIE) clinics |  | Juaboso |  |  |  |  |  | 5,000.00 | 4,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Support the District Education Oversight Committee to monitor teaching and learning in schools |  | Juaboso |  |  |  |  |  | 4,500.00 |  |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organization of Independence Day celebration |  | Juaboso |  |  |  |  |  | 45,000.00 |  |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Support for Needy but Brilliants Students |  | District wide |  |  |  |  |  | 30,000.00 |  |  |  |  | Ongoing |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organize reading festivals to create awareness and encourage children to read |  | Juaboso |  |  |  |  |  |  | 6,000.00 |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organise my first day at school ceremony schools |  | Selected schools |  |  |  |  |  | 15,000.00 |  |  |  |  | On-going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1 No. School feeding kitchen |  | Juaboso Nkwanta |  |  |  |  |  | 350,000.00 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Organize mock examination for JHS three students |  | District wide |  |  |  |  |  | 20,000.00 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Procure and Supply of 240metal Dual Desk for 2No. Primary School @ 1,400.00 |  | Juaboso |  |  |  |  |  | 336,000.00 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Procure and Supply of 934 Dual metal Desk for 200 basic schools@ 1400 |  | Distruct wide |  |  |  |  |  | 1,306,540.00 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1 No. K.G block & Ancillary facility |  | Bonsu Nkwanta |  |  |  |  |  | 500,227 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Procure and supply of 2Set of K.G tables and chairs for 2No. KG School@ 20,000.00 |  | Kofikrom Breman |  |  |  |  |  | 40,000.00 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Procure and supply Set of tables and chairs for teachers for 2No. KG and 2No. Primary Schools |  | Kofikrom Breman Kyene kokoo |  |  |  |  |  | 25, 300.96 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1 No. school kitchen with Ancillary facilities |  | Juaboso Nkwanta |  |  |  |  |  | 400,227 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Supply of 600 dual desks for Pry. School and 500 mono desks for JHS |  | District-wide |  |  |  |  |  | 400,000.00 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Provide financial support to promote ICT education |  | Juaboso |  |  |  |  |  | 18,000.00 |  |  |  | New |  |  | JDA | GIFEC |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Undertake stakeholder and consultative meeting on scaling up effective mechanisms to promote and build sustainable TVET among women |  | District wide |  |  |  |  |  | 6,000.00 |  |  |  | New |  |  | GDO | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction. of 1 No. K.G block & Ancillary facility |  | Juaboso |  |  |  |  |  | 500,227 |  |  |  |  | Ongoing |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Renovation . of 1 No. 6 K.G block |  | Sayerano |  |  |  |  |  | 350,227 |  |  |  |  | On going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 6Unit classroom block (CODA) |  | Aboso |  |  |  |  |  | 350,000.00 |  |  |  |  | Ongoing |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Completion of Juaboso1Unit K.G block (CODA) |  | Juaboso Nkwanta |  |  |  |  |  | 200,000.00 |  |  |  |  | Ongoing |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1No 6-unit classroom Block with Ancillary facility |  | Yawagyiemkrom |  |  |  |  |  | 650,000.00 |  |  |  |  | On going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1No 3unit classroom block |  | Mantukwa |  |  |  |  |  | 3,447.10 |  |  |  |  | On going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 2No.6Units classroom block, officer, store, changing room washrooms, |  | Sayerena, kyensekokoo |  |  |  |  |  | 1,000,000.00 |  |  |  | New |  |  | GSE | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 2No. K.G block, officer, store, washrooms, 2poly tanks |  | Kofikrom, Breman |  |  |  |  |  | 707,840.8 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1No 3unit classroom block |  | Komeamaa |  |  |  |  |  | 2,000.00 |  |  |  |  | On going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1no. 6unit C. Block and Ancillary facilities |  | Eteso |  |  |  |  |  | 120,000.00 |  |  |  |  | On going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Const. of 1 no. 6 unit Classroom Block with Ancillary facilities |  | Mafia |  |  |  |  |  | 12,524.87 |  |  |  |  | On going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1no. Double 1200mm |  | Kotosah |  |  |  |  |  | 6,021.76 |  |  |  |  | On going |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Construction of 1 no. 6 unit Classroom Block with Ancillary facilities |  | Dominibo |  |  |  |  |  | 150,000.00 |  |  |  |  | On going |  | GES | JDA |  |  |  |
| Focus area: Sports and Recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Education and Youth Development | Support the organization of inter district sports festival |  | Juaboso |  |  |  |  |  | 20,000.00 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1No 6unit block with ancillary facilities |  | Bechimaa |  |  |  |  |  | 180,681.00 |  |  |  |  | Ongoing |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Development | Construction of football pitch |  | Juaboso Kotosah Antobia |  |  |  |  |  | 450,000.00 |  |  |  | New |  |  | GES | JDA |  |  |  |
| Social Services Delivery | Education and Youth Development | Renovation of community centre |  | Juaboso Kotosah Antobia |  |  |  |  |  | 500,000.00 |  |  |  |  | Ongoing |  | GES | JDA |  |  |  |
| Focus area: Health and Health Services |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Construction of 2N0. CHPS Compounds |  |  | Kefas |  |  |  |  | 600,000.00 |  |  |  |  | Ongoing |  | District Health | DA |  |  |  |
| Social Services Delivery | Health Delivery | Completion of 1N0. CHPS Compound (CODA) |  |  | Mansokrom |  |  |  |  | 150,000.00 |  |  |  | Ongoing |  |  | GHS | JDA |  |  |  |
| Social Services Delivery | Health Delivery | Construction of 3No. CHPS Compound with Mechanized borehole, Midwife Quarters, with furnished accommodation |  |  | Adwumamu and fantraline, Nkyensenkokoo |  |  |  |  | 1,707,840.80 |  |  |  | New |  |  | GHS | DA |  |  |  |
| Social Services Delivery | Health Delivery | Intensify public education on causes, prevention and control of Malaria |  |  | District wide |  |  |  |  | 4,500.00 |  |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Focus area: HIV/AIDS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | HIV/AIDS | Organize know your status campaigns in selected communities |  |  | District-wide |  |  |  |  | 7,000 |  |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | HIV/AIDS | Ensure celebration of World HIV/AIDS day and Know your status Campaigns |  |  | District-wide |  |  |  |  | 7,500 |  |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | HIV/AIDS | Organize radio sensitization on the effect of stigmatization against PLWHA |  |  | District-wide |  |  |  |  | 6,500 |  |  |  |  | Ongoing |  | District Health Dir | DA |  |  |  |
| Social Services Delivery | Health Delivery | Provide support for organization of health education on communicable and non-communicable diseases on local FM station |  |  | District-wide |  |  |  |  | 3,500.00 |  |  |  | New |  |  | District Health Dir | DA |  |  |  |
| Focus area: Environmental and Sanitation Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Health Delivery | Organized medical screening exercise and Promote Public Health Hygiene Education in Basic School |  |  | District wide |  |  |  |  | 8,000.00 |  |  |  |  | Ongoing |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Leveling and Pushing of Refuse Dump |  |  | Datano |  |  |  |  | 100,000.00 |  |  |  | New |  |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Completion 12 seater flash toilet (CODA) |  |  | Antobia |  |  |  |  | 300,000.00 |  |  |  |  | Ongoing |  |  | DA |  |  |  |
| Social Services Delivery | Health Delivery | Facilitate the organization of monthly national sanitation day and Daily Public Cleaning |  |  | Asempaneye,Juaboso,Proso,Bonsu Nkwanta |  |  |  |  | 8,000.00 |  |  |  |  | Ongoing |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Procurement of 1No. Refuse Truck |  |  | Juaboso |  |  |  |  | 300,000.00 |  |  |  | New |  |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Purchase of waste Management Logistics |  |  | Juaboso |  |  |  |  | 88,000.00 |  |  |  | New |  |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Acquisition and Documentation of final Disposal site |  |  | Juaboso |  |  |  |  | 100,000,00 |  |  |  | New |  |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Disinfection of Communities in the District |  |  | Districtwide |  |  |  |  | 100,000.00 |  |  |  | New |  |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Sanitation Improvement package |  |  | Districtwide |  |  |  |  | 600,000.00 |  |  |  | New |  |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Construction of Modernized Slaughterhouse with Mechanized boreholes |  |  | Juaboso |  |  |  |  | 350,000.00 |  |  |  | New |  |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Procurement and supply of 180 dust bins |  |  | Districtwide |  |  |  |  | 50,000.00 |  |  |  | New |  |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Facilitate the organization of monthly national sanitation day and Daily Public Cleaning |  |  | District wide |  |  |  |  | 60,500.00 |  |  |  |  | Ongoing |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Quarterly pushing/leveling of final dumping site |  |  | District wide |  |  |  |  | 80,000.00 |  |  |  |  | Ongoing |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Undertake premises inspection |  |  | District wide |  |  |  |  | 3,500.00 |  |  |  |  | Ongoing |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Construction of 3 No. public toilet at market centers and Promote Household Latrine construction. |  |  | Selected communities |  |  |  |  | 360,000.00 |  |  |  | New |  |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Educate the Public on Noise and Air Pollution and Purchase 1No Ambient Device for Noise Control |  |  | Selected Communities |  |  |  |  | 10,000 |  |  |  | New |  |  | DEHU | DA |  |  |  |
| Social Services Delivery | Health Delivery | Control of Stray Animals |  |  | District Wide |  |  |  |  | 5,000 |  |  |  | New |  |  | DEHU | DA |  |  |  |
| Focus area: Population Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Population management | Sensitize people on reproductive health to increase family planning acceptor rate |  |  | District-wide |  |  |  |  |  | 5,000.00 |  |  | New |  |  | GHS | Birth & Death department |  |  |  |
| Social Services Delivery | Population management | Organize radio and community information center discussions on birth and death registration |  |  | District-wide |  |  |  |  |  | 6,500.00 |  |  |  | On-going |  | Birth & Death department | GHS, communities, traditional and religious leaders |  |  |  |
| Social Services Delivery | Population management | Registration of births and deaths in the district |  |  | District-wide |  |  |  |  |  | 4,500.00 |  |  | New |  |  | Birth & Death department | GHS, |  |  |  |
| Focus area: Child Protection and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Child development and protection | Create 4 awareness campaigns for parents to desist from child neglect, discrimination, exposure to physical and moral threats |  |  | District-wide |  |  |  |  |  | 1,600.00 |  |  |  | Ongoing |  | SWCD Central Admin | CRI, Mondelez ILO |  |  |  |
| Social Services Delivery | Child development and protection | Promote public-private partnerships in the provision of alternative care services |  |  | 20 Communities |  |  |  |  | 2,600.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | CRI, Mondelez ILO |  |  |  |
| Social Services Delivery | Child development and protection | Formation of four (4) new women groups and monitoring twelve (12) of the existing groups and to link them to Additional Livelihoods Training |  |  | District-wide |  |  |  |  | 1,550.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | Planning Unit / Gender Desk Officer |  |  |  |
| Disability and Development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | Create 4 awareness campaign on voluntary participation in community initiated projects |  |  | 20 Communities |  |  |  |  | 1,642.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Gender Empowerment | Organize radio talk show programs to advocate for girl child education |  |  | 5 communities |  |  |  |  | 2, 000.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Disability and Development | Facilitate the registration and renewal of 400 vulnerable groups such as PWDs, LEAP beneficiaries etc. onto NHIS |  |  | District wide |  |  |  |  | 2, 000.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social service Delivery | Disability and Development | To support and to train 60% of registered PWDs in the District to engage in economic and business ventures |  |  | District wide |  |  |  |  | 1,500.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Poverty and Inequality |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Social Services Delivery | Gender Empowerment | To Establish four (4) Village Savings and Loans Associations (VSLA) |  |  | District wide |  |  |  |  | 1,500.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Social Services Delivery | Gender Empowerment | To facilitate community dialogue and school outreaches on redefining gender roles to harness women participation in politics, science and technology |  |  | District wide |  |  |  |  | 1,500.00 |  |  |  | New |  |  | GDO | SWCD NGO’s GES |  |  |  |
| Social Services Delivery | Social Welfare and Community Development | To organize training workshops for the NGOs working within the district to understand the need to be registered with the department |  |  | Juaboso |  |  |  |  | 2,000.00 |  |  |  |  | Ongoing |  | SWCD Central Admin | NGOs |  |  |  |
| Development Dimension: ENVIRONMENT, INFRASTRUCTURE AND HUMAN SETTLEMENTS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Protected Areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Focus Area: Climate variability and change |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Organized awareness creation workshop on climate change for Assembly Members, staff and other stakeholders |  |  | District wide |  |  |  |  | 13,500.00 |  |  |  | New |  | JDA |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Train male and female farmers on climate-smart agribusiness |  |  | District wide |  |  |  |  | 10,000.00 |  |  |  | New |  | MoFA |  |  | JDA |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Gazette and strictly enforcement of all HIA by-laws in Juaboso District by December 2024. |  |  | Juaboso |  |  |  |  | 50,000.00 |  |  |  | New |  | JDA |  |  |  |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out sensitization campaign on climate change awareness in line with the Ghana Cocoa Forest REED+ Programme (GCFRP) in 15 Communities |  |  | HTA Communities |  |  |  |  | 91,971.00 |  |  |  | New |  | JDA |  |  | MoFA |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Formation and establishment of Climate Change Ambassadorial Clubs (CCAC) in 20 schools |  |  | Selected schools |  |  |  |  | 100,000.00 |  |  |  | New |  | JDA |  |  | GES |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Carry out stakeholder training and sensitization on climate smart agricultural practices in 13 communities within the HIAs |  |  | HTA Communities |  |  |  |  | 82,500.00 |  |  |  | New |  | JDA |  |  | Agric |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Undertake quarterly forest monitoring (Quarterly) |  |  | Krokosue forest |  |  |  |  | 28,000.00 |  |  |  | New |  | JDA |  |  | Agric |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Participate in consortium meetings with other stakeholders in the HIAs (Quarterly) |  |  | Juaboso |  |  |  |  | 20,000.00 |  |  |  | New |  | JDA |  |  | Agric |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Organize fresher training on the Ghana Cocoa Forest REED+ Programme (GCFRP) for staff and honorable assembly members |  |  | Juaboso |  |  |  |  | 22,500.00 |  |  |  | New |  | JDA |  |  | Forestry |  |  |
| Environmental and Sanitation Management | Natural Resource Conservation | Support to women in agroforestry within climate prone zones |  |  | HTA communities |  |  |  |  | 50,000.00 |  |  |  | New |  | JDA |  |  | Agric |  |  |
| Focus Area: Water Resource Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Water resources management | Construct 13No. Mechanized boreholes |  |  | Selected Communities |  |  |  |  | 853,920.475 |  |  |  | New |  | DWE |  |  | CWSA, DP |  |  |
| Environment, Infrastructure and Human Settlements | Water resources management | Construction of 19No. hand pumps boreholes |  |  | Selected Communities |  |  |  |  | 853,920.475 |  |  |  | New |  | DWE |  |  | CWSA, DP |  |  |
| Environment, Infrastructure and Human Settlements | Water resources management | Extension of water system at ECOMG |  |  | Juaboso |  |  |  |  | 100,000.00 |  |  |  |  | Ongoing | DWD |  |  | JDA |  |  |
| Environment, Infrastructure and Human Settlements | Water resources management | Maintain 15No broken down boreholes |  |  | District wide |  |  |  |  | 170,000.00 |  |  |  | New |  | DWE |  |  | CWSA, DP |  |  |
| Focus area: Transport Infrastructure |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance and reshaping of 145 km feeder roads |  |  | District Wide |  |  |  |  | 345,000.00 |  |  |  |  | ongoing | DWE |  |  | Central Admi |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Construction of 2No. culverts |  |  | Selected communities |  |  |  |  | 290,000.00 |  |  |  | New |  | DWE |  |  | Central Admi |  |  |
| Social Services Delivery | Education and Youth Dev’t. | Completion of 1No.Double box Culvert |  |  | Yawagyiemkrom |  |  |  |  | 130,000.00 |  |  |  |  | On going | GES |  |  | JDA |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Routine maintenance of Assembly vehicle |  |  | Juaboso |  |  |  |  | 106,000.00 |  |  |  |  | ongoing | DWE |  |  | Central Admi |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Rewiring of District Assembly Complex |  |  | Juaboso |  |  |  |  | 200,000.00 |  |  |  |  | Ongoing | DWD |  |  | Central Admi |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Purchase of No. Motor bike for inspection |  |  | Juaboso |  |  |  |  | 19,840.96 |  |  |  | New |  | DWD |  |  | Central Admi |  |  |
| Infrastructure Delivery and Management | Infrastructure Development | Maintenance of Assembly grader |  |  | Juaboso |  |  |  |  | 160,000.00 |  |  |  |  | ongoing | DWE |  |  | Central Admi |  |  |
| Focus area: Infrastructure and Infrastructure Maintenance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Maintenance of office laptops, printers and photo copiers |  |  | Juaboso |  |  |  |  | 25,000 | 10,000 |  | - | - | On-going | ICT officer |  |  | Central admi store keeper |  |  |
| Management and administration | General administration | Procure officer fitting, Equipment and Stationery |  |  | Juaboso |  |  |  |  | 80,000.00 |  |  |  |  | Ongoing | Central Admi |  |  | JDA |  |  |
| Management and administration | General administration | Renovation of DCE and DCD Bungalow |  |  | Juaboso |  |  |  |  | 385,000.00 |  |  |  |  | Ongoing | DWD |  |  | JDA |  |  |
| Management and administration | General administration | Maintenance of official buildings and accommodation |  |  | Juaboso |  |  |  |  | 50,000 | 20,000 |  | - | New | - | JDA |  |  | MLGDRD |  |  |
| Focus area: Energy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environment, Infrastructure and Human Settlements | Energy Infrastructure | Procure/ Maintain 500 Street light bulbs |  |  | District-wide |  |  |  |  | 120,000 | 10,000 |  |  | New |  | JDA, ECG |  |  | Energy Ministry |  |  |
| Focus area: Human Settlements and Housing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Organize radio sensitization on building permit |  |  | Juaboso |  |  |  |  | 5, 500.00 |  |  |  |  | On-going | Works/Planning |  |  | LUSPA |  |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Expansion of street naming and property addressing system |  |  | Proso Kofikrom |  |  |  |  | 40,000.00 |  |  |  |  | On-going | Works/Planning |  |  | Central Admi |  |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Prepare District Spatial Development framework |  |  | Juaboso |  |  |  |  | 15,000.00 |  |  |  |  | Ongoing | Work/Planning |  |  | Central Admi |  |  |
| Infrastructure Delivery and Management | Physical and Spatial Planning | Enforce planning and building regulations |  |  | District-wide |  |  |  |  | 6,000.00 |  |  |  |  | On-going | Works/Planning |  |  | Central Admi |  |  |
| Focus area: Emergency Planning And Response (Include COVID-19) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Hold disaster management committee meeting |  |  | District-wide |  |  |  |  | 3,500 |  |  |  | New |  | NADMO |  |  | Central Admi |  |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Reformation of DVG’s |  |  | District-wide |  |  |  |  | 5,000 |  | 5,000 |  | New |  | NADMO |  |  | Central Admi |  |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Organize anti-bush fire campaign on radio and communities |  |  | District-wide |  |  |  |  | 8,000 |  |  |  | New |  | NADMO, GNFS |  |  | Central Admi |  |  |
| Environmental and Sanitation Management | Disaster Prevention and Management | Form and train disaster clubs |  |  | Schools in the district |  |  |  |  |  | 10,500.00 |  |  | New |  | NADMO, GNFS |  |  | Central Admi |  |  |
| Emergency Planning and response | Health delivery | Carry out active surveillance of diseases of public health importance |  |  | District-wide |  |  |  |  | 11, 000 | 2,000 |  |  | New |  | DHD |  |  | NADMO, JDA |  |  |
| DEVELOPMENT DIMENSION: GOVERNANCE, CORRUPTION AND PUBLIC ACCOUNTABILITY |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Focus area: Local Government and Decentralization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Organize sub-committee, general assembly meeting, and management meetings |  |  | Juaboso |  |  |  |  | 60,000.00 |  |  |  | New |  | Central Admi |  |  |  | MLGDRD NALAG |  |
| Management and administration | General administration | Prepare and gazette Assembly by-laws and fee fixing resolution for 2026 |  |  | Juaboso |  |  |  |  | 35,000.00 |  |  |  | New |  | Central Admi |  |  |  | MLGDRD NALAG |  |
| Management and administration | General administration | Procure and supply office logistics and equipment |  |  | Juaboso |  |  |  |  | 30,000.00 |  |  |  | New |  | Procurement officer |  |  |  | Central Admi, stores |  |
| Management and administration | General administration | Procure 5N0. Laptop computers |  |  | Juaboso |  |  |  |  | 20,000.00 |  |  |  | New |  | Procurement officer |  |  |  | Central Admi, stores |  |
| Management and administration | General administration | Prepare and submit monthly and quarterly progress reports |  |  | Juaboso |  |  |  |  | 10,000.00 |  |  |  |  | Ongoing | DPCU |  |  |  |  |  |
| Management and administration | General administration | Organized quarterly Audit Committee meetings |  |  | Juaboso |  |  |  |  | 12,000.00 |  |  |  |  | Ongoing | Audit committee |  |  |  |  |  |
| Management and administration | General administration | Provide financial support for anti-corruption activities |  |  | Juaboso |  |  |  |  | 10,000.00 |  |  |  | New |  | NACAP Desk Officer |  |  |  | Central Admi, CHRAG, NCCE |  |
| Management and administration | General administration | Financial management and revenue training mobilization for Area councils |  |  | Juaboso |  |  |  |  | 11,000.00 |  |  |  | New |  | Finance Dept |  |  |  |  |  |
| Focus area: Security and public safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and administration | General administration | Provide financial support for conflict and DISEC activities |  |  | District wide |  |  |  |  | 11,000.00 |  |  |  |  | Ongoing | JDA |  |  |  |  | Security Agencies |
| Management and administration | General administration | Sensitize the public on violent extremism, security consciousness through radio and community visits |  |  | Juaboso |  |  |  |  | 15,000.00 |  |  |  | New |  | NCCE, GPS |  |  |  |  | Central Admi |
| Management and administration | General administration | Construction of 2No. Police check points |  |  | Selected Communities |  |  |  |  | 350,000.00 |  |  |  | New |  | GPS |  |  |  |  | Central Admi |
| Focus area: IMPLEMENTATION, CO-ORDINATION, MONITORING AND EVALUATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Prepare 2026-2029 MTDP |  |  | Juaboso |  |  |  |  | 30,000.00 |  |  |  | New |  | DPCU |  |  |  |  | JDA |
| Management and Administration | Planning, Budgeting and Coordination | Prepare 2026 composite budget and procurement plan |  |  | Juaboso |  |  |  |  | 35,000.00 |  |  |  | New |  | DPCU |  |  |  |  | JDA |
| Management and Administration | Planning, Budgeting and Coordination | Organize 4 DPCU meetings |  |  | Juaboso |  |  |  |  | 24,000.00 |  |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Organize 4 Town Hall meetings for 35 males and 25 females |  |  | Juaboso |  |  |  |  | 45,000.00 |  |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Ensure Monitoring of all development projects/programmes |  |  | Juaboso |  |  |  |  | 40,000.00 |  |  |  | New |  | DPCU |  |  |  |  |  |
| Management and Administration | Planning, Budgeting and Coordination | Prepare and disseminate M&E reports |  |  | Juaboso |  |  |  |  | 15,000.00 |  |  |  | New |  | DPCU |  |  |  |  |  |